PRIME STUDIOS F-AUTH-1 FIX-PLANNING DOCUMENT First fix after audit close. Tier 0 keystone. Six-step coordinated single-PR plan.

Document version

v2.32 — Step 3 CP7 (Storyteller + memories + franchiseBrain Q13 — 17 source files / 153 handlers / 148 promotions / 10 new test files / 157 new tests / 6 integration test updates / 1 single session — collapsed from 2-3 session forecast despite 1.85x scope-expansion outlier) approved at commit 10577813, auto-merged to dev at 44474a08. CP7 SCOPE-EXPANSION OUTLIER (D11 lock): forecast 8-10 files / 80-100 handlers vs actual 17 files / 153 handlers — driver was src/routes/memories/ sub-directory with 8 sub-routers (engine.js alone has 23 handlers + 11 unique AI POSTs). NEW v2.32 §5.4 RETROACTIVE CP7 scope correction. NEW v2.32 §5.56 scope-expansion outlier marker methodology. CP7 architectural firsts (12): LARGEST mount-collision yet — Collision A2 at /api/v1/memories with 7 active routers + 8 sub-routers (NEW v2.32 §5.34 amendment); 3rd cumulative §5.21 mixed Tier 1+4 instance — franchiseBrainRoutes.js (1st worldStudio @ CP3; 2nd universe @ CP6; 3rd franchiseBrain @ CP7) PATTERN-LOCKS to production-tooling-cluster default (NEW v2.32 §5.21 amendment); 5th application of AI POST reference model — 47 AI POSTs in CP7 alone (cumulative ~92 across ~30 files post-CP7 at uniform pattern; largest cumulative single-CP application by far; NEW v2.32 §5.43 amendment); 4th consecutive frontend ideal state PATTERN-LOCKS at production-tooling-cluster default (NEW v2.32 §5.36/§5.44/§5.49 amendment); first CP since CP3 with zero sub-form (b) presence (NEW v2.32 §5.49 amendment); cleanest hygiene surface yet — zero F-AUTH-4 obsolescence (3 G4 false positives in API key error string content + system prompt content; NEW v2.32 §5.57 false-positive discipline), zero F-AUTH-5 hits, zero §5.51 Item 16 candidates (NEW v2.32 §5.51 amendment - 0-candidate result repeatable methodology); first detected legacy authenticateToken usage in CP-zone — franchiseBrainRoutes.js:560 → requireAuth + aiRateLimiter conversion (NEW v2.32 §5.53 legacy authenticateToken conversion discipline); largest lazy-noop residue cleanup yet — 13 files (CP6 had 7); cross-coupling discovered — memories/engine.js:23 imports buildKnowledgeInjection + getTechContext from franchiseBrainRoutes.js (NEW v2.32 §5.54 cross-coupling commit-ordering signal); custom rate-limiter preservation pattern — memories/assistant.js preserves bespoke assistantLimiter alongside canonical aiRateLimiter (NEW v2.32 §5.55 custom rate-limiter preservation discipline; defer-to-Track-8 consolidation); 7th backend Step 3 data point with scope-expansion outlier marker (CP7 single-session despite 1.85x scope; mean ~85min ±10min holds across 7 data points if scope-corrected; CP7 raw ~85min within mean band). Surface-correction graduates to 27 cumulative data points across CP15 + CP1 + CP2 + CP3 + Track 7 mini-CP + CP4 + CP5 + CP6 + CP7 (CP7 contributed 4 corrections: scope expansion 1.85x; assistantLimiter discovery; G4 false-positive triage; engine.js AI endpoint count refinement 14→11 unique). Backend test suite: 1808 → 1965 passing (+157 tests vs +160-180 forecast — near lower edge; 0 regressions). Integration test §5.52 discipline 2nd application — 6 storyEvalV2 anonymous-request assertions updated to expect 401 (cumulative 10 with CP6\'s 4; NEW v2.32 §5.52 amendment). Out-of-scope concerns confirmed not touched at CP7: Show Bible / Season Arc disconnect + goal_summary stale + decision_log triple parallel + multiple seed strategies + archetype taxonomy drift + storybook_proposals canon-mutation policy + stories standalone-first principle — none affect auth disposition. Step 3 CP8 (Social-feeds per v2.23 §5.4) is next — fresh session after v2.32 lands on dev. NO Track 7 mini-CP coordination needed at CP7 (frontend ideal state — 4th consecutive PATTERN LOCK).

Author

JAWIHP / Evoni — Prime Studios

Status

G2 IN PROGRESS — Tracks 1, 1.5, 1.6, 2 (A+B), 2.5, 3 (Stage 1 + Stage 2), 4 complete. Track 6 IMPLEMENTATION CLOSED — CP2-CP15 COMPLETE (04777edd). 466 sites migrated, 466/469 = 99.4% by site count = 100% of migratable scope. 38 deferred-by-discipline sites remain (Path E LOCKED PUBLIC + 6 Pattern G + 2 external blob). Step 3 backend sweep is next phase.

# 1. Executive Summary

F-AUTH-1 is a codebase-wide auth bypass on writes. It is the Tier 0 keystone in audit handoff v8 §4.1. Every other P0 fix re-deploys mutation routes; re-deploying mutation routes without auth ships the bug fix and the unauth surface together. v8 is explicit: partial execution is worse than no change. This plan ships all six steps in one coordinated PR.

Why this fix is one PR — not six Steps 1–2 (F-Auth-2, F-Auth-3) harden the auth module itself. Steps 3–5 are the mechanical sweep across three sub-forms. Step 6 is the frontend coordination (sendBeacon + interceptor strings) that prevents silent 401s the moment the sweep lands. If sub-form (a) ships before sub-form (c), every episode-mutation surface still bypasses auth. If the sweep ships before CZ-5, BookEditor.jsx silently 401s on every beforeunload save. If the sweep ships before F-Auth-4 reconciliation, mid-session token refresh stops working. The six steps interlock.

### Scope summary

- Fix the codebase-wide auth bypass on writes by closing all three F-AUTH-1 sub-forms.

- Harden middleware/auth.js so misconfiguration is loud (boot-fail) and Cognito outages are distinguishable from anonymous traffic.

- Coordinate the frontend so requireAuth landing does not silently break mid-session refresh or beforeunload saves.

- Close F34 automatically (it is sub-form a inside franchiseBrainRoutes.js).

- Close F-Auth-5 (req.user.sub vs req.user.id drift) as a folded-in sub-step of Step 6.

### Out of scope (deferred)

- F-Auth-6 — tokenUse (access vs ID token) gating. Informs but does not block. Deferred to follow-up.

- Director Brain build (F-Franchise-1 resolution). Sequenced after F-AUTH-1 + structural prerequisites per Decision #94.

- Any of the 269 P0 correctness findings outside auth. Sequenced after Tier 0.

# 2. Keystone Precedence (why this is the first fix)

Prime Studios Audit Handoff v8 locks F-AUTH-1 as Tier 0. The reasoning, restated from §4.1 and §12 of v8: every other P0 fix touches mutation routes. Shipping a P0 fix to a route that still accepts unauthenticated writes ships the security exposure with the correctness fix. Therefore: every correctness fix is blocked on auth.

v8 also makes the partial-execution warning explicit (§4.1, end of recipe). Closing optionalAuth without fixing F-Auth-2 ships a server that silently 401s every authenticated request when env vars are missing. Closing the sweep without F-Auth-3 means a Cognito outage looks identical to anonymous traffic. Closing the sweep without CZ-5 means BookEditor.jsx beforeunload saves silently 401 on every page navigation. Closing the sweep without F-Auth-4 reconciliation means the frontend interceptor cannot distinguish AUTH_REQUIRED from AUTH_INVALID_TOKEN and mid-session refresh degrades silently.

F34 disposition F34 (unauthenticated destructive writes on /franchise-brain/*) was hotfix-offered May 1, 2026 and DECLINED to maintain audit discipline (Decision #34). v8 reaffirms: F34 closes automatically inside Step 3 (sub-form a) of this plan. No separate F34 hotfix ships. The exposure window is being closed, not patched around.

# 3. The Six Steps

All six steps land in a single PR. Each step has its own §4.x detail section below. The steps are listed here in dependency order; the implementation order is given in §5.

| # | Finding | What it does | Surface |
| --- | --- | --- | --- |
| 1 | F-Auth-2 | Throw at module load if Cognito env vars are absent. Boot-fail beats silent 401s on every authenticated request. | middleware/auth.js:13–22, :44–46 |
| 2 | F-Auth-3 | Distinguish "Cognito down" from "anonymous user" in optionalAuth. Stop swallowing all errors. Add an alarm signal. | middleware/auth.js:164–168 |
| 3 | Sweep (a) | Replace optionalAuth → requireAuth on every write route currently using optionalAuth. F34 closes here. | app.js:364 + per-route |
| 4 | Sweep (b) | Add requireAuth to write routes with NO auth middleware declaration at all. | outfitSets.js + episodes.js:101/109/117 |
| 5 | Sweep (c) | Replace optionalAuth → requireAuth on episode-mutation routes that explicitly declare optionalAuth. | episodeOrchestrationRoute.js:135 |
| 6 | CZ-5 + F-Auth-4 + F-Auth-5 | Migrate sendBeacon → fetch+keepalive. Reconcile requireAuth/authenticateToken duplication with frontend interceptor. Close req.user.sub/req.user.id drift. | BookEditor.jsx:173–186 + middleware/auth.js:256–293 + decisionLogs.js:22 |

# 4. Step Details

## 4.1 Step 1 — F-Auth-2: Boot-fail on missing Cognito env vars

### Current behavior

middleware/auth.js:13–22 constructs Cognito ID-token and access-token verifier objects at require() time using process.env.COGNITO_USER_POOL_ID || 'us-east-1_XXXXXXXXX' and process.env.COGNITO_CLIENT_ID || 'xxxxxxxxxxxxxxxxxxxxxxxxxx'. The runtime check at lines 44–46 only fires inside verifyToken — it does not fire at boot. A misconfigured deploy with missing env vars produces a server that boots cleanly and 401s every authenticated request with a generic “Token verification failed” error and no diagnostic hint that env vars are absent.

### Why it must ship before the sweep

- Once Steps 3–5 land, every write route requires a valid token. If a deploy is missing Cognito env vars, those routes 401 silently with no operator-visible cause.

- The placeholder verifier objects make the failure mode look like a token problem, not an env-var problem. Triage gets pointed at the wrong layer.

### Fix

- Add a top-of-module check in middleware/auth.js that throws if either COGNITO_USER_POOL_ID or COGNITO_CLIENT_ID is undefined or matches the placeholder string.

- The throw must happen at require() time, before the verifier objects are constructed.

- Throw text must name the missing variable explicitly so deploy logs make the cause obvious.

- Remove the placeholder fallback strings entirely once the throw is in place — they exist only to defer the failure to runtime.

### Verification

- Boot the app locally with both env vars unset → expect immediate startup failure with a named error.

- Boot with one env var set, one unset → expect immediate startup failure naming the missing variable.

- Boot with both env vars set to real values → expect normal startup.

### Risk

- Risk: a dev or prod environment that was running on placeholder values breaks immediately on first deploy of this PR. Mitigation: env vars confirmed in pre-flight (§5.1) — dev and prod both verified at G1.

## 4.2 Step 2 — F-Auth-3: Distinguish Cognito-down from anonymous

### Current behavior

middleware/auth.js:164–168 — optionalAuth swallows all errors and sets req.user = null with a console.warn. Routes that gate behavior on req.user (characterDepthRoutes:88 isAuthor, characterRegistry author-only field gate ~600) silently degrade to the unauthenticated path during a Cognito outage. No alarm fires. Response codes are identical to legitimate anonymous traffic. This is a service-availability finding, not just security.

### Why it must ship with the sweep

- Once requireAuth replaces optionalAuth on writes, the failure mode for those routes becomes 401-on-Cognito-outage instead of silent-degradation. That is correct.

- But routes that legitimately remain on optionalAuth (genuine read-where-auth-is-optional) still need to differentiate "no token" from "Cognito broken" so the gating logic does not silently flip during outages.

### Fix

- In optionalAuth, catch token-verification errors separately from "no Authorization header" and "header but verifier rejected as invalid token".

- Preserve the underlying verifier error via Error.cause when verifyToken rethrows. Without this preservation, the inner aws-jwt-verify error class is lost and optionalAuth cannot classify the failure mode. Detection in the classifier should match by error.name and error.code (not instanceof) to survive bundler/module-loading edge cases. (Confirmed during Step 2 implementation; recorded here so Step 6b reconciliation does not undo it.)

- On verifier-throws-unexpected-error (Cognito timeout, DNS failure, JWKS unreachable): log at error level with a structured grep-friendly format, and return 503 with code AUTH_SERVICE_UNAVAILABLE — do NOT silently degrade to req.user = null. EXCEPTION: the degradeOnInfraFailure flag (see below).

- On no-Authorization-header: req.user = null is correct, no log needed.

- On invalid-token: req.user = null with a quiet log (use console.log("[F-Auth-3] optionalAuth: token rejected", …) — codebase ESLint config forbids console.debug; do not add lint suppressions or new dep).

### degradeOnInfraFailure flag (v1.6 amendment)

Step 2 implementation surfaced a real edge case: a few optionalAuth routes are genuine public reads (manuscript-export.js, press.js per pre-flight §7.2 exemption list) that do NOT read req.user at all. For those routes, returning 503 during a Cognito outage is a regression — anonymous users would no longer be able to read the press kit or download a published manuscript just because the auth service is degraded. Public-read availability should not be coupled to auth-service health.

Resolution: optionalAuth accepts an options object with a degradeOnInfraFailure boolean.

- Default: false. Preserves the strict §4.2 behavior — Cognito outage returns 503 instead of silently degrading to anonymous. This is correct for routes that gate on req.user (most current optionalAuth users) because silent degradation hides the failure.

- When degradeOnInfraFailure: true: Cognito outage falls back to req.user = null and continues. The structured error log still fires (visibility preserved); only the 503 response is suppressed.

- Usage: routes pass the option at mount time, e.g., router.get('/path', optionalAuth({ degradeOnInfraFailure: true }), handler).

- Step 3 sweep applies this option to the genuine-public-read exemption list (the routes pre-flight §7.2 tagged for // PUBLIC: comments). All other optionalAuth-using routes get the default behavior (503 on outage).

- Pre-flight §7.2 exemption list maps directly: pageContent.js GETs (already correct under default), manuscript-export.js GETs (need degradeOnInfraFailure: true), press.js GETs (need degradeOnInfraFailure: true). Other routes pre-flight surfaced as candidates remain default (strict 503) unless their route file explicitly justifies the flag with a // PUBLIC: comment.

### Metric mechanism — DECIDED

Pre-flight confirmed Prime Studios has no metrics library in the codebase (no prom-client, statsd, opentelemetry, or in-house helper). Adding one mid-PR is scope creep. Decision: use a stable, grep-friendly structured log line in the format: console.error("[F-Auth-3] cognito_unreachable", { name, code, message, path, method, degraded }). The degraded field is boolean: true when the request fell through to anonymous via degradeOnInfraFailure, false when 503 was returned. Operators can wire this to a CloudWatch Logs metric filter, ELK/Loki count query, or PM2 log-monitor to derive the alarm signal §4.2 calls for. Real metric library is filed as P1 follow-up if/when needed; the call site is a single line so the swap is trivial.

### Implementation note — wrapper vs. cause (LOCKED, do not regress)

The structured log payload's name and code fields come from the matching cause via a classifier helper (findCognitoInfraCause(err)), NOT from the wrapper error directly. Reasoning: verifyToken wraps verifier errors via Error.cause to preserve information across the rethrow boundary. The wrapper itself has name='Error' and code=undefined, which would render the log payload useless if logged directly. The classifier walks the cause chain matching on name (set: FetchError, NonRetryableFetchError, JwksNotAvailableInCacheError, WaitPeriodNotYetEndedJwkError) or code (set: ECONNREFUSED, ETIMEDOUT, ENOTFOUND, EAI_AGAIN, ECONNRESET, EHOSTUNREACH, ENETUNREACH) and returns the matching error. The wrapper's message is preserved separately because it carries the readable "Token verification failed: ..." prefix.

Future maintainers may be tempted to log error.name directly because the wrapper is the immediate object in scope. Do not. The first draft of Step 2 hit this and the test suite caught it. Lock as canon.

### Tests (G3 prerequisite — added in Step 2)

- Unit tests added at tests/unit/middleware/auth-gaps.test.js (or equivalent) covering four cases:

  - Case 1 — no Authorization header → req.user = null, no 503, no log spam

  - Case 2 — token rejected (verifier throws JwtInvalidClaimError or similar) → req.user = null, single console.log, no 503

  - Case 3 — Cognito infra error (FetchError, ECONNREFUSED, etc.) with default options → 503 with code AUTH_SERVICE_UNAVAILABLE, structured console.error fired

  - Case 4 — Cognito infra error with degradeOnInfraFailure: true → req.user = null, structured console.error still fired (visibility), no 503

- Tests run as part of CI before G2 closes. G3 self-review confirms all four pass.

### Verification (G4)

- Hit a route under optionalAuth (default options) with no Authorization header → req.user = null, no log spam.

- Hit it with a malformed token → req.user = null, single quiet log only.

- Simulate Cognito unavailability (e.g., point JWKS URI at an invalid host) → expect 503 with AUTH_SERVICE_UNAVAILABLE, structured error log fired.

- Hit a route configured with degradeOnInfraFailure: true under simulated Cognito unavailability → expect 200 (or whatever the public route returns), structured error log still fired, no 503.

### Risk

- Step 3 sweep must correctly apply degradeOnInfraFailure: true to the exemption list. If applied wrongly (e.g., to a route that does gate on req.user), that route silently degrades during outages — exactly the bug F-Auth-3 was meant to prevent. Mitigation: every route receiving the flag gets a // PUBLIC: comment in Step 3 with the reasoning.

- Error.cause requires Node ≥ 16.9. package.json specifies "node": ">=20.0.0" — fine. Note here so a future Node downgrade triggers a check.

## 4.3 Step 3 — Sweep sub-form (a): optionalAuth → requireAuth on writes

### Current behavior

app.js:364 applies app.use(optionalAuth) globally. Individual write routes either redundantly re-apply optionalAuth (storyteller.js, careerGoals.js, uiOverlayRoutes.js, calendarRoutes.js, characterRegistry.js, evaluation.js, wardrobe.js — and many more confirmed across Zones 18–26) or do nothing — meaning the global mount IS the bypass on those routes.

### Confirmed surfaces (from v8 audit)

| File | Lines / count | Audit zone |
| --- | --- | --- |
| app.js | :364 (global mount) | Zone 21 (cross-zone root) |
| storyteller.js | :38–43 (require), :53, :113, :192, :213, :241, :263, :312, :333, :354, :553, :615, :636, :663, :738, :769, :790, :826, :856, :880, :910 | Zone 20 |
| characterRegistry.js | ~1700 lines; requireAuth applied to ONE legacy route (/deep-profile/generate); every other write under optionalAuth — set-status, promote-to-canon, bulk-delete, bulk-status, bulk-move, JSONB PUTs, AI generation endpoints | Zone 21 |
| evaluation.js | :587 (Stats save) | Zone 22 |
| careerGoals.js | every mutation route | Security Batch / Zone 22 |
| uiOverlayRoutes.js | every mutation route | Security Batch |
| calendarRoutes.js | event CRUD, auto-spawn, world-event spawn | Security Batch |
| franchiseBrainRoutes.js | 10 mutation routes (entries POST/PATCH/DELETE, activate, activate-all, archive/unarchive, ingest-document, guard, seed) | F34 root |
| wardrobe.js | :895 (/select), :970 (/purchase) and others | Zone 23 |

Notes:

- The list above is the audit-confirmed inventory. Pre-flight (§5.1) requires a fresh codebase grep to catch any optionalAuth uses added since v8 closed (May 1, 2026).

- characterRegistry.js has a no-op fallback in its require block (lines 12–22) if the auth module fails to load. The fallback must be removed as part of this step — it is the same anti-pattern as F-Auth-2.

### Fix

- For every confirmed surface above and every match found in pre-flight grep: replace optionalAuth with requireAuth.

- Where optionalAuth is applied at app.js:364 globally and individual routes do NOT re-declare it, add explicit requireAuth at the route level.

- After the per-route requireAuth is in place, remove the global optionalAuth mount at app.js:364 — leaving it creates two passes through auth and confuses error handling.

- Remove no-op fallback require blocks (characterRegistry.js:12–22 and any twin instances).

- For routes confirmed during pre-flight as genuinely public (read-only, no req.user gating downstream), document the exemption in a comment with the audit reasoning. Do not leave bare optionalAuth without a justifying comment.

- For each genuine-public-read exemption, also pass optionalAuth({ degradeOnInfraFailure: true }) instead of bare optionalAuth (per §4.2 amendment). This preserves availability of public reads during Cognito outages. The // PUBLIC: comment justifying the exemption should also reference the flag, e.g., // PUBLIC: published canon, no req.user gating; degradeOnInfraFailure preserves availability during Cognito outages.

### F34 absorbed here

All 10 mutation routes on franchiseBrainRoutes.js close in this step. Decision #33 / #34 are honored: F34 closes as part of the sweep, not as a separate hotfix. The push-from-page route (already requireAuth) is the model the rest of the file conforms to.

### Verification

- Pre-flight grep result list (§5.1 deliverable) is fully addressed — every entry either swapped to requireAuth or commented as a justified exemption.

- Zero matches for optionalAuth on a write route with no comment. Run:

grep -rE "optionalAuth" src/routes/ src/app.js | grep -E "(post|put|patch|delete)" | grep -v "// PUBLIC:"

- Authenticated request to a previously-unauth route returns 200 with req.user populated.

- Unauthenticated request to the same route returns 401 with AUTH_REQUIRED.

## 4.4 Step 4 — Sweep sub-form (b): write routes with NO auth declaration

### Current behavior

Zone 23 confirmed routes/outfitSets.js declares no auth middleware on any of its 5 routes. routes/episodes.js mounts the plural outfit-set controller at lines 101, 109, 117 with no auth declaration. Same blast radius as sub-form (a) — different starting state.

### Confirmed surfaces

- routes/outfitSets.js — all 5 routes (no auth middleware declared anywhere in file).

- routes/episodes.js:101 — mounts plural outfit-set controller without auth.

- routes/episodes.js:109 — same pattern.

- routes/episodes.js:117 — same pattern.

- Pre-flight (§5.1) requires a sweep for any other route file that does not import auth middleware at all.

### Fix

- Add requireAuth import at the top of routes/outfitSets.js.

- Apply requireAuth to all 5 outfitSets routes.

- Apply requireAuth at routes/episodes.js:101, :109, :117.

- Note: F-Ward-3 keystone (Decision #60) calls for deleting the plural outfit-set controller — it is dead code wired to live URLs (Pattern 47, the this. binding bug crashes every create). The F-AUTH-1 PR should still apply requireAuth to these routes; deletion is a separate post-AUTH PR. Reasoning: leaving them open during the AUTH PR window is a security exposure; deleting them is a structural change that warrants its own review.

### Verification

- grep for "router\.(post|put|patch|delete)" in routes/outfitSets.js → every match has requireAuth.

- Pre-flight grep produces no untouched routes.

## 4.5 Step 5 — Sweep sub-form (c): episode-mutation routes that declare optionalAuth

### Current behavior

Zone 26 confirmed a third sub-form: episodeOrchestrationRoute.js:135 explicitly declares optionalAuth on its mutation handler. The handler at line 220 writes orchestration_data to the episodes table. This is distinct from sub-form (a) because the route file has its own optionalAuth declaration — sweeping the global app.js mount alone does not touch it.

### Confirmed surfaces

- episodeOrchestrationRoute.js:135 — declares optionalAuth on episode-mutation handler.

- Pre-flight (§5.1) requires a sweep for any other route file that explicitly declares optionalAuth on a mutation route. v8 named only the orchestration route, but the audit closed before a comprehensive grep of this sub-form across the full codebase.

### Fix

- Replace optionalAuth with requireAuth at episodeOrchestrationRoute.js:135.

- Apply same fix to any additional sub-form (c) instances pre-flight grep identifies.

### Verification

- Authenticated POST/PUT to the orchestration route returns 200 with req.user populated and writes to episodes.orchestration_data succeed.

- Unauthenticated POST/PUT returns 401 with AUTH_REQUIRED.

## 4.6 Step 6 — CZ-5 (sendBeacon) + F-Auth-4 (interceptor reconciliation) + F-Auth-5 (user-id drift)

### CZ-5 — sendBeacon current behavior

BookEditor.jsx:173–186 uses navigator.sendBeacon for the beforeunload save. sendBeacon cannot carry Authorization headers. The moment Steps 3–5 land, every BookEditor beforeunload save silently 401s — and silently fails to save the user’s last edits before navigation. This is a data-loss path, not just an auth-noise path.

### CZ-5 — fix

- Replace navigator.sendBeacon with fetch(url, { method: ..., headers, body, keepalive: true }). The keepalive flag preserves the request through page navigation, the same property sendBeacon was used for.

- Confirm the Authorization header is added by the existing api service interceptor — sendBeacon was bypassing the interceptor entirely.

- Test: trigger beforeunload → confirm request fires with Authorization header → confirm 200 response in network log → confirm save persisted on next page load.

### F-Auth-4 — current behavior

middleware/auth.js:256–293 reimplements authenticateToken with one differing string: AUTH_REQUIRED instead of AUTH_INVALID_TOKEN. The frontend interceptor differentiates on these strings to decide whether to wipe credentials and redirect (per the comment at lines 250–255). Two parallel auth-checking code paths must be kept in sync.

### F-Auth-4 — fix (Path 1 LOCKED, Maximum scope locked v1.9)

v1.9 amendment: the Step 6b prep inventory (commit a9c8b36e on dev, F-AUTH-1_Step6b_Inventory.md) revealed that "the frontend interceptor" referenced in v1.8 is actually FOUR parallel auth-injection paths, not one. v1.8 §4.6 was written assuming a single interceptor; reality is more complex. v1.9 expands Step 6b scope to Maximum: collapse all four paths into one (axios apiClient).

### Backend changes (unchanged from v1.8)

- Delete the duplicate authenticateToken implementation at middleware/auth.js:256–293.

- Have requireAuth emit two distinct error codes: AUTH_REQUIRED when no Authorization header is present, AUTH_INVALID_TOKEN when a header is present but verifier rejects the token.

- Migrate every existing authenticateToken call site to requireAuth. Pre-flight inventory found 103 mount sites across 17 files. Top-volume files (must not be missed):

  - episodes.js (14 sites — including the D17 special case at :307–315 which currently uses optionalAuth as a workaround for the very contract problem Path 1 fixes; swap to requireAuth)

  - stories.js (9), search.js (9), notificationController.js (9)

  - thumbnails.js (7), socketController.js (7), activityController.js (7)

  - Plus 10 additional files. Pre-flight report §14.1 carries the full inventory.

- Touch the lazy-import fallbacks too: characterRegistry.js:17 and worldEvents.js:28 use authenticateToken as a defensive fallback. Update both to fall back to requireAuth instead.

- Drop the dead alias at middleware/auth.js:237 (exports.authenticate = authenticateToken). Pre-flight confirmed zero callers (Decision D21). One-line cleanup in the same commit as the duplicate removal.

### Frontend changes (Maximum scope — v1.9)

The frontend has four parallel auth-injection paths per the inventory:

- Path A — authHeader() (singular) from frontend/src/utils/storytellerApi.js. ~34 call sites across 7 files.

- Path B — axios apiClient from src/services/api.js with response interceptor at lines 41–73. ~563 call sites across 53 files. The de facto standard.

- Path C — authHeaders() (plural) — local helper functions duplicated across 7 files plus a shared one in pages/feed/feedConstants.js. ~75 call sites.

- Path D — inline Bearer ${token} construction. ~25+ call sites across ~17 files.

- Plus ~478 raw fetch() calls without auth-header injection — see Track 5 below for triage.

Step 6b implementation runs as four tracks in sequence. Track 5 (raw-fetch triage) runs before the migration tracks so any auth-required-but-missing-bug findings can adjust scope before code lands.

### Track 5 — Raw fetch() triage (FIRST, sequential before migration)

- Audit ~478 raw fetch() calls in frontend/src/. Classify each as:

  - (a) Intentionally public — read-only published data, no auth needed. Annotate with // PUBLIC: comment matching backend Step 3 exemption convention.

  - (b) Auth-required-but-missing — bug. Auth was needed but never wired up. These get migrated to apiClient as part of Step 6b.

  - (c) Unclear — cannot determine intent from the call site. Surface for review; default to apiClient migration if uncertain.

- Triage produces an updated inventory file with classifications. Commit on dev (docs work), not feature/f-auth-1.

- Triage findings can adjust the migration scope. If many (b)-class bugs surface, the migration becomes "the four paths + the bugs." If almost all are (a), the migration is just the four paths.

### Track 1 — apiClient interceptor update (Path B, 563 sites covered automatically)

- Update the response interceptor in src/services/api.js to handle the unified F-Auth-4 contract:

  - AUTH_REQUIRED (no header) → redirect to login.

  - AUTH_INVALID_TOKEN (header rejected) → attempt token refresh once via the existing refresh path; on refresh failure, redirect to login.

  - Pass-through (LOCKED): AUTH_INVALID_FORMAT, AUTH_GROUP_REQUIRED, and AUTH_ROLE_REQUIRED MUST NOT trigger session-redirect logic. Display inline as user-facing errors. Reasoning preserved from v1.8. (AUTH_ROLE_REQUIRED added in v2.1 per Track 1 surface §3.3 — jwtAuth.js emits it, code-before-status check covers it correctly.)

- Implementation note (v2.1, locked from Track 1 commit da604ed2): check error.response.data.code BEFORE error.response.status. Pass-through codes can be 400 or 403, not just 401 — code-first dispatch handles them correctly regardless of status.

- Single-retry guard: AUTH_INVALID_TOKEN retries refresh once (originalConfig._retried flag). If retry still fails, wipe + redirect. Refresh-endpoint URL itself excluded from retry to prevent recursion.

- Refresh helper uses bare axios.post(), NOT apiClient — this bypasses the interceptor for refresh requests, avoiding circular auth.

### Track 1.5 — Frontend test scaffolding (NEW v2.1)

Track 1 surfaced (§3.1) that the frontend has never run a test. vitest is in package.json but no vitest.config.js, no jsdom, no .test files exist. ESLint v9 is broken because .eslintrc.js is the v8 format and not auto-detected. G3 gate ("test coverage minimum") is unenforceable on the frontend until this is fixed.

- Establish frontend test scaffolding before Tracks 2/3/4/6/7 land. Each later migration commit then includes tests for the migrated call sites in the same commit — that is how G3 becomes enforceable for the ~556-site migration.

- Deliverables for Track 1.5:

  - Add vitest.config.js with environment: jsdom (or happy-dom — pick whichever has cleaner DOM emulation for our use case).

  - Add jsdom (or happy-dom) to devDependencies.

  - Write frontend/src/services/api.test.js covering the 5 interceptor cases:

    - Case A — AUTH_REQUIRED triggers wipeSessionAndRedirect, no retry.

    - Case B — AUTH_INVALID_TOKEN first hit triggers refresh, request retries with new token.

    - Case C — AUTH_INVALID_TOKEN on retry triggers wipeSessionAndRedirect (no infinite loop).

    - Case D — AUTH_INVALID_FORMAT / AUTH_GROUP_REQUIRED / AUTH_ROLE_REQUIRED do NOT trigger redirect, pass through as caller errors.

    - Case E — non-auth errors (500, network, etc.) pass through unchanged.

  - Mock localStorage, window.location.href, and axios.post (for refresh path).

- ESLint v9 migration is OUT of scope for Track 1.5. .eslintrc.js → eslint.config.js is a separate concern; pre-flight or post-F-AUTH-1 follow-up. Track 1.5 only adds test runner scaffolding; lint config stays as-is.

- Estimated: ~10 lines vitest config + 1 devDep + ~150 lines test file = single commit. Reviewed and approved before Track 1.6 begins.

### Track 1.6 — Backend requireAuth split (NEW v2.1)

Track 1 surfaced (§3.2) that backend requireAuth currently emits AUTH_REQUIRED for both no-header AND verifier-rejected cases — never AUTH_INVALID_TOKEN. The Track 1 interceptor's refresh-on-AUTH_INVALID_TOKEN branch is wired correctly but fires for nothing on requireAuth routes today (only authenticateToken legacy middleware emits AUTH_INVALID_TOKEN, at auth.js:126).

- Track 1.6 closes the contract end-to-end before migration tracks land. Without it, Tracks 2/3/4/6/7 migrate call sites that depend on the new contract working correctly — and they would silently log users out on token expiry instead of refreshing.

- Deliverables for Track 1.6 (backend, src/middleware/auth.js):

  - In requireAuth: emit four distinct error codes based on what was wrong with the request:

    - No Authorization header → 401 with code AUTH_REQUIRED (current behavior; preserved)

    - Authorization header present but malformed (not 2 parts or not "Bearer ...") → 401 with code AUTH_INVALID_FORMAT (v2.3 amendment — see below)

    - Header valid format, verifier rejected token → 401 with code AUTH_INVALID_TOKEN (NEW)

    - Header valid format, Cognito infra failure → 503 with code AUTH_SERVICE_UNAVAILABLE (existing F-Auth-3 path; preserved)

  - Use the same Cognito-vs-rejected classifier landed in Step 2: findCognitoInfraCause(err) → if matches, this is an infra failure; else this is a token-rejection (emit AUTH_INVALID_TOKEN).

- Add unit tests for the split:

  - No header → 401 + AUTH_REQUIRED

  - Malformed header → 401 + AUTH_INVALID_FORMAT (v2.3 amendment — matches authenticateToken; Track 1 interceptor pass-throughs)

  - Header + valid token → 200 + req.user populated

  - Header + verifier-rejected token → 401 + AUTH_INVALID_TOKEN (NEW)

  - Header + Cognito infra failure → 503 (already covered by Step 2 tests; verify no regression)

- Once Track 1.6 lands, the F-Auth-4 Path 1 contract is complete on requireAuth routes: frontend interceptor + backend codes both speak the new vocabulary. Mid-session token expiry now triggers refresh, not logout.

### Track 1.6 — AUTH_INVALID_FORMAT amendment (v2.3, locked from commit e0b03d18)

Track 1.6 was originally specced (v2.1) with three outcomes: AUTH_REQUIRED / AUTH_INVALID_TOKEN / AUTH_SERVICE_UNAVAILABLE. The malformed-header case (header present but not in "Bearer <token>" 2-part format) was inherited as AUTH_REQUIRED from prior code. Track 1.6 implementation review surfaced this as a contract mismatch:

- A logged-in user whose code accidentally sends a malformed Authorization header receives 401 AUTH_REQUIRED.

- Track 1 frontend interceptor reads AUTH_REQUIRED → wipes session and redirects to /login.

- Net effect: a client-side integration bug punts the user to login. The user IS logged in (the header is set); they should see an inline error, not a session redirect.

Resolution: requireAuth emits AUTH_INVALID_FORMAT for the malformed-header case (matches authenticateToken's existing behavior at auth.js:98). The Track 1 interceptor already pass-throughs AUTH_INVALID_FORMAT per LOCKED §4.6 (the user sees the error inline, no redirect). The contract is now end-to-end consistent across all four codes:

- AUTH_REQUIRED → frontend redirects to login (correct: user is not logged in)

- AUTH_INVALID_FORMAT → frontend pass-through, inline error (correct: user IS logged in, integration bug)

- AUTH_INVALID_TOKEN → frontend refreshes-then-redirects (correct: user was logged in, token expired, auto-recover or escalate)

- AUTH_SERVICE_UNAVAILABLE → frontend caller decides UX (correct: not a session issue)

- Implementation note: response message and error label aligned to authenticateToken's existing AUTH_INVALID_FORMAT response for cross-middleware consistency. A 4-line comment at the malformed-header branch in auth.js documents the WHY, preventing future maintainers from "fixing" it back to AUTH_REQUIRED.

- Track 1.6 does NOT touch authenticateToken (which already emits AUTH_INVALID_TOKEN and AUTH_INVALID_FORMAT). authenticateToken is removed entirely later in Step 6b backend cleanup per §4.6 backend changes (LOCKED v1.8) — the duplicate at middleware/auth.js:256–293 is deleted.

- Estimated: middleware change + tests = single commit. Reviewed and approved before Track 2 begins.

### Pre-existing message-leak fix (silently closed in Track 1.6)

Pre-Track-1.6 requireAuth's catch block returned message: error.message to clients — the wrapped verifier error message ("Token verification failed: JwtExpiredError: ..." etc.) leaked verifier internals. Track 1.6's refactor hardened this to a generic "The provided token is invalid or expired." message. Verifier internals stay in server-side logs only via the structured [F-Auth-4] requireAuth: token rejected log line. Net effect: small information-leak surface closed as a side effect of the spec'd work. Documented here so future readers see the fix was intentional, not silent.

### Track 2 — Migrate Path A (authHeader) to apiClient (LOCKED v2.5, COMPLETE)

- 34 call sites across 7 files. Replace fetch + ...authHeader() spread with apiClient method calls.

- Tested change. Each migration must preserve: HTTP method, URL, payload shape, response shape consumption. Add tests for any migrated path that did not have them.

- Once migration is complete: delete authHeader() export from frontend/src/utils/storytellerApi.js. Confirm zero remaining imports before deletion.

Track 2 implementation pattern (LOCKED v2.5 from commits 501cd737 + 59f9868a + a079a04b) — helper-internal migration covers transitive call sites with zero touches: if a Path A site is reached via a wrapping helper (e.g., api() in storytellerApi.js), migrate the helper's internals to call apiClient while preserving the helper's external contract (return shape, error throw shape). All transitive call sites are migrated by changing one helper. Use this pattern wherever Tracks 3/4/6/7 encounter wrapping helpers — saves linear-scan migration work.

Track 2.5 amendment (v2.5): for direct call sites that aren't reached via a wrapping helper, extract small module-scope const helpers from inline apiClient.X(url, payload) invocations into 1-4 line export const helperName = (args) => apiClient.method(url, payload) definitions. Tests import the helpers directly and verify call shape. This avoids full RTL component-render setup. Pattern proven across 8 helpers in 3 files (SectionEditor, StoryPlannerConversational, BookEditor) with zero RTL setup required. Apply pattern to Tracks 3/4/6/7 when migrated sites need behavioral test coverage.

- Track 2 keepalive exception (LOCKED v2.5) — BookEditor.jsx:181 (the beforeunload save established by Step 6a per CZ-5) cannot migrate to apiClient. axios does not support keepalive: true; the request must survive page unload to satisfy CZ-5's data-loss-prevention contract. Migration converts this site from Path A (...authHeader spread) to Path D (inline Bearer ${token}) with a 6-line in-code comment explaining the exception. This is the only Path D site that has a documented engineering reason to remain after Track 4 lands. Track 4 verification grep must allowlist this site.

### Track 3 — Migrate Path C (authHeaders plural duplicates) to apiClient (LOCKED v2.6, COMPLETE)

- 75 call sites across 9 files. Seven files define their own local authHeaders() helper; one shared in feedConstants.js used by SocialProfileGenerator.jsx (~40 sites alone) and ProfileDetailPanel.jsx.

- Migration consolidates the seven duplicate helpers AND migrates call sites to apiClient. Two-stage:

  - Stage 1: replace each local authHeaders() helper with apiClient calls at the call site. Delete the local helper.

  - Stage 2: migrate the shared authHeaders() in feedConstants.js + its consumers (SocialProfileGenerator.jsx, ProfileDetailPanel.jsx) to apiClient. Delete the shared helper.

- Pre-flight inventory noted subtle drift between copies (useStoryEngine.js accepts an extra param; others do not). The migration eliminates this drift surface.

Track 3 architectural findings (v2.6, locked from commits c6047c46 Stage 1 + 69f0a926 Stage 2):

- Five subtly different authHeaders() implementations dissolved into one apiClient interceptor contract. Pre-migration shapes: A (Content-Type + optional Auth + 3-fallback), B (A + dead extra= param), C (Content-Type + always-Auth + no token guard), D (Content-Type + optional Auth + 2-fallback), E (Auth-only, relied on Express default JSON parse). Post-migration: uniform via apiClient. Drift surface eliminated.

SessionStorage fallback was unreachable code. 5 of 7 helpers fell back through localStorage.authToken || localStorage.token || sessionStorage.token. Stage 1 §5 investigation found zero write sites for sessionStorage.token anywhere in the codebase — the third fallback was never reachable. apiClient's 2-fallback (localStorage.authToken || localStorage.token) covers every reachable token path. No interceptor change needed. The sessionStorage.getItem('token') pattern persists in 7 Path D files (App.jsx, SidebarProgress.jsx, FeedBulkImport.jsx ×2, NarrativeControlCenter.jsx, ProductionTab.jsx, WorldStudio.jsx) plus feedConstants.js getToken(); Track 4 will scrub these as it migrates the dependents.

Helper-name shadow conflicts when extracting Track 2.5-style helpers — Pattern F locked in §9.11. SocialProfileGenerator.jsx had 11 component-local handlers whose names matched proposed module-scope exports. Resolution: Api suffix on the network helpers (finalizeProfileApi, crossProfileApi, etc.). Component handlers stay unchanged — they wrap the network helper plus UI state updates. Convention applies wherever Tracks 4/6 encounter files where component handler names mirror endpoint operation names.

### Track 4 — Migrate Path D (inline Bearer) to apiClient (LOCKED v2.7, COMPLETE)

- 25+ call sites across ~17 files. Replace inline Bearer ${token} construction with apiClient method calls.

- Cohabiting files (apiClient + inline Bearer in the same file): ProductionTab.jsx, WorldAdmin.jsx. The inline Bearer sites in these files are accidental drift, not intentional dual-paradigm. Convert all to apiClient.

- Special case: FeedBulkImport.jsx mixes Path C local helper + Path D inline. Track 3 + Track 4 work converges in this file.

LOCKED EXCEPTION (v2.5 — Track 2 surfaced) — BookEditor.jsx:181 is the only Path D site that survives Track 4. The beforeunload save (Step 6a / CZ-5) requires keepalive: true; axios does not support keepalive, so apiClient cannot replace it without breaking CZ-5's data-loss-prevention contract. The site has a 6-line in-code comment documenting the exception, and a regression-lock test (Track 2.5) that asserts apiClient.post/put/request are NOT called when the keepalive helper fires. Track 4 must preserve this site, allowlist it in the verification grep, and not "fix" it.

getToken() handoff from Track 3 (LOCKED v2.6) — pages/feed/feedConstants.js exports a getToken() function that reads the same 3-fallback chain (with the unreachable sessionStorage). Track 3 Stage 2 deleted the shared authHeaders() but kept getToken() because seven Path D files import it: App.jsx, SidebarProgress.jsx, FeedBulkImport.jsx (×2 sites), NarrativeControlCenter.jsx, ProductionTab.jsx, WorldStudio.jsx. Track 4 migrates these seven files to apiClient (which doesn't need getToken because the request interceptor reads localStorage directly). Once all seven importers are migrated, getToken() has zero callers and gets deleted from feedConstants.js as Track 4's final cleanup commit. After that deletion, the unreachable sessionStorage code path is fully eliminated from frontend production code.

Pattern F applies (LOCKED v2.6 §9.11) — when extracting Track 2.5-style helpers from Track 4 files where component handler names mirror endpoint operation names, suffix the module-scope helper with Api. Track 3 Stage 2 surfaced this in SocialProfileGenerator.jsx (11 shadow conflicts resolved with the suffix). Tracks 4 and 6 will hit similar patterns in larger files — apply the convention from the start.

Track 4 architectural findings (v2.7, locked from commits 08a24fec migration + 06beb1d1 getToken deletion):

25 active sites migrated across 19 files (1 site preserved per locked exception). The only inline-Bearer construction in frontend production code is now BookEditor.jsx:55 — the CZ-5 keepalive helper, with 3 protective regression-lock tests (Track 2.5 lock). All other auth injection now flows through the apiClient request interceptor.

Inventory v2 scope correction — WorldStudio headers() helper covered 3 sites, not 32. Track 4 surface re-read found the helper is scoped to the CharacterFollowsTab sub-component (line 468) with 3 callers, not module-scope wrapping all 32 file fetches. The other 29 fetches in WorldStudio.jsx are unrelated unauth Path E candidates (filed in §9.12). Surface-before-execute discipline caught the misclassification before any code changes.

BookEditor keepalive line corrected — inline-Bearer literal is at line 55, not line 181. Track 2.5's extraction of sendKeepaliveBeforeUnload to module scope moved the literal from inline component-body (pre-2.5 line 181) to the helper definition (post-2.5 line 55). v2.5/v2.6 references to BookEditor.jsx:181 are stale. v2.7 verification grep allowlist updated to BookEditor.jsx:55. Track 2.5 regression-lock tests (3 tests in BookEditor.test.jsx) cover the corrected line.

templateService stale-token bug self-resolved — inadvertent fix as side effect of the migration. templateService.js cached this.token = localStorage.getItem('authToken') at construction time; re-login mid-session left the service using the stale token (inventory v2 §8.7 surfaced). Migration to apiClient eliminates the bug because the request interceptor reads localStorage fresh on every call. Same pattern as Track 1.6's pre-existing message-leak silent-fix: surface explicitly so it's not "silent."

NarrativeControlCenter.fetchJSON contract change — shipped behavioral change worth flagging. Pre-Track-4 fetchJSON returned res.json() unconditionally including on non-2xx responses (callers received error bodies as if successful). Post-Track-4 fetchJSON throws on non-2xx via apiClient. All 17 callers verified to follow the happy-path await fetchJSON(...).then(data => check shape) pattern; none rely on receiving error bodies. Net effect: silent error-body returns eliminated; error handling now consistently flows through try/catch. Documented in fetchJSON's docblock.

getToken() handoff was unnecessary — dead code, not dependent code. v2.6 §4.6 Track 4 spec assumed seven Path D files imported getToken from feedConstants.js; Track 4 surface grep found zero importers anywhere in the codebase. The seven Path D files reimplemented the 3-fallback chain inline rather than importing the helper. feedConstants.getToken() was dead code through the entire F-AUTH-1 work and likely through prior history. Deleted in commit 06beb1d1 as the final Track 4 cleanup. The unreachable sessionStorage code path is now fully eliminated from frontend production code.

Pattern F applied prophylactically — did not trigger. Track 4 surface flagged WorldAdmin.jsx (6000+ lines, not read end-to-end) as a Pattern F candidate. During migration, no shadow conflicts surfaced in WorldAdmin, ProductionTab, or WorldStudio. Conservative-application discipline correct: the cost of preparation was zero (naming convention from the start), the cost of mid-flow discovery would have been a refactor. Pattern F stays as canon for Track 6.

### Track 6 — Migrate BUG-class raw fetches to apiClient (NEW v2.0)

v2.0 amendment: Track 5 triage (commit a929ce29 on dev, F-AUTH-1_Step6b_Inventory_v2.md) reclassified ~478 raw fetch() calls. Found 345 BUG-class sites — auth-required-but-missing. These would silently 401 the moment Step 3 sweep lands. Track 6 closes them by migrating to apiClient.

Why this is in F-AUTH-1 (not deferred): Step 3 sweep transforms backend optionalAuth → requireAuth. The 345 BUG-class fetches today get unauth'd responses (which the routes serve under optionalAuth). The moment Step 3 lands, those routes return 401. Every user hitting these features sees broken writes, blank pages, silent failures. Shipping Step 3 without Track 6 actively breaks the product. That is worse than not shipping F-AUTH-1.

### Track 6 — priority order (10 high-density files first, ~180 of 345 sites)

- 1. SceneSetsTab.jsx (64 sites). Single-file cluster. SceneSetRoutes.js will Step-3-sweep to requireAuth; this page would silently break for every user. Migrate first.

- 2. WriteMode.jsx (33 sites). /storyteller/* writes.

- 3. FranchiseBrain.jsx (18 sites). All 9 franchise-brain mutations bare. F34 closure depends on this file.

- 4. StoryThreadTracker.jsx (11 sites). Thread writes.

- 5. CharacterGenerator.jsx (10 sites).

- 6. ContinuityEnginePage.jsx (10 sites).

- 7. Episodes/EpisodeScenesTab.jsx (9 sites).

- 8. TemplateDesigner.jsx (9 sites).

- 9. CharacterTherapy.jsx (9 sites).

- 10. SeriesPage.jsx (8 sites).

- Remaining ~165 sites distributed across ~60 other files at 1-8 sites each. Track 6 continues file-by-file in priority order (highest count first) until 0 BUG sites remain.

- Each file becomes its own commit per Pace 2 batched checkpoints. SceneSetsTab.jsx alone is ~64 sites in one file — that single file is one commit and gets reviewed before the next file starts.

### Track 6 multi-session pacing model (NEW v2.8)

CP2 (SceneSetsTab.jsx) execution surfaced that high-density files cannot complete in one conversation session. The 64 sites in SceneSetsTab.jsx are not 64 simple inline migrations — they are 64 fetch+state-update+toast+callback chains, each embedded in different surrounding state-management contexts. Per-site migration cost (read 15-30 lines of context, write a state-preserving Edit, sometimes trace downstream consumers) consumes meaningfully more conversation budget than a single-session checkpoint can absorb.

Pacing model amended (LOCKED v2.8): a checkpoint spans sessions for high-density files. The model is:

- Session 1 through Session N: Claude Code migrates as far as available budget allows. Each session lands WIP commits on feature/f-auth-1. WIP commits are NOT pushed to backup — they are private progress markers across sessions.

- Final session: when the file is fully migrated (all sites + tests + verification grep), Claude Code squashes the WIP commits into a single coherent CP commit. Sends report. I review. Approve. Backup push.

- This preserves the original review-once-per-checkpoint discipline. It just acknowledges that "checkpoint" does not mean "single conversation turn" for high-density files.

- Estimated session counts: CP2 (SceneSetsTab, 64 sites) — 3-4 sessions. CP3 (WriteMode, 33 sites + 3,721 lines + Pattern F max density) — 2-3 sessions. CP4 (FranchiseBrain, 18 sites) — likely 1 session. CP5/CP6/CP7 mid-tier — 1 session each. CP8 long-tail — 1 session if the simpler-site hypothesis holds (1-3 sites per file, less surrounding state-management); multi-session if not. Total Track 6 session estimate: 8-12 sessions. Total commit count when squashed: 7-10 (unchanged from CP1 plan; squashing preserves clean history).

WIP commit discipline: each WIP commit must leave the working tree in a clean state — file compiles, no half-edits in the middle of a function, no dangling syntax errors. WIP commits are private to feature/f-auth-1 and never go to backup until the checkpoint is complete. Pre-push hook should still pass on each WIP commit (it does today; existing async-handler warnings are informational and stay informational).

### Per-site cost estimation in surface reports (NEW v2.8)

CP1 surface report estimated structural shape (uniform vs clustered, wrapping helpers vs direct, Pattern F risk) but did not estimate per-site migration cost. The 64-vs-64 site count match was correct as raw fetch count; the cost-per-site was 5-10x higher than expected because each site is embedded in a state-management chain. Surface reports for future high-density files (CP3+) must include per-site cost estimation.

- Surface report deliverable for high-density files (>20 sites): in addition to site count and structural shape, sample 3-5 representative sites and estimate per-site migration cost. Cost factors: (a) lines of context required to migrate safely, (b) presence of state-update chains, (c) downstream consumer tracing requirements, (d) Pattern F suffix-resolution overhead. The estimate informs session-count planning per the multi-session pacing model.

- Inventory v2 (Track 5 commit a929ce29) counted raw fetch literals only. It is correct as a count but undersells migration cost on dense files. Future tracks should treat inventory site counts as a lower bound on work, not a complete estimate.

### Track 6 CP2 architectural findings (LOCKED v2.9, COMPLETE — SceneSetsTab.jsx)

CP2 completed at commit 30a15d05 (squashed from 4 WIP commits across multiple sessions per the v2.8 pacing model). 64/64 sites migrated, 39 module-scope helpers added with Pattern F Api suffix. 45 new behavioral tests added; full frontend suite at 180/180 passing. Backed up at 30a15d05 on claude/f-auth-1-backup.

3 HTTP method corrections caught mid-flow — shipping bugs, not migration choices. CP2 surfaced three sites where the original fetch used the wrong HTTP method against the backend route. The migration documented the correct method in the helper definition; the original wrong method has been shipping to production. Filed in §9.12 for Step 3 sweep awareness.

- setCoverAngleApi — backend route is PATCH; original code used GET. Backend tolerated it (or the path wasn't reaching execution) — the migration uses PATCH per backend contract.

- reorderAnglesApi — backend route is PATCH; original code used POST. Same disposition.

- getAiCameraDirectionApi — backend route is POST; original code used GET. Same disposition.

Pattern: BUG-class migrations surface pre-existing HTTP method mismatches. The migration writer should use the correct method per backend contract (it is a regression to preserve a wrong method) and surface the original wrong method in the report. Don't analyze why the original was wrong — the migration's job is correctness, not forensics. Step 3 sweep will further audit each route's contract.

- Pattern F prophylactic discipline confirmed correct. CP2 surfaced 8 component-handler shadow-conflict prone names (handleCreate, handleDeleteSet, handleSetCoverAngle, handleAddAngle, handlePreviewPrompt, handleUploadAngleImage, handleCascadeRegenerate, handleReorderAngle); the Api suffix on every helper from the start avoided 8 mid-flow refactors. Future high-density files (CP3 WriteMode, CP4 FranchiseBrain) apply Pattern F prophylactically from the first extraction per same discipline.

- Multi-session pacing model worked as designed. WIP commits across sessions, squash before approval, single CP2 commit at the end. Each session was a clean handoff via WIP commit hash. The 96cc3341 → 97808e97 → b328226b → 30a15d05 progression preserved progress without polluting the eventual squashed commit's history.

### Track 6 CP3 architectural findings (LOCKED v2.10, COMPLETE — WriteMode.jsx)

CP3 completed at commit b0127817 (squashed from 3 WIP commits across 3 sessions per the v2.8 pacing model). 31/33 sites migrated to apiClient via 17 module-scope helpers with Pattern F Api suffix. 2 sites retained as locked exceptions (streaming SSE — see Pattern G below). 25 new behavioral tests added; full frontend suite at 205/205 passing across 19 test files. Backed up at b0127817 on claude/f-auth-1-backup.

- Pacing model validated against two data points. CP2 (SceneSetsTab, 64 sites) completed in 4 sessions (~16 sites/session). CP3 (WriteMode, 33 sites + 2 streaming exceptions) completed in 3 sessions (~11 sites/session — slightly slower per-site cadence due to higher state-management complexity per site, plus the streaming exception adjudication in Session 2). The v2.9 §4.6 forecast of "2-3 sessions" for CP3 held at the upper bound. The model holds for high-density files; CP4 (FranchiseBrain, 18 sites, lower density) is forecast at 1 session per same model.

- Pattern F prophylactic discipline confirmed correct (second data point). CP3 surfaced ~20 component-handler shadow-conflict prone names (saveDraft, generateSynopsis, generateTransition, generateProse, loadReferenceChapter, loadReviewLines, approveLine, rejectLine, saveLineEdit, saveTocSections, deleteTocSection, approveAll, handleContinue, handleDeepen, handleNudge, handleParagraphAction, handleChapterInstruction, commitAddChapter, commitTocRename, syncLinesToDraft); Pattern F suffix on every helper from the start avoided ~20 mid-flow refactors. The discipline is now validated across two files (CP2 + CP3); apply prophylactically to all high-density files going forward.

Streaming SSE exception class surfaced (Session 2) — Pattern G locked in §9.11. WriteMode.jsx had two sites that use Server-Sent Events (SSE) to stream Claude AI generation incrementally: WriteMode.jsx:980 (voice-to-story) and WriteMode.jsx:1145 (story-continue in handleContinue). Both use fetch() + res.body.getReader() for incremental response-body reads. axios cannot stream response bodies in browsers (only in Node), so these sites cannot migrate to apiClient. Both retained as locked exceptions per the BookEditor.jsx:55 keepalive precedent: raw fetch + inline Bearer auth from localStorage + 9-line documenting comment + verification-grep allowlist.

- Implementation byte-identical across both streaming sites; only the endpoint path and payload differ. The 9-line comment template explains the SSE streaming requirement, the axios constraint, the inline-auth approach, and points at the v2.10 §4.6 + §9.11 canon. Future maintainers see the comment, do not "fix" by attempting apiClient migration.

- No HTTP method mismatches surfaced in CP3 (CP2 caught 3; CP3 caught 0). No Path E candidates surfaced. No bugs surfaced. Multi-session pacing handoffs (2a021cf2 → 22ab7a4e → b0127817 squashed) were clean.

- CP3 squashed commit message follows the canonical Track 6 closing format: file name, sites migrated count, exceptions count and rationale, helpers added, test count, "Closes Track 6 CP3" marker. Future CPs follow same template.

### Track 6 CP4 architectural findings (LOCKED v2.11, COMPLETE — FranchiseBrain.jsx; F34 CLOSED at call site)

CP4 completed at commit 11a82876 (single commit, single session — 1-session forecast held exactly per v2.10 §4.6). 18/18 sites migrated to apiClient via 11 module-scope helpers with Pattern F Api suffix. 20 new behavioral tests added; full frontend suite at 225/225 passing across 20 test files. Backed up at 11a82876 on claude/f-auth-1-backup.

F34 from audit handoff v8 — CLOSED at the call site by this commit. Server-side enforcement closes via Step 3 backend sweep on franchiseBrainRoutes.js (optionalAuth → requireAuth swap). The push-from-page route was already requireAuth and is the model the rest of the file conforms to per v2.10 §4.4. F34 marked closed in §9.12.

- Pattern F prophylactic discipline confirmed correct (third data point). 4 direct shadow conflicts (unarchiveEntry, activateEntry, archiveEntry, deleteEntry handlers ↔ same-named *Api helpers) cleanly avoided. ~7 indirect operation-name overlaps prevented from surfacing mid-flow. Discipline now validated across three files (CP2 + CP3 + CP4); apply prophylactically to all high-density and operation-named files going forward.

- Pattern G NOT triggered — verified zero SSE / keepalive / streaming markers in FranchiseBrain.jsx. Three Pattern G sites total in F-AUTH-1 scope (BookEditor.jsx:55, WriteMode.jsx:980, WriteMode.jsx:1145). No new Pattern G sites added.

- Throw-on-error idiom cleanup applied at every site. apiClient request interceptor handles non-2xx; the surrounding component-level try/catch already routed errors to showToast. Net: -2 LOC per site typical, -85 deletions total against +79 insertions in source file.

- Two-reload pattern (load() + loadCounts() after every entry mutation) preserved verbatim across unarchiveEntry, handleCreate, activateEntry, archiveEntry, deleteEntry, bulkActivate. UI-state-refresh discipline outside Track 6 scope.

- Promise.all parallelism preserved in loadCounts (4 GETs) and bulkActivate (filtered list). loadCounts collapsed from two-stage Promise.all (fetches + .json() parses) to one stage because axios returns parsed data directly — net cleanup.

- Error message fallback strengthened: showToast(e.message || 'Failed to <op>', 'error') preserves caller-thrown text when present and provides operation-named fallback when apiClient errors don't carry a message.

- Path E candidates surfaced: 8 GET sites on /franchise-brain/* (entries listing ×6 + documents + amber-activity) filed for §9.12 Step 3 sweep awareness. CP4 read suggests all are auth-required (LalaVerse internal knowledge); Step 3 backend audit will adjudicate per-route disposition.

- No HTTP method mismatches surfaced (CP2 caught 3, CP3 caught 0, CP4 caught 0). File-level variation expected per v2.9 §9.12 finding pattern.

### Pacing model validated against three data points (UPDATED v2.11)

Three checkpoints across Track 6 high-density / mid-density work:

- CP2 (SceneSetsTab.jsx, 64 sites): 4 sessions, ~16 sites/session. Highest density file. Per-site state-management complexity (fetch+state+toast+callback chains) drove session-count up.

- CP3 (WriteMode.jsx, 33 sites + 2 Pattern G exceptions): 3 sessions, ~11 sites/session. State-management complexity per site higher than CP2; two-stage saveDraft, fire-and-forget patterns, closure captures, thenable rewrites, plus mid-flow Pattern G surface adjudication.

- CP4 (FranchiseBrain.jsx, 18 sites): 1 session, 18 sites/session. Lower-density file with no state-management chains, no fire-and-forget, no closures, no Pattern G triggers. Throughput at the upper end of the band.

Throughput band: 11-18 sites/session, modulated by file's state-management complexity. The cost-class predictor (simple/medium/complex distribution from surface report) is now a reliable input to session-count forecasting. CP5+ uses this band for forecasting:

- Files with state-management chains, fire-and-forget, closure captures: forecast 11-13 sites/session (CP3 zone)

- Files with simple shape (mostly direct fetch + setState + reload): forecast 15-18 sites/session (CP4 zone)

- Files with combined density and complexity: forecast 14-16 sites/session (CP2 zone)

- CP5 mid-tier targets per v2.10 CP1 priority order: StoryThreadTracker.jsx (~10 sites), EpisodeScenesTab.jsx (~10 sites), SeriesPage.jsx (~8 sites). Three files at 8-10 sites each. CP5 surface report will adjudicate whether they cluster into one CP commit (if Pattern F surfaces are similar across them) or split into CP5/CP6/CP7 (if files are independent in their migration shape).

### Track 6 CP5 architectural findings (LOCKED v2.12, COMPLETE — mid-tier batch)

CP5 completed at commit c306ad4d (single squashed commit, 3 file-boundary WIPs collapsed; single session). 28/28 sites migrated across three files via 27 module-scope helpers with Pattern F Api suffix (helpers duplicated locally per file, 4 cross-file overlaps with CP2 SceneSetsTab handlers preserved as duplicates per file-local convention). 37 new behavioral tests added; full frontend suite at 262/262 passing across 23 test files. Backed up at c306ad4d on claude/f-auth-1-backup.

Per-file breakdown:

- frontend/src/pages/StoryThreadTracker.jsx — 11 sites, 11 helpers, 14 tests. Idiom: if (res.ok) { ... } collapsed (apiClient interceptor handles failure via thrown error caught by component-level catch).

- frontend/src/components/Episodes/EpisodeScenesTab.jsx — 9 sites, 9 helpers (3 duplicated from CP2), 11 tests. Idiom: success-envelope { success, data, error } preserved verbatim via res.data?.success.

- frontend/src/pages/SeriesPage.jsx — 8 sites, 7 helpers (1 duplicated from CP2), 12 tests. Idiom: if (!res.ok) throw removed (apiClient interceptor throws). Error path strengthened to read err.response?.data?.error || err.message preserving pre-migration 4xx body exposure.

File-local helper convention LOCKED v2.12. Helper modules are file-local; cross-file imports are not used in F-AUTH-1 even when endpoints overlap. Validated against 4 cross-file duplications in CP5 (3 in EpisodeScenesTab: listSceneSetsApi, suggestAnglesApi, createAngleApi + 1 in SeriesPage: listShowsApi). Each duplicated helper is ~3 LOC; total drift surface ~12 LOC. Rationale: each CP commit's helper module is self-contained per CP2/CP3/CP4 precedent; cross-file imports would break test-per-file isolation; bounded duplication is cheaper than coupling.

- Pattern F prophylactic discipline confirmed correct (fourth data point). All three CP5 files had LOW direct-shadow density (zero direct conflicts; ~15 indirect operation-name overlaps total). Suffix from first extraction kept the migration mechanical. Discipline now validated across four files (CP2 + CP3 + CP4 + CP5 batch); apply prophylactically to all Track 6 files going forward.

- Pattern G NOT triggered — verified zero SSE / keepalive / streaming markers across all three files. Three Pattern G sites total in F-AUTH-1 scope remain (BookEditor.jsx:55, WriteMode.jsx:980, WriteMode.jsx:1145). No new Pattern G sites added.

- Throw-on-error idiom cleanup applied where applicable (StoryThreadTracker, SeriesPage). Success-envelope preservation applied where applicable (EpisodeScenesTab). Three different idioms migrated cleanly per file with no cross-contamination.

- Promise.all parallelism preserved in StoryThreadTracker (fetchThreads, fetchVoice) and SeriesPage (load). Sequential POST loop in EpisodeScenesTab.generateAngles preserves await semantics inside for...of.

- Path E candidates surfaced from CP5: ~10 GET sites filed for §9.12 Step 3 sweep awareness. Distribution: 6 GETs on /storyteller/* (StoryThreadTracker), 3 GETs on /episodes/:id/* + /scene-sets (EpisodeScenesTab), 3 GETs on /universe/series + /storyteller/books + /shows (SeriesPage). The /shows GET is consistent with CP2's migration (already auth-required disposition).

- No HTTP method mismatches surfaced (CP2 caught 3, CP3-CP5 caught 0). The three method-correction findings remain a CP2-specific finding pattern; later CPs running cleanly on this dimension.

- CP5 squashed commit message follows the canonical Track 6 closing format with the mid-tier-batch variant: per-file site count breakdown, helpers added, tests added, "Closes Track 6 CP5" marker.

### Pacing model — 4 data points validated, multi-file batch effect (NEW v2.12, supersedes v2.11 §4.6 3-data-point band)

Four checkpoints across Track 6 high-density / mid-density work:

- CP2 (SceneSetsTab.jsx, 64 sites): 4 sessions, ~16 sites/session. Highest density single file with state-management complexity.

- CP3 (WriteMode.jsx, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session. Single file with state-management chains, fire-and-forget, closure captures, mid-flow Pattern G adjudication.

- CP4 (FranchiseBrain.jsx, 18 sites): 1 session, 18 sites/session. Single lower-density file with simple shape.

- CP5 (StoryThreadTracker + EpisodeScenesTab + SeriesPage, 28 sites): 1 session, 28 sites/session — exceeded the v2.11 throughput band's upper bound. Multi-file batch of simple-shape files stacked higher than predicted.

Updated throughput model — multi-file batch effect locked as a fifth predictor:

- Single high-density file with state-management chains, fire-and-forget, closure captures: 11-13 sites/session (CP3 zone)

- Single mid-density file with combined density: 14-16 sites/session (CP2 zone)

- Single lower-density simple file: 15-18 sites/session (CP4 zone)

- Multi-file batch of simple-shape files (each <600 LOC, 8-12 sites each): 25-30 sites/session (CP5 zone)

- Why CP5 exceeded the single-file throughput band: (a) all three files were simple-shape (verified pre-execution via surface report), (b) per-site cost averaged 4.7 min/site (CP4 was 5.1, CP3 was 10.7), (c) sites distributed across 3 smaller files vs concentrated in one larger file, (d) file-boundary WIP discipline gave clean per-file checkpoints, (e) no mid-flow surprises (no Pattern G, no HTTP method corrections, no architectural decisions to adjudicate during execution).

- CP6 mid-tier batch 2 targets per v2.10 CP1 priority order: CharacterGenerator.jsx, ContinuityEnginePage.jsx, TemplateDesigner.jsx, CharacterTherapy.jsx. Total estimated ~30 sites across 4 files. CP6 surface report will adjudicate whether the multi-file batch effect applies (single CP6 commit) or whether file-specific complexity argues for splitting. If shapes are similar to CP5 (all simple), single-session execution at ~25-30 sites/session is achievable. If any file has CP3-zone state-management complexity, the batch may split.

Track 6 progress as of CP5: 141 sites migrated across 5 files (SceneSetsTab 64 + WriteMode 31 + FranchiseBrain 18 + StoryThreadTracker 11 + EpisodeScenesTab 9 + SeriesPage 8). 3 Pattern G locked exceptions (BookEditor:55 + WriteMode:980,1145). Tests grew from 135 (Track 6 start) to 262 (+127). Track 6 projected total ~345 sites; current progress ~41% by site count. Remaining: CP6 mid-tier batch 2 (~30 sites across 4 files), then CP7-CP8 long-tail (~165 sites distributed across ~50 files at 1-8 each).

### Track 6 CP6 architectural findings (LOCKED v2.13, COMPLETE — mid-tier batch 2; heterogeneous-complexity batch effect validated)

CP6 completed at commit 2e3db223 (single squashed commit, 4 file-boundary WIPs collapsed; single session despite 38 sites + heterogeneous complexity). 38/38 sites migrated across four files via 35 module-scope helpers with Pattern F Api suffix (helpers duplicated locally per file; 2 cross-CP overlaps with CP3 WriteMode handlers preserved as duplicates per file-local convention). 51 new behavioral tests added; full frontend suite at 313/313 passing across 27 test files. Backed up at 2e3db223 on claude/f-auth-1-backup.

Per-file breakdown:

- frontend/src/pages/CharacterGenerator.jsx — 10 sites, 8 helpers, 12 tests. MEDIUM-HIGH cost class (CP3 zone, ~80 min) — held within 90-min hard cap. Mixed idioms (success-property checks for POSTs, if (res.ok) for GETs); preserved verbatim, no idiom cleanup. 2 distinctive patterns: nested Promise.all over batch entries (handleProposeSeeds + handleGenerateBatch), manual commit loop with double-click guard (handleCommitAll).

- frontend/src/pages/CharacterTherapy.jsx — 9 sites, 9 helpers (2 duplicated from CP3), 12 tests. Idiom: if (data.success) lowercase boolean — preserved via res.data?.success. File-local duplication of listRegistriesApi + getRegistryApi (~6 LOC).

- frontend/src/pages/ContinuityEnginePage.jsx — 10 sites, 10 helpers, 14 tests. Idiom: if (!res.ok) return collapsed (CP4 zone). Cascade pattern preserved (await loadConflicts after each beat mutation).

- frontend/src/pages/TemplateDesigner.jsx — 9 sites, 8 helpers, 13 tests. Idiom: status === 'SUCCESS' uppercase-string envelope (different from EpisodeScenesTab's lowercase success boolean) — preserved verbatim. Method-branching split: handleSave's POST/PUT branching cleanly split into createTemplateApi + updateTemplateApi with call-site conditional. setInterval polling site cleanly migrated (apiClient call inside interval callback; clearInterval semantics unchanged).

Inline-anonymous-onClick handling pattern LOCKED v2.13. When fetch sites are inline anonymous async arrow inside JSX onClick handlers, extract to module-scope helper, call from named handler function. Validated against 2 sites in CP6 (CharacterGenerator:312 + CharacterTherapy:625). Rationale: inline anonymous async arrows are anti-Pattern-D — hard to test, hard to refactor, harder to debug. Cost ~2 LOC per extraction; produces testable handler functions matching CP2/CP3/CP4/CP5 discipline.

Hardest-first execution discipline LOCKED v2.13. In multi-file batches with heterogeneous cost-class distribution, migrate the highest-complexity file first. Combined with explicit hard-cap on the hardest file (CP6 used 90-min cap on CharacterGenerator; not triggered, but available as a fail-fast diagnostic). Rationale: complexity surprises in the hardest file are most likely to force WIP-and-resume; surfacing them first preserves clean checkpoint discipline. CP6 validated this — CharacterGenerator completed within cap, the simple files batched cleanly afterward.

- Pattern F prophylactic discipline confirmed correct (fifth data point). All four CP6 files had LOW direct-shadow density. Suffix from first extraction kept the migration mechanical across heterogeneous complexity. Discipline now validated across five files (CP2 + CP3 + CP4 + CP5 batch + CP6 batch); apply prophylactically to all Track 6 files going forward.

- Pattern G NOT triggered — verified zero SSE / keepalive / streaming markers across all four files. Three Pattern G sites total in F-AUTH-1 scope remain (BookEditor.jsx:55, WriteMode.jsx:980, WriteMode.jsx:1145).

- Four different success-shape idioms across four files all migrated cleanly: mixed (CG), boolean success (CT), throw-on-error collapse (CE), uppercase SUCCESS envelope (TD). Idiom heterogeneity in a single batch is now validated as manageable; preservation discipline (preserve verbatim where applicable, collapse where applicable) holds across diverse shapes.

- Path E candidates surfaced from CP6: ~13 GET sites filed for §9.12 Step 3 sweep awareness. Distribution: 1 in CharacterGenerator, 4 in CharacterTherapy, 3 in ContinuityEnginePage, 5 in TemplateDesigner.

- No HTTP method mismatches surfaced (CP2 caught 3, CP3-CP6 caught 0). The pattern is now established: CP2 was the outlier; later CPs run cleanly on this dimension. Documented as CP2-specific finding pattern.

### Pacing model — 5 data points validated, heterogeneous-batch effect (NEW v2.13, supersedes v2.12 §4.6 4-data-point band)

Five checkpoints across Track 6 high-density / mid-density / multi-file work:

- CP2 (SceneSetsTab.jsx, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (WriteMode.jsx, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (FranchiseBrain.jsx, 18 sites): 1 session, 18 sites/session.

- CP5 (3-file uniform-simple batch, 28 sites): 1 session, 28 sites/session.

- CP6 (4-file heterogeneous batch — 1 medium-high + 3 simple, 38 sites): 1 session, 38 sites/session. Hardest-first ordering with 90-min cap on hardest file kept it single-session.

Updated throughput model — heterogeneous-batch effect locked as a sixth predictor:

- Single high-density file with state-management chains: 11-13 sites/session (CP3 zone)

- Single mid-density file with combined density: 14-16 sites/session (CP2 zone)

- Single lower-density simple file: 15-18 sites/session (CP4 zone)

- Multi-file batch of uniform simple-shape files: 25-30 sites/session (CP5 zone)

- Multi-file batch with heterogeneous complexity (mostly simple + 1 medium-high): 35-40 sites/session (CP6 zone) — NEW

- Why CP6 worked at 38 sites/session despite heterogeneous complexity: (a) hardest-first execution surfaced no surprises in CharacterGenerator (cost class held within forecast), (b) 90-min hard cap was a guardrail that didn't need to fire — diagnostic confirmation of accurate forecasting, (c) file-boundary WIP discipline gave clean checkpoints throughout, (d) file-local helper duplication kept each file self-contained, (e) idiom heterogeneity (4 different success-shape idioms across 4 files) didn't cause cross-contamination because each file's migration is structurally isolated.

- Long-tail forecast (CP7+): ~165 sites distributed across ~50 files at 1-8 sites each. Average ~3.3 sites/file. Most files will have <5 sites and migrate trivially; the challenge becomes volume and per-file overhead (read context, extract helpers, write tests, verify) rather than per-site complexity. Forecast: CP7+ uses long-tail batching (10-15 files per CP commit). Per-CP throughput: ~30-40 sites covering ~10-15 files. Total CP7+ commits estimated: 4-6 commits to clear remaining ~165 sites.

Track 6 progress as of CP6: 179 sites migrated across 9 files (SceneSetsTab 64 + WriteMode 31 + FranchiseBrain 18 + StoryThreadTracker 11 + EpisodeScenesTab 9 + SeriesPage 8 + CharacterGenerator 10 + CharacterTherapy 9 + ContinuityEnginePage 10 + TemplateDesigner 9). 3 Pattern G locked exceptions. Tests grew from 135 (Track 6 start) to 313 (+178). Track 6 projected total ~345 sites; current progress ~52% by site count — past the halfway mark. Remaining: CP7+ long-tail (~165 sites distributed across ~50 files at 1-8 each).

### Track 6 CP7 architectural findings (LOCKED v2.14, COMPLETE — long-tail batch 1; multipart-upload + internal-helper-refactor patterns surfaced)

CP7 completed at commit 75c804e4 (single squashed commit, 10 file-boundary WIPs collapsed; single session). 39/39 sites migrated across ten files via 37 module-scope helpers with Pattern F Api suffix (1 cross-CP overlap with CP3 + CP6 handlers preserved as duplicate per file-local convention). 55 new behavioral tests added; full frontend suite at 368/368 passing across 37 test files. Backed up at 75c804e4 on claude/f-auth-1-backup. Simplest-first execution order validated for long-tail batches.

Per-file breakdown:

- Home.jsx (1 site), SessionStart.jsx (1), StoryHealthDashboard.jsx (1), CommandPalette.jsx (1), PdfIngestZone.jsx (1, multipart) — 5 warm-up files cleared cadence in first ~15 min

- AICostTracker.jsx (6 sites), EpisodeTodoPage.jsx (6), AmberCommandCenter.jsx (6), CFOAgent.jsx (8), WorldDashboard.jsx (8) — 5 anchors covering 34 sites across diverse idioms

Multipart upload pattern LOCKED v2.14 (NEW — first F-AUTH-1 multipart site). PdfIngestZone.jsx uses FormData for PDF upload; pattern: pass FormData directly as second argument to apiClient.post(url, formData). Do NOT manually set Content-Type header. axios detects FormData payload and sets the multipart Content-Type with the correct boundary automatically. The pre-migration code's comment "No Content-Type header — browser sets it with boundary automatically" is preserved verbatim by axios behavior. Future Track 6 multipart sites follow the same pattern.

Internal-helper-refactor pattern LOCKED v2.14 (NEW — surfaced in WorldDashboard). WorldDashboard.jsx had its own internal safeFetch(url) wrapper used by 8 callers. Pattern: refactor the wrapper internally to use apiClient rather than migrating each caller individually. Caller-side simplicity preserved (8 callers unchanged); the migration is a single edit inside safeFetch. Future tracks encountering similar internal-fetch-wrapper patterns follow the same approach. Avoids unnecessary call-site churn.

Method-correction discovery — surface-time vs mid-flow (NEW v2.14). CFOAgent's setBudget endpoint was identified as PUT (not POST) during the surface report's sample-site analysis, NOT mid-flow during execution. This is the first method correction caught at surface time across F-AUTH-1. CP2 caught 3 mid-flow; CP3-CP6 caught 0 mid-flow; CP7 caught 1 at surface. With surface-with-cost-estimation discipline (locked v2.8 §4.6), method-correction discovery moves earlier in the workflow. The CP2 finding pattern of "BUG-class migrations surface pre-existing HTTP method mismatches mid-flow" gets an addendum: surface-report rigor catches them at surface time when achievable. Both discovery modes remain valid; surface-time is preferred.

- Pattern F prophylactic discipline confirmed correct (sixth data point). All 10 CP7 files had LOW direct-shadow density. Suffix from first extraction kept the migration mechanical even at long-tail batch composition with 10 files. Discipline now validated across six checkpoints.

- Pattern G NOT triggered — verified zero SSE / keepalive / streaming markers across all 10 files. Three Pattern G sites total in F-AUTH-1 scope remain (BookEditor.jsx:55, WriteMode.jsx:980, WriteMode.jsx:1145).

- Five distinct idioms across 10 files all migrated cleanly: thenable + .catch (Home, StoryHealthDashboard), Promise.all thenable (AICostTracker, EpisodeTodoPage), async + if(!res.ok) throw (AmberCommandCenter, parts of CFOAgent), mixed thenable + async (CFOAgent), internal helper refactor (WorldDashboard). Idiom diversity in long-tail batches validated as manageable; preservation discipline holds across diverse shapes.

- Helper reuse within a file: CP7 surfaced one example (CFOAgent.getQuickStatsApi covers 2 sites — mount + post-budget refresh). Pattern is fine; module-scope helpers are reusable from any handler in the same file.

- Promise.all parallelism preserved: AICostTracker (5 parallel GETs), EpisodeTodoPage (3 parallel GETs). With apiClient returning parsed res.data directly, the typical two-stage Promise.all (fetches + .json() parses) collapses to one stage — net cleanup.

- Path E candidates surfaced from CP7: ~12 GET sites filed for §9.12 Step 3 sweep awareness.

- CP7 squashed commit message follows the canonical Track 6 long-tail format with per-file site count breakdown, helpers added, tests added, and the new patterns surfaced (multipart, internal-helper-refactor) noted.

### Pacing model — 6 data points, long-tail batch effect at 10 files (NEW v2.14, supersedes v2.13 §4.6 5-data-point band)

Six checkpoints across Track 6:

- CP2 (1 file, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (1 file, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (1 file, 18 sites): 1 session, 18 sites/session.

- CP5 (3 files uniform-simple, 28 sites): 1 session, 28 sites/session.

- CP6 (4 files heterogeneous, 38 sites): 1 session, 38 sites/session.

- CP7 (10 files long-tail simplest-first, 39 sites): 1 session, 39 sites/session. Long-tail batch effect at higher file count held throughput band.

Updated throughput model (CP7-zone added; CP6-zone broadened):

- Single high-density file (state-management chains): 11-13 sites/session (CP3 zone)

- Single mid-density file (combined density): 14-16 sites/session (CP2 zone)

- Single lower-density simple file: 15-18 sites/session (CP4 zone)

- Multi-file batch uniform-simple shape (3-4 files): 25-30 sites/session (CP5 zone)

- Multi-file batch heterogeneous (1 medium-high + simples, 4 files): 35-40 sites/session (CP6 zone)

- Long-tail batch simplest-first (~10 files, mostly small site counts): 35-40 sites/session (CP7 zone) — NEW

- Why CP7 worked at 39 sites/session despite 10 files: (a) simplest-first execution built migration cadence in the first ~15 min via 5 single-site warm-ups, (b) anchor files were structurally simple (mostly thenable or async with throw-on-error or success-envelope idioms), (c) per-file overhead — read context, extract helpers, write tests, verify — was the dominant cost as v2.13 §4.6 forecast predicted, but didn't exceed budget at 10-file scale, (d) zero Pattern G triggers, (e) the one method correction was caught at surface, not mid-flow.

### Long-tail forecast updated to actuals (NEW v2.14, supersedes v2.13 §4.6 estimate)

CP7 inventory reconciliation against branch tip surfaced more accurate long-tail counts than v2.13's projection:

- Pre-CP7 actuals: 84 files with bare fetch sites, 325 total sites (vs v2.13 estimate of 50 files / 165 sites)

- Post-CP7 actuals: 74 files with bare fetch sites, 286 total sites

- Pattern G locked exceptions: 3 (BookEditor:55, WriteMode:980, WriteMode:1145)

- Path E cluster: 35 sites (WorldStudio.jsx 29 + locked PUBLIC 5 + UIOverlaysTab external-blob 1, all deferred to Step 3)

- Estimated BUG-class remaining for Track 6 migration: ~248 sites across ~70 files

Updated CP forecast: 4-5 more CP commits to close Track 6 long-tail (down from 8-10 estimated in v2.13). At ~35-40 sites per CP at the CP7 throughput zone, ~248 remaining sites = 6-7 more CPs by raw arithmetic; but high-density deferrals (useStoryEngine 14, WorldAdmin 11, EpisodeDetail 10) likely warrant dedicated CPs at lower throughput, balancing out to 4-5 long-tail CPs + 2-3 dedicated single-file CPs = 6-8 more CPs total to close Track 6. Trajectory remains coherent.

Track 6 progress as of CP7: 218 sites migrated across 19 files. 3 Pattern G locked exceptions. Tests grew from 135 (Track 6 start) to 368 (+233). Current progress ~63% by site count (218 / ~345). Remaining: CP8+ long-tail (~248 sites across ~70 files). CP8 candidate batch composition: world/* cluster (WorldFoundation, WorldStateTensions, SceneStudio, NovelAssembler, StoryProposer) + small filler files = ~30-35 sites. Defer high-density deferrals (useStoryEngine, WorldAdmin, EpisodeDetail) to dedicated CPs in CP9+ since each is potentially CP3-zone complexity.

### Track 6 CP8 architectural findings (LOCKED v2.15, COMPLETE — long-tail batch 2; cross-CP duplication scaling + pattern composability validated)

CP8 completed at commit e5d4355f (single squashed commit, 10 file-boundary WIPs collapsed; single session). 38/38 sites migrated across ten files via 46 module-scope helpers with Pattern F Api suffix (11 cross-CP duplications across 5 files — highest cross-CP density of any CP yet). 56 new behavioral tests added; full frontend suite at 424/424 passing across 46 test files. Backed up at e5d4355f on claude/f-auth-1-backup.

Per-file breakdown (simplest-first execution order):

- ArcTrackingPanel.jsx (1 site, thenable warm-up), NarrativeControlCenter.jsx (1, joins existing Track 4 fetchJSON), RelationshipEngine.jsx (1, registries duplicate from CP3+CP6+CP7), ChapterBrief.jsx (1, updateChapter duplicate from CP3), ImportDraftModal.jsx (1, importChapter duplicate from CP3) — 5 single-site warm-ups

- SceneStudio.jsx (6 sites, clean /world/*), NovelAssembler.jsx (6, clean /stories/*), WorldStateTensions.jsx (7, full CP7 helper duplication ×7), StoryProposer.jsx (7, registries duplicate + /memories/*), WorldFoundation.jsx (7, multipart + method-branching + 4 idiom sub-shapes — last per simplest-first)

Pattern reuse confirmed (second instances for both): multipart upload + method-branching split now validated against 2 files each. WorldFoundation.uploadMapApi is the second F-AUTH-1 multipart site (PdfIngestZone was first); pattern held with apiClient.post(url, formData) and no manual Content-Type. WorldFoundation.saveLocation's editId-conditional split into createLocationApi + updateLocationApi reused CP6 TemplateDesigner pattern, with call site doing the conditional ternary.

Existing-test-file amendment convention LOCKED v2.15 (NEW). When amending a file with existing helpers and tests, append new helpers/tests to existing files rather than creating duplicate test files. Validated against RelationshipEngine.jsx in CP8 — file already had 11 helpers (presumably from earlier track work), CP8 appended +1 helper (listRegistriesApi) and +1 test rather than creating a duplicate test file. Relevant for CP9+ — StoryEvaluationEngine.jsx and NarrativeIntelligence.jsx have existing test files from earlier tracks; same append-not-overwrite discipline applies.

Cross-CP duplication scaling validated (NEW v2.15 note). v2.12 §9.11 file-local convention scales without coupling concerns at 11 cross-CP duplications in a single CP. CP5 had 4 dups, CP6 had 2 dups, CP7 had 1 dup, CP8 had 11 dups across 5 files (~33 LOC). The test-isolation benefit dominates the LOC cost. WorldStateTensions duplicating 7 helpers from CP7 WorldDashboard is the largest single-file cross-CP duplication in F-AUTH-1; the file-local module block kept the migration mechanical.

Pattern composability validated (NEW v2.15 note). First file applying three locked patterns simultaneously: WorldFoundation.jsx applied multipart upload (v2.14) + method-branching split (v2.13) + idiom mix (mixed thenable/async/multipart) in one file. Migrated cleanly. Pattern composability was implicit in the convention library; CP8 explicitly validates that locked patterns can stack within a single file without cross-contamination. Future high-pattern-density files apply the same composability.

- Pattern F prophylactic discipline confirmed correct (seventh data point). All 10 CP8 files had LOW direct-shadow density. Suffix from first extraction kept the migration mechanical even at 11-cross-CP-duplication scale.

- Pattern G NOT triggered. One false-positive ruled out at surface (ChapterBrief comment text "downstream"). Three Pattern G sites total in F-AUTH-1 scope remain (BookEditor.jsx:55, WriteMode.jsx:980, WriteMode.jsx:1145).

- Five distinct idioms across 10 files all migrated cleanly: thenable + .catch (ArcTrackingPanel, NarrativeControlCenter), simple async (RelationshipEngine, ChapterBrief, ImportDraftModal), success-property check (SceneStudio), if-res-ok throw collapse (NovelAssembler, StoryProposer), dense one-liners mirroring CP7 (WorldStateTensions), 4-shape mix (WorldFoundation: async + thenable + multipart + method-branching).

- No HTTP method mismatches surfaced (CP3-CP6+CP8 all clean; CP7 caught 1 at surface; CP2 caught 3 mid-flow). Method-correction discovery rate is now 4/8 CPs caught zero, 1/8 caught at surface, 1/8 caught mid-flow. Pattern: surface-time discovery preferred when achievable.

- Path E candidates surfaced from CP8: ~16 GET sites filed for §9.12 Step 3 sweep awareness (with deduplication note: 3 GETs already filed by CP7 for /world/state/* family; surfaced again for completeness, not duplicated in running list).

- CP8 squashed commit message follows the canonical Track 6 long-tail format with cross-CP duplication tally + pattern reuse notes (multipart, method-branching) explicit.

### Pacing model — 7 data points, long-tail simplest-first reproducibility validated (NEW v2.15)

Seven checkpoints across Track 6:

- CP2 (1 file, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (1 file, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (1 file, 18 sites): 1 session, 18 sites/session.

- CP5 (3 files uniform-simple, 28 sites): 1 session, 28 sites/session.

- CP6 (4 files heterogeneous, 38 sites): 1 session, 38 sites/session.

- CP7 (10 files long-tail simplest-first, 39 sites): 1 session, 39 sites/session.

- CP8 (10 files long-tail simplest-first, 38 sites): 1 session, 38 sites/session. CP7 zone reproducibility validated.

CP7 + CP8 establish the long-tail simplest-first pattern as reliably reproducible at the 35-40 sites/session band for 10-file batches with idiom diversity and bounded cross-CP duplication. Two consecutive single-session executions at near-identical site counts and file counts confirm the throughput band is not a fluke. CP9+ uses this band for forecast.

- Throughput model unchanged from v2.14 — six predictors (CP3 zone 11-13, CP2 zone 14-16, CP4 zone 15-18, CP5 zone 25-30 uniform-simple, CP6 zone 35-40 heterogeneous-with-1-medium-high, CP7 zone 35-40 long-tail simplest-first ~10 files). v2.15 broadens the CP7 zone applicability via the CP8 second data point but does not introduce a new zone.

### Long-tail forecast updated to actuals — post-CP8 (UPDATED v2.15)

CP8 inventory reconciliation:

- Pre-CP8: 74 files / 286 sites (matched CP7 close exactly; no external work touched implementation files)

- Post-CP8: 64 files / 248 sites

- Path E cluster (deferred to Step 3): WorldStudio.jsx 29 + LOCKED PUBLIC 5 + UIOverlaysTab external blob 1 = 35 sites

- Pattern G locked exceptions: 3 (BookEditor:55, WriteMode:980, WriteMode:1145)

- Estimated BUG-class remaining for Track 6 migration: ~210 sites across ~58 files

Updated CP forecast: 3-4 more long-tail CPs to clear ~140 long-tail sites at CP7-zone throughput + 2-3 dedicated CPs for the remaining high-density files (useStoryEngine 14, WorldAdmin 11, EpisodeDetail 10) at CP3/CP4-zone throughput. Total: 5-7 more CPs to close Track 6. Trajectory remains coherent.

Track 6 progress as of CP8: 256 sites migrated across 29 files. 3 Pattern G locked exceptions. Tests grew from 135 (Track 6 start) to 424 (+289). Current progress ~74% by site count (256 / ~345). Remaining: CP9+ long-tail (~210 sites across ~58 files). CP9 candidate batch composition: mid-density anchors mix — TextureReviewPage (5), SocialImport (5), StoryEvaluationEngine (5, existing test file — append), StoryEngine (5), CharacterProfilePage (5), WritingRhythm (5), NarrativeIntelligence (5, existing test file from CP3 mocks — append) + small filler = ~35-40 sites. Defer high-density deferrals (useStoryEngine, WorldAdmin, EpisodeDetail) to dedicated CPs in CP10+.

### Track 6 CP9 architectural findings (LOCKED v2.16, COMPLETE — long-tail batch 3; binary-response + service-module + hook patterns surfaced)

CP9 completed at commit 1830605e (single squashed commit, 8 file-boundary WIPs collapsed; single session). 40/40 sites migrated across eight files via 41 module-scope helpers with Pattern F Api suffix (1 cross-CP duplication: SocialImport.listCharacterSocialApi from CP8 NovelAssembler). 67 new behavioral tests added; full frontend suite at 491/491 passing across 54 test files. Backed up at 1830605e on claude/f-auth-1-backup. StoryEvaluationEngine deferred to CP10 at surface time (cross-cluster + 2 cross-CP duplicates + existing structural-test-file warrants its own focused commit).

Per-file breakdown (simplest-first execution order):

- services/showService.js (5 sites, service-method internal refactor — precedence inversion), SocialImport.jsx (5, clean cluster + 1 cross-CP dup), StoryEngine.jsx (5, multi-cluster — first binary-response site at readStoryApi for ElevenLabs TTS audio), TextureReviewPage.jsx (5, texture-layer cluster — 2 helpers cover 4 sites)

- CharacterProfilePage.jsx (5, 3-way Promise.all + nested-loop fetch), useGenerationJob.js (5, hook + polling preserved), NarrativeIntelligence.jsx (5, multi-cluster — WriteMode mock conflict empirically cleared), WritingRhythm.jsx (5, URL composition concern preserved verbatim + PATCH method verified at surface)

Binary-response pattern LOCKED v2.16 (NEW — first F-AUTH-1 binary-response site). StoryEngine.readStoryApi for ElevenLabs TTS audio uses apiClient.post(url, payload, { responseType: 'blob' }). Pre-migration code did await res.blob() after fetch; axios with responseType:'blob' returns the blob directly as response.data. Future Track 6 binary-response sites (PDFs, audio, images) follow the same pattern. Joins multipart upload (v2.14) as the second non-JSON apiClient interaction pattern.

Service-module internal-refactor pattern LOCKED v2.16 (NEW — validated by showService.js). When a service module exposes the canonical accessor for an endpoint family, refactor each method's internals to use apiClient while preserving the service contract (method signatures + return shapes) unchanged for consumers. Tests use vi.mock for apiClient and call service methods directly (e.g. showService.getAllShows()). Different from page-level helper extraction. Validated at showService.js in CP9.

Hook module-scope helper pattern LOCKED v2.16 (NEW — validated by useGenerationJob.js). Helpers exported from hook module-scope as export const; consumers of the hook unchanged. Polling lifecycle preserved (3 GET sites inside useEffect-driven recursion). Different from page/component shape; same Pattern D test approach. Validated at useGenerationJob.js in CP9. Joins the page (CP2-CP8) and service module (CP9) shapes as a third structural class for helper extraction in F-AUTH-1.

showService precedence inversion (NEW v2.16 note). When a service module is the canonical accessor for an endpoint family, file-local duplicates in earlier CPs are downstream copies of the service contract, not parallel copies. showService.js is the canonical /shows accessor; CP2 SceneSetsTab + CP5 SeriesPage + CP7 (via listShowsApi) file-local duplicates exist downstream of this contract. v2.12 file-local convention still applies; this is a clarifying observation about precedence, not a new rule.

URL composition preserved-verbatim discipline (NEW v2.16 note — validated by WritingRhythm.jsx). When surface-time analysis reveals an unusual URL composition pattern (e.g., empty API base, missing /api/v1/ prefix), preserve verbatim during migration. Don't fix. Don't investigate. Surface for Step 3 audit. WritingRhythm uses const API = import.meta.env.VITE_API_URL || '' empty default + ${API}/writing-rhythm/... = relative paths without /api/v1/ prefix. Migration preserved this composition verbatim. apiClient.baseURL is also empty string. If pre-existing bug, surfaced for Step 3 audit per v2.15 §9.11 "bugs surface, don't fix" discipline.

- Pattern F prophylactic discipline confirmed correct (eighth data point). All 8 CP9 files had LOW direct-shadow density. Suffix from first extraction kept the migration mechanical across structural diversity (page + hook + service module).

- Pattern G NOT triggered. Three false-positives ruled out at surface ("downstream" comment/JSX text). Three Pattern G sites total in F-AUTH-1 scope remain (BookEditor:55, WriteMode:980, WriteMode:1145).

- NarrativeIntelligence mock conflict empirically cleared (validated at execution). CP3 WriteMode.test.jsx mock factory returns only { default: () => null }; new CP9 named exports coexist without conflict because the mock ignores them, WriteMode.jsx imports only the default, and NarrativeIntelligence.test.jsx (new in CP9) loads the real module via named imports. Verified: 491/491 tests pass including WriteMode (180 helper tests preserved) + NarrativeIntelligence (8 new tests). The default-export-only mock discipline (locked implicitly across F-AUTH-1) is validated as architecturally sound for parallel test surfaces.

- Method-correction discipline: 1 verified at surface (WritingRhythm /multi-product/:id/status PATCH confirmed against source line 192). CP7 surface-time precedent applied. Total method-correction discoveries across F-AUTH-1: 5 across 9 CPs (CP2 caught 3 mid-flow, CP7 caught 1 at surface, CP9 verified 1 at surface).

- Path E candidates surfaced from CP9: ~10 GET sites filed for §9.12 Step 3 sweep awareness (some dedup-noted from CP2/CP5/CP8).

- CP9 squashed commit message follows the canonical Track 6 long-tail format with binary-response + service-module + hook structural pattern notes + URL composition observation + WritingRhythm method verification result.

### Pacing model — 8 data points, CP7-9 zone validated as 3-consecutive-reproducible (NEW v2.16, supersedes v2.15)

Eight checkpoints across Track 6:

- CP2 (1 file, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (1 file, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (1 file, 18 sites): 1 session, 18 sites/session.

- CP5 (3 files uniform-simple, 28 sites): 1 session, 28 sites/session.

- CP6 (4 files heterogeneous, 38 sites): 1 session, 38 sites/session.

- CP7 (10 files long-tail simplest-first, 39 sites): 1 session, 39 sites/session.

- CP8 (10 files long-tail simplest-first, 38 sites): 1 session, 38 sites/session.

- CP9 (8 files long-tail simplest-first, 40 sites): 1 session, 40 sites/session. CP7-9 zone validated as 3-consecutive-reproducible across 8-10 file batches.

CP7 + CP8 + CP9 establish the long-tail simplest-first pattern as robust across file-count variation 8-10 files at the 35-40 sites/session band. Three consecutive single-session executions at near-identical site counts confirm the throughput band is reliable for forecast. v2.16 broadens the CP7-9 zone applicability: site count is the dominant predictor; file count modulates per-file overhead within the 8-10 file empirical envelope.

- Throughput model unchanged — six predictor zones. v2.16 strengthens the CP7-9 zone confidence via three data points but does not introduce a new zone. Forecast for CP10+ remains in this band for long-tail batches; high-density single-file CPs return to CP3/CP4 zone shape.

### Long-tail forecast updated to actuals — post-CP9 (UPDATED v2.16)

CP9 inventory reconciliation:

- Pre-CP9: 64 files / 248 sites (matched CP8 close exactly)

- Post-CP9: 56 files / 208 sites

- Path E cluster (deferred to Step 3): WorldStudio.jsx 29 + LOCKED PUBLIC 5 + UIOverlaysTab external blob 1 = 35 sites

- Pattern G locked exceptions: 3 (BookEditor:55, WriteMode:980, WriteMode:1145)

- Estimated BUG-class remaining for Track 6 migration: ~170 sites across ~50 files

Updated CP forecast: 3-4 more CPs to close Track 6. CP10 long-tail mid-density batch (StoryEvaluationEngine deferred-from-CP9 + StoryDashboard with API='' verification + 2-3 of TemplateStudio/CompositionDetail/StoryPlanner + 4-5 small filler = ~35-40 sites in 8-10 files). CP11 second long-tail batch with remaining mid-density + filler. CP12-13 dedicated CPs for high-density singles (useStoryEngine 14, WorldAdmin 11, EpisodeDetail 10) at CP3/CP4-zone throughput. WorldSetupGuide (8 mixed PUBLIC+BUG) likely folds into a long-tail CP since it requires per-site adjudication. Trajectory remains coherent.

Track 6 progress as of CP9: 296 sites migrated across 37 files. 3 Pattern G locked exceptions. Tests grew from 135 (Track 6 start) to 491 (+356). Current progress ~86% by site count (296 / ~345). Remaining: CP10+ (~170 sites across ~50 files). Track 6 is in the home stretch.

### Track 6 CP10 architectural findings (LOCKED v2.17, COMPLETE — long-tail batch 4; multi-pattern existing-test-file amendment + variable-URL split + 6-fold cross-CP existence)

CP10 completed at commit 85095a80 (single squashed commit, 8 file-boundary WIPs collapsed; single session). 42/42 sites migrated across eight files via 39 module-scope helpers with Pattern F Api suffix (9 cross-CP duplications across 6 files). 65 new behavioral tests added; full frontend suite at 556/556 passing across 61 test files. Backed up at 85095a80 on claude/f-auth-1-backup.

Per-file breakdown (simplest-first execution order):

- CharacterDepthPanel.jsx (4 sites, clean cluster), CulturalCalendar.jsx (4, listShowsApi 4-fold dup), NewBookModal.jsx (4, mixed clusters — getUniverseApi covers 2), CompositionDetail.jsx (6, 1 CP6 dup — generateOutputsApi covers 2)

- TemplateStudio.jsx (6, 1 CP6 dup), StoryPlanner.jsx (7, 2 CP3 dups — updateChapterApi reused 5×; highest helper-reuse), StoryDashboard.jsx (6, URL composition verbatim — second instance), StoryEvaluationEngine.jsx (5, 3 cross-CP dups + variable-URL split + structural-test-file amendment — last per simplest-first)

StoryEvaluationEngine — first multi-pattern existing-test-file amendment (LOCKED v2.17). Three locked patterns applied simultaneously to one file: (1) v2.13 method-branching split applied to URL-branching variant (line 1243 conditional URL split into getBookApi + listAllChaptersApi with caller doing ternary); (2) v2.15 existing-test-file amendment applied to a STRUCTURAL test file (fs.readFileSync against source); (3) v2.16 cross-CP duplication scaling at 6-fold (listRegistriesApi reaches highest cross-CP existence in F-AUTH-1). Existing structural assertions remain valid post-migration (apiClient import preserved, no authHeaders, internal apiPost/apiGet wrappers unchanged). vi.mock hoisted to top so it applies to dynamic imports inside the new describe block. Final: 16 tests in single file (6 Track 3 structural + 10 new CP10 helper tests), all passing.

Branching-split generalization LOCKED v2.17 (NEW). v2.13 §9.11 method-branching split (PUT vs POST conditional) generalizes to any conditional shape at the call site — method, URL, or both. Helper extraction handles each branch as a separate helper; call site does the ternary. Validated at CP6 TemplateDesigner (method-branching: PUT/POST same URL) and CP10 StoryEvaluationEngine line 1243 (URL-branching: GET different URLs based on bookId). Future tracks encountering branching at any axis follow the same convention.

Structural-test-file amendment validation LOCKED v2.17 (NEW). v2.15 §9.11 existing-test-file amendment scales to both behavioral test files (CP8 RelationshipEngine) and structural test files (CP10 StoryEvaluationEngine). For structural tests (fs.readFileSync against source asserting on shape/imports), existing assertions remain valid post-migration when migration preserves apiClient import + absence of authHeaders + internal wrappers. vi.mock hoisting required if dynamic imports are added in new describe blocks. Future tracks encountering files with structural test assertions follow the same convention.

Cross-CP existence high-water mark (NEW v2.17 note). listRegistriesApi reaches 6-fold cross-CP existence at CP10 (CP3 WriteMode + CP6 CharacterTherapy + CP7 Home + CP8 RelationshipEngine + CP8 StoryProposer + CP10 StoryEvaluationEngine). Empirical ceiling for cross-CP duplication density in F-AUTH-1. v2.12 file-local convention scales without coupling concerns up to and including 6-fold existence. Each duplicate is ~3 LOC; ~18 LOC total across all 6 files. Test isolation per file dominates LOC cost.

Pattern composability — second instance (NEW v2.17 note). CP6 WorldFoundation was first triple-pattern file (multipart + method-branching + idiom mix); CP10 StoryEvaluationEngine is the second triple-pattern file (URL-branching + existing-test-file amendment + 6-fold cross-CP duplication). Pattern composability is now validated at 2 data points across diverse pattern combinations. Patterns compose cleanly within a single file without cross-contamination, regardless of which 3 (or more) locked patterns apply.

- Pattern F prophylactic discipline confirmed correct (ninth data point). All 8 CP10 files had LOW direct-shadow density.

- Pattern G NOT triggered — verified zero across all 8 files. Three Pattern G sites total in F-AUTH-1 scope remain (BookEditor:55, WriteMode:980, WriteMode:1145).

- StoryDashboard URL composition preserved verbatim — second instance after CP9 WritingRhythm. Same shape: API='' empty default → relative paths without /api/v1/ prefix. apiClient.baseURL also empty string. v2.16 §9.11 URL composition preserved-verbatim pattern lock validated against 2 instances. Step 3 audit should adjudicate both observations together (likely the same Vite proxy or server rewrite resolution applies).

- No HTTP method mismatches surfaced (CP3-CP6+CP8-CP10 all clean mid-flow). Total method-correction discoveries across F-AUTH-1: 5 (CP2 caught 3 mid-flow, CP7 caught 1 at surface, CP9 verified 1 at surface).

- 9 cross-CP duplications across 6 files in CP10. CP8 had 11 (largest single-CP); CP10 is second-largest. Pattern: as CPs accumulate, long-tail naturally has more cross-CP overlap. v2.15 cross-CP scaling note holds — bounded duplication is benign.

- Path E candidates surfaced from CP10: ~10 GET sites filed for §9.12 Step 3 sweep awareness (many dedup-noted from CP3+/CP5/CP6/CP8).

### Track 6 denominator correction — actual scope ~469 sites vs ~345 projected (NEW v2.17, supersedes prior projections)

Self-flagged at CP10 reconciliation: the "% of Track 6 by site count" framing has been using ~345 as the denominator since v2.13. CP10 inventory reconciliation surfaces the actual Track 6 BUG-class scope is closer to ~469 sites.

Arithmetic:

- Cumulative migrated post-CP10: 338 sites (CP2 64 + CP3 33 + CP4 18 + CP5 28 + CP6 38 + CP7 39 + CP8 38 + CP9 40 + CP10 42)

- Inventory remaining at branch tip post-CP10: 48 files / 166 sites total

- Minus deferred Path E cluster: 35 sites (WorldStudio.jsx 29 + LOCKED PUBLIC 5 + UIOverlaysTab external blob 1)

- BUG-class remaining: 166 − 35 = ~131 sites

- Total Track 6 BUG-class scope: 338 + 131 = ~469 sites

Pattern observed across the project: each inventory reconciliation surfaced higher actuals than the prior projection. v2.13 estimated 50 files / 165 sites; CP7 reconciliation surfaced 84 files / 325 sites (post-CP7); v2.16 used ~345 as Track 6 denominator; CP10 reconciliation confirms ~469 actual. The projection error is acknowledged, not corrective — it does not change the tracked migration count or the per-CP actuals.

Reframed Track 6 progress: 338 / 469 = ~72% by site count after CP10 (not 98% as the ~345 denominator implied). Remaining ~131 sites across ~42 files. 5-7 more CPs to close Track 6: 3-4 long-tail CPs (CP11+ at CP7-10 zone throughput 35-42 sites/session) + 2-3 dedicated high-density singles (useStoryEngine 14, WorldAdmin 11, EpisodeDetail 10 at CP3/CP4-zone throughput) + WorldSetupGuide 8 mixed PUBLIC+BUG (likely folds into a long-tail CP since per-site adjudication is bounded).

### Pacing model — 9 data points, CP7-10 zone validated as 4-consecutive-reproducible (NEW v2.17, supersedes v2.16)

Nine checkpoints across Track 6:

- CP2 (1 file, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (1 file, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (1 file, 18 sites): 1 session, 18 sites/session.

- CP5 (3 files uniform-simple, 28 sites): 1 session, 28 sites/session.

- CP6 (4 files heterogeneous, 38 sites): 1 session, 38 sites/session.

- CP7 (10 files long-tail simplest-first, 39 sites): 1 session, 39 sites/session.

- CP8 (10 files long-tail simplest-first, 38 sites): 1 session, 38 sites/session.

- CP9 (8 files long-tail simplest-first, 40 sites): 1 session, 40 sites/session.

- CP10 (8 files long-tail simplest-first, 42 sites): 1 session, 42 sites/session. CP7-10 zone validated as 4-consecutive-reproducible at 35-42 sites/session band.

CP7 + CP8 + CP9 + CP10 establish the long-tail simplest-first pattern as thoroughly reproducible across 4 consecutive checkpoints at the 35-42 sites/session band in 8-10 file batches. The throughput band is not a fluke; it is the empirical baseline for forecast at long-tail batch composition. Site count remains the dominant predictor; file count modulates per-file overhead within the 8-10 file empirical envelope.

- Throughput model unchanged — six predictor zones. v2.17 broadens the CP7-10 zone confidence via four data points but does not introduce a new zone. Forecast for CP11+ remains in this band for long-tail batches; high-density single-file CPs return to CP3/CP4 zone shape.

### Long-tail forecast updated to actuals — post-CP10 (UPDATED v2.17)

CP10 inventory reconciliation:

- Pre-CP10: 56 files / 208 sites (matched CP9 close exactly)

- Post-CP10: 48 files / 166 sites

- Path E cluster (deferred to Step 3): WorldStudio.jsx 29 + LOCKED PUBLIC 5 + UIOverlaysTab external blob 1 = 35 sites

- Pattern G locked exceptions: 3 (BookEditor:55, WriteMode:980, WriteMode:1145)

- Estimated BUG-class remaining for Track 6 migration: ~131 sites across ~42 files

Updated CP forecast: 5-7 more CPs to close Track 6. CP11 cleanup-overlap batch (PressPublisher 4 mixed PUBLIC+BUG + CultureEvents 4 pairs with CulturalCalendar + WorldLocations 4 heavy CP8 overlap + ~6-8 small filler files = ~30-40 sites in 8-10 files). CP12 second long-tail batch with remaining mid-density + filler. CP13-15 dedicated CPs for high-density singles (useStoryEngine 14, WorldAdmin 11, EpisodeDetail 10) at CP3/CP4-zone throughput. WorldSetupGuide (8 mixed PUBLIC+BUG) likely folds into a long-tail CP since per-site adjudication is bounded. Trajectory remains coherent.

Track 6 progress as of CP10: 338 sites migrated across 45 files. 3 Pattern G locked exceptions. Tests grew from 135 (Track 6 start) to 556 (+421). Current progress ~72% by site count (338 / ~469 corrected denominator). Remaining: CP11+ (~131 sites across ~42 files). Past the two-thirds mark; well into the home stretch but more substantial work remaining than prior projections suggested.

### Track 6 CP11 architectural findings (LOCKED v2.18, COMPLETE — cleanup-overlap batch; new throughput high-water mark + mixed PUBLIC+BUG convention + combined-axis branching)

CP11 completed at commit 87460600 (single squashed commit, 17 file-boundary WIPs collapsed; single session). 51 BUG-class fetch sites migrated across seventeen files via ~37 module-scope helpers with Pattern F Api suffix. 3 sites retained per discipline: PressPublisher:119 LOCKED PUBLIC + WriteModeAIWriter:281 + AppAssistant:239 (latter two new Pattern G locked sites). 14 cross-CP duplications across 6 files — largest single-CP cross-CP duplication count in F-AUTH-1. 127 new behavioral tests added; full frontend suite at 683/683 passing across 78 test files. Backed up at 87460600 on claude/f-auth-1-backup. CP11 surface arithmetic projected 45 migrated; actual was 51 (surface understated by 6). Outcome exceeded projection; quality maintained.

Per-file breakdown (simplest-first execution, 17 files):

- Filler tier (8 fresh-helper files at 3 sites each = 24 sites): RecycleBin, PropertyManager, SiteOrganizer, SetupWizard, StoryCalendar (storyteller-scoped distinct from /calendar/* per surface correction), usePageData (hook), EpisodeDistributionTab, ContinuityGuard.

- Mid-tier with cross-CP duplications (5 files at 3 sites each = 15 sites): CharacterProfile (3 CP9 dups), LayoutEditor (1 CP6 dup), SceneInterview (1 CP3 dup, updateChapterApi 3-fold), StoryReviewPanel (1 CP9 dup).

- Anchor tier (3 files at 4 sites each = 12 sites): WorldLocations (4 CP8 dups + combined-axis branching at line 141), CultureEvents (4 CP10 dups, listShowsApi 5-fold), PressPublisher (4 sites: 1 LOCKED PUBLIC retained + 3 BUG migrated incl. URL-branching split at line 124).

- Pattern G tier (2 files at 3 sites each = 6 sites; 4 migrated + 2 locked): WriteModeAIWriter (line 281 streaming locked, lines 329 + 405 migrated), AppAssistant (line 239 streaming locked, lines 69 + 205 migrated).

Mixed PUBLIC+BUG convention LOCKED v2.18 (NEW — first F-AUTH-1 instance at PressPublisher.jsx). When a single file contains a mix of LOCKED PUBLIC and BUG-class fetch sites, apply per-site adjudication during surface analysis. LOCKED PUBLIC sites retain raw fetch with a 9-line PUBLIC comment block referencing inventory v2 §4.2 + F-Auth-3 degradeOnInfraFailure exemption list (parallel to BookEditor:55 / WriteMode:980 Pattern G locked-comment template, but for PUBLIC disposition rather than streaming). BUG-class sites in the same file migrate to apiClient with module-scope helpers per the standard Path A discipline. The file's test scaffolding includes a structural assertion that the LOCKED PUBLIC site's raw fetch is preserved post-migration (parallel to v2.17 §9.11 structural-test-file amendment shape applied to CP10 StoryEvaluationEngine). Validated against PressPublisher line 119 in CP11 (1 LOCKED PUBLIC + 3 BUG migrated). Future tracks encountering mixed-disposition files (WorldSetupGuide deferred to CP15 with 3 LOCKED PUBLIC + 5 BUG) follow the same convention.

Combined-axis branching split — stacking validated (NEW v2.18 note, NOT a new convention). v2.13 §9.11 method-branching split + v2.17 §9.11 URL-branching generalize natively to combined axes — a single conditional may switch BOTH method AND URL simultaneously, handled by the existing convention without extension. Validated at CP11 WorldLocations:141 — saveLocation's editId conditional selects PUT /world/locations/:id when editing OR POST /world/locations when creating, on the same line. Convention application: extract updateLocationApi(id, payload) + createLocationApi(payload) as separate helpers covering both branches; call site does single ternary covering combined axes (editId ? updateLocationApi(...) : createLocationApi(...)). No new lock language required; v2.18 documents this as "stacking validated" — the convention library handles combined-axis branching natively.

Pattern G allowlist update LOCKED v2.18 (3 → 5 locked sites). First Pattern G additions since CP3. Two new streaming-response-body locked sites added in CP11: WriteModeAIWriter:281 (res.body.getReader() preceded by line 273 streaming kickoff fetch with AbortController.signal) + AppAssistant:239 (res.body.getReader() preceded by line 215 streaming kickoff fetch). 9-line locked comment template scales unchanged. Total Pattern G locked sites in F-AUTH-1: 5 (BookEditor:58 keepalive, WriteMode:1000 streaming, WriteMode:1191 streaming, WriteModeAIWriter:281 streaming, AppAssistant:239 streaming). Verification-grep allowlist updated for all 5 sites. Note: useStoryEngine:356 has res.body.getReader() — surface analysis at CP12 will adjudicate as Pattern G or NodeFetch migration.

URL-string-shape disambiguation note (NEW v2.18 §9.12). Surface analysis must inspect API base composition, not just URL fragments. CP11 surface initially flagged StoryCalendar's ${API}/calendar/events as a CP10 CulturalCalendar duplicate. Migration revealed StoryCalendar imports API from a constants module where API = '/api/v1/storyteller'; full URL resolves to /api/v1/storyteller/calendar/events, distinct from CP10's global /api/v1/calendar/events. Helpers were FRESH, not duplicates. Discipline: at surface time, read the import statement for the API base constant; resolve the full URL; only then decide if a cross-CP duplicate exists. CP11 caught this mid-flow; future surface reports should catch it before lock to avoid subsequent surface-correction notes.

- Pattern F prophylactic discipline confirmed correct (tenth data point). All 17 CP11 files had LOW direct-shadow density.

- Heaviest cross-CP duplication CP yet — 14 cross-CP duplications across 6 files (was 11 across 5 files in CP8). v2.12 §9.11 file-local convention scales unbroken at 14-fold density. listShowsApi reaches 5-fold cross-CP existence (CP2 + CP5 + CP7 + CP9 service + CP10 + CP11 — under v2.17 §9.11 6-fold ceiling). updateChapterApi reaches 3-fold (CP3 + CP10 + CP11).

- No HTTP method mismatches surfaced (CP3-CP11 cumulative still at 0 mid-flow + 1 caught at surface in CP7 + 1 verified at surface in CP9). Total method-correction discoveries: 5 across 11 CPs.

- Path E candidates surfaced from CP11: ~14 GET sites filed for §9.12 Step 3 sweep awareness (many dedup-noted from CP2/CP3/CP5/CP6/CP9/CP10).

- Pattern composability stacked at 5+ patterns within CP11 (Pattern F + Pattern G + file-local duplication + URL-branching + method-branching + mixed PUBLIC+BUG). No file invokes more than 3 patterns simultaneously (CP6 WorldFoundation + CP10 SEE remain the per-file high-water marks at 3 patterns each); CP-level density is higher in CP11 because of more files.

### Pacing model — 10 data points, CP11 zone identified (long-tail + heavy duplication, 45-55 sites/session) (NEW v2.18, supersedes v2.17)

Ten checkpoints across Track 6:

- CP2 (1 file, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (1 file, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (1 file, 18 sites): 1 session, 18 sites/session.

- CP5 (3 files uniform-simple, 28 sites): 1 session, 28 sites/session.

- CP6 (4 files heterogeneous, 38 sites): 1 session, 38 sites/session.

- CP7 (10 files long-tail simplest-first, 39 sites): 1 session, 39 sites/session.

- CP8 (10 files long-tail simplest-first, 38 sites): 1 session, 38 sites/session.

- CP9 (8 files long-tail simplest-first, 40 sites): 1 session, 40 sites/session.

- CP10 (8 files long-tail simplest-first, 42 sites): 1 session, 42 sites/session.

- CP11 (17 files cleanup-overlap, 51 BUG-class migrated): 1 session, 51 sites/session. New throughput high-water mark.

CP11 zone IDENTIFIED v2.18 (NEW): long-tail batches with heavy file-local cross-CP duplication can scale to 45-55 sites/session at 15-17 files. Conditions for the CP11 zone:

- Most files are 3-site clean clusters (cheapest possible migrations)

- Cross-CP duplications are mechanical translation (no novel work)

- 1-2 anchor files apply locked patterns (no new convention work)

- Pattern G additions are bounded (9-line template applies)

CP11 zone is an extension of the CP7-10 zone, not a replacement. Future CPs at similar shape (long-tail + heavy duplication + many small files) can target this throughput. CPs with novel pattern work (e.g., new convention design) or high-density single files (CP3-zone complexity) revert to the lower zones.

Updated throughput model — seven predictor zones now:

- Single high-density file: 11-13 sites/session (CP3 zone)

- Single mid-density file: 14-16 sites/session (CP2 zone)

- Single lower-density simple file: 15-18 sites/session (CP4 zone)

- Multi-file batch uniform-simple (3-4 files): 25-30 sites/session (CP5 zone)

- Multi-file batch heterogeneous (4 files): 35-40 sites/session (CP6 zone)

- Long-tail simplest-first (8-10 files): 35-42 sites/session (CP7-10 zone)

- Long-tail + heavy duplication (15-17 files): 45-55 sites/session (CP11 zone) — NEW

### Long-tail forecast updated to actuals — post-CP11 (UPDATED v2.18)

CP11 inventory reconciliation:

- Pre-CP11: 48 files / 166 sites (matched CP10 close exactly)

- Post-CP11: 31 files / 115 sites

- Path E cluster (deferred to Step 3): WorldStudio.jsx 29 + LOCKED PUBLIC 5 + UIOverlaysTab external blob 1 = 35 sites

- Pattern G locked exceptions: 5 (BookEditor:58, WriteMode:1000, WriteMode:1191, WriteModeAIWriter:281, AppAssistant:239)

- Estimated BUG-class remaining for Track 6 migration: ~80 sites across ~26 files

Updated CP forecast: 4 more CPs to close Track 6 implementation (CP12-CP15). CP12 useStoryEngine.js (14 sites; CP3-zone single-file dedicated; line 356 streaming pair adjudication). CP13 WorldAdmin.jsx (11 sites; CP3-zone; FormData uploads + variable-URL op.endpoint). CP14 EpisodeDetail.jsx (10 sites; UNCLEAR-B mixed-paradigm spot-check). CP15 WorldSetupGuide.jsx (8 mixed PUBLIC+BUG; second F-AUTH-1 mixed instance — applies CP11 PressPublisher convention) + tail residual filler. After CP15: Track 6 implementation closes; remaining 35 Path E sites are deferred to Step 3 backend audit (never migrated). Trajectory remains coherent.

Track 6 progress as of CP11: 389 sites migrated across 62 files. 5 Pattern G locked exceptions (was 3). Tests grew from 135 (Track 6 start) to 683 (+548). Current progress ~83% by site count (389 / ~469 corrected denominator). Remaining: CP12-CP15 (~80 sites across ~26 files). Track 6 implementation closure projected at CP15.

### File-count arithmetic correction post-CP11 (NEW v2.19 §4.6 note)

CP12 surface re-reconciliation surfaced an arithmetic error in v2.18 §4.6 + the CP11 closure report. v2.18 listed "31 files / 115 sites" post-CP11; actual grep at branch tip 87460600 returned 34 files / 115 sites. The discrepancy: CP11 touched 17 files but only 14 were fully cleared. The 3 sites retained per discipline (PressPublisher:119 LOCKED PUBLIC + WriteModeAIWriter:281 Pattern G + AppAssistant:239 Pattern G) keep their files in the inventory with 1 fetch site each. 48 − 14 fully-cleared = 34 residual, not 31. Site count (115) was correct; file count (31) was wrong. Doesn't change any execution; corrects the counting going forward. The discipline that caught this: re-reconciling at branch tip during surface analysis.

### Track 6 CP12 architectural findings (LOCKED v2.19, COMPLETE — useStoryEngine.js dedicated high-density single; 11th consecutive zero method-mismatch CP)

CP12 completed at commit 7eec2a21 (single squashed commit, 5 file-boundary WIPs collapsed; single session, ~105 min actual against 200-220 min forecast). 13 BUG-class fetch sites migrated in useStoryEngine.js + 1 Pattern G locked at line 358 (post-comment-block insertion shifted from line 356 surface-time projection). 12 module-scope helpers with Pattern F Api suffix (11 fresh + 1 cross-CP duplication: listStoriesForCharacterApi reaches 3-fold cross-CP existence — CP9 + CP11 + CP12). 28 new tests added (19 CP12 behavioral + 9 Pattern G structural; pre-existing 3 Track 3 tests preserved unchanged); full frontend suite at 711/711 passing across 78 test files. Backed up at 7eec2a21 on claude/f-auth-1-backup. First dedicated high-density single-file CP since CP4 (DraftFusion 18 sites). CP12 is the 11th consecutive CP with zero HTTP method mismatches.

Per-site execution (within-file simplest-first):

- Step 1 (Pattern G first): line 348/356 → line 376 streaming kickoff + line 358 res.body.getReader() — locked per matching-precedent (shape matches WriteMode:1000/1191 + WriteModeAIWriter:281 exactly). 9-line comment template applied. Verification-grep allowlist 5 → 6 sites (useStoryEngine.js:358 added).

- Step 2 (Loaders): sites 1-3 — getStoryEngineCharactersApi (line 197), listStoriesForCharacterApi (line 261, 3-fold cross-CP dup), getStoryEngineTasksApi (line 303).

- Step 3 (Single-shot writers): sites 5, 12, 13 — generateNextChapterApi (line 412, also covers site 11 reuse), checkStoryConsistencyApi (line 740), addStoryEngineCharacterApi (line 762).

- Step 4 (handleApprove cluster): sites 6-11 — 6 sites in single 156-line callback. extractStoryMemoriesApi (line 522, Promise.all member must complete; Path E dedup from Track 3 v2.18 §9.12), updateStoryEngineRegistryApi (line 544, fire-and-forget), generateTextureLayerApi (line 560, fire-and-forget), updateArcTrackingApi (line 580, .catch only — helper omits .then for no-body-read), checkSceneEligibilityApi (line 593, fire-and-forget conditional on story.db_id), generateNextChapterApi reuse (line 619, success-path branching DIFFERENT from site 5).

- Step 5 (site 14): line 776 — getStoryEngineCharactersApi reuse on registry refresh.

Pattern G default-on-matching-precedent discipline LOCKED v2.19 (NEW). When a streaming-shape candidate is surfaced, default disposition is Pattern G lock if shape matches existing locked precedent. NodeFetch migration is a NEW policy decision distinct from Pattern G — requires explicit Evoni approval, not a default. Validated at CP12 useStoryEngine:358 (matched WriteMode:1000/1191 + WriteModeAIWriter:281 shape exactly: POST + JSON.stringify body + res.body.getReader, no AbortController). Pattern G lock applied without policy escalation. Future tracks encountering streaming-shape candidates: surface report compares shape against existing locked precedents; if match, propose Pattern G lock as default; if genuine deviation, surface for policy discussion before committing.

Pattern G line-number shift on comment insertion (NEW v2.19 note). The 9-line locked-comment block insertion shifts the locked-site line number downward by ~9-10 lines. Surface report line numbers are pre-insertion approximations; final allowlist line numbers are post-insertion. Validated at CP12: surface predicted line 356 for Pattern G site; actual is line 358 post-migration. Not a problem; just observed mechanic. Verification-grep allowlist references the post-insertion line number (useStoryEngine.js:358).

Hook module-scope helper pattern third validation (UPDATED v2.19, supersedes v2.16 single-instance lock). v2.16 §9.11 hook module-scope helper convention now validated across three hooks of varying complexity: CP9 useGenerationJob (5 sites, simple polling), CP11 usePageData (3 sites, mid-density), CP12 useStoryEngine (13 sites + 1 Pattern G, high-density 14-site). Convention scales unchanged. Helpers exported as export const at module scope; consumers of the hook unchanged; tests use direct named imports. Pre-existing Track 3 Stage 1 exports at useStoryEngine lines 11-15 (persistStory, deleteStoryFromDb) confirmed the file already followed the convention before CP12 extended it with 12 more helpers.

Existing-test-file amendment third validation (UPDATED v2.19, supersedes v2.17 dual-instance lock). v2.15 §9.11 existing-test-file amendment convention now validated across three test-file shapes: CP8 RelationshipEngine (behavioral-only append), CP10 StoryEvaluationEngine (structural-with-behavioral-append, vi.mock hoisting required), CP12 useStoryEngine (hook-with-helper-append + Pattern G structural tests). Three distinct shapes; convention scales unchanged across all observed test-file structures. Pre-existing 3 Track 3 tests preserved; 28 CP12 tests appended (19 behavioral + 9 Pattern G structural).

Callback-cluster preservation pattern (NEW v2.19 observation, NOT a new convention). When a single callback contains multiple fetch sites with varied semantic roles (must-complete vs fire-and-forget vs conditional vs no-body-read), file-local helpers replace each fetch call site individually; surrounding Promise.all/Promise.allSettled/conditional wrappers stay verbatim; semantic preservation comes from the helper-replaces-fetch shape, not from explicit cluster orchestration. Validated at CP12 handleApprove (6 sites in 156-line callback, 5 distinct semantic shapes: site 6 Promise.all member must-complete; sites 7-8 fire-and-forget concurrent in postApprovalTasks array; site 9 .catch only with no-body-read helper variant; site 10 fire-and-forget conditional on story.db_id; site 11 success-path branching different from site 5 same-helper). All 6 semantic invariants preserved without flattening. The convention library naturally handles callback clusters; no new lock language needed.

- Pattern F prophylactic discipline confirmed correct (eleventh data point). 17 component-internal handlers use handle* prefix; 12 new helpers use *Api suffix. No direct shadow conflicts. Pattern F applied from first extraction.

- handleApprove cluster came in well under estimate (25 min actual vs 75 min forecast) because helper-extraction-then-replace-call pattern was mechanical once helpers were defined. Promise.all + Promise.allSettled wrappers stayed verbatim. WIP-and-resume checkpoint not needed.

- Cross-CP duplication: listStoriesForCharacterApi reaches 3-fold cross-CP existence (CP9 StoryEngine + CP11 StoryReviewPanel + CP12 useStoryEngine). All other 11 CP12 helpers are FRESH — /memories/story-engine-* family is unique to this hook; /texture-layer/generate, /arc-tracking/update, /world/scenes/check-eligibility, /memories/extract-story-memories, /memories/check-story-consistency, /memories/generate-next-chapter are not duplicated elsewhere.

- Path E dedup: /memories/extract-story-memories was already filed in v2.18 §9.12 line 1488 from Track 3 surface. CP12 migration applies apiClient (auth-required default) — site is now covered by extractStoryMemoriesApi helper. Dedup-noted from Track 3 filing.

- No HTTP method mismatches surfaced (CP3-CP12 cumulative still at 0 mid-flow + 1 caught at surface in CP7 + 1 verified at surface in CP9). CP12 is the 11th consecutive CP with zero method mismatches. Total method-correction discoveries: 5 across 12 CPs.

### Pacing model — 11 data points, CP3 zone reproducibility validated for high-density singles (NEW v2.19, supersedes v2.18)

Eleven checkpoints across Track 6:

- CP2 (1 file, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (1 file, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (1 file, 18 sites): 1 session, 18 sites/session.

- CP5 (3 files uniform-simple, 28 sites): 1 session, 28 sites/session.

- CP6 (4 files heterogeneous, 38 sites): 1 session, 38 sites/session.

- CP7 (10 files long-tail simplest-first, 39 sites): 1 session, 39 sites/session.

- CP8 (10 files long-tail simplest-first, 38 sites): 1 session, 38 sites/session.

- CP9 (8 files long-tail simplest-first, 40 sites): 1 session, 40 sites/session.

- CP10 (8 files long-tail simplest-first, 42 sites): 1 session, 42 sites/session.

- CP11 (17 files cleanup-overlap, 51 BUG-class migrated): 1 session, 51 sites/session.

- CP12 (1 file dedicated high-density, 13 sites + 1 Pattern G locked): 1 session, 13 sites/session. CP3 zone (11-13 sites/session) reproducibility validated for high-density singles.

CP12 confirms CP3 zone applicability for high-density single files: 11-13 sites/session is the empirical band for dedicated single-file CPs at high density (>10 sites). Surface-with-cost-estimation discipline forecast 1 session probable / 2 sessions possible at 60% confidence; actual was 1 session at 105 min against 200-220 min estimate. Conservative forecasting validated. CP13 WorldAdmin (11 sites) + CP14 EpisodeDetail (10 sites) carry similar conservative forecasts in this band.

- Throughput model unchanged — seven predictor zones. v2.19 strengthens CP3 zone confidence via CP12 second data point at high-density single shape (CP3 was first at 33 sites + 2 Pattern G in 3 sessions; CP12 was second at 13 sites + 1 Pattern G in 1 session; both within 11-13 sites/session band).

### Long-tail forecast updated to actuals — post-CP12 (UPDATED v2.19)

CP12 inventory reconciliation:

- Pre-CP12: 34 files / 115 sites (corrected from v2.18's 31 files figure)

- Post-CP12: 34 files / 102 sites (useStoryEngine retains 1 entry for Pattern G locked site)

- Path E cluster (deferred to Step 3): WorldStudio.jsx 29 + LOCKED PUBLIC 5 + UIOverlaysTab external blob 1 = 35 sites

- Pattern G locked exceptions: 6 (BookEditor:58, WriteMode:1000, WriteMode:1191, WriteModeAIWriter:281, AppAssistant:239, useStoryEngine:358)

- Estimated BUG-class remaining for Track 6 migration: ~67 sites across ~30 files

Updated CP forecast: 3 more CPs to close Track 6 implementation (CP13-CP15). CP13 WorldAdmin.jsx (11 sites; CP3-zone single; FormData uploads + variable-URL op.endpoint; multipart pattern v2.14 + URL-branching v2.17 likely composable). CP14 EpisodeDetail.jsx (10 sites; CP3-zone single; UNCLEAR-B mixed-paradigm spot-check). CP15 WorldSetupGuide.jsx (8 mixed PUBLIC+BUG; second F-AUTH-1 mixed instance applies CP11 PressPublisher convention) + tail residual filler. After CP15: Track 6 implementation closes; remaining 35 Path E sites are deferred to Step 3 backend audit (never migrated). Trajectory remains coherent.

Track 6 progress as of CP12: 402 sites migrated across 46 files. 6 Pattern G locked exceptions (was 5). Tests grew from 135 (Track 6 start) to 711 (+576). Current progress ~86% by site count (402 / ~469 corrected denominator). Remaining: CP13-CP15 (~67 sites across ~30 files). Track 6 implementation closure projected at CP15.

### Track 6 CP13 architectural findings (LOCKED v2.20, COMPLETE — WorldAdmin.jsx dedicated high-density single; second consecutive high-density single; first formal lock of Data-driven URL pass-through pattern)

CP13 completed at commit bdd6b6df (single squashed commit, 4 file-boundary WIPs collapsed; single session, ~75 min actual against 120-145 min forecast). 11 BUG-class fetch sites migrated in WorldAdmin.jsx + 0 Pattern G locked (zero CP13-zone triggers). 11 module-scope helpers with Pattern F Api suffix (7 fresh + 4 cross-CP duplications, 3 of which are service-module precedence inversions). 22 new tests added (4 cross-CP dup + 4 fresh + 1 outfit-sets + 4 Option B parameterized variants + 1 Option B unwrap + 2 multipart + 6 error propagation); full frontend suite at 733/733 passing across 79 test files. Backed up at bdd6b6df on claude/f-auth-1-backup. Second dedicated high-density single-file CP in a row (after CP12 useStoryEngine). WorldAdmin.jsx fully cleared from inventory (file count 34 → 33). CP13 is the 12th consecutive CP with zero HTTP method mismatches.

Per-site execution (within-file simplest-first):

- Step 1 (Cross-CP dups, 4 sites): listEpisodeTodoSocialApi (line 1635, CP9 dup, 2-fold), listWorldEventsApi (line 1636, service-module precedence inversion — first file-local capture from 7+ component consumers), listShowWardrobeApi (line 5563, wardrobeService.js + 7-component precedence inversion), updateWardrobeItemApi (line 6088, wardrobeService.js precedence inversion).

- Step 2 (Fresh wardrobe-detail helpers, 4 sites): promoteWardrobePrimaryVariantApi (line 5251, PATCH), sendWardrobeToPhoneApi (line 5291, POST), regenerateWardrobeProductShotApi (line 5331, POST), getWardrobeUsageApi (line 6013, GET).

- Step 3 (Site 11): createOutfitSetApi (line 7174, POST).

- Step 4 (Site 6 Option B Data-driven URL pass-through): bulkWardrobeOpApi(endpoint, payload) (line 5550). Config array at lines 5538-5542 preserved verbatim. Call site replaced fetch with helper invocation. test.each parameterization deployed over 4 endpoint variants + 5th test for r.data unwrap.

- Step 5 (Site 10 multipart): uploadWardrobeApi(formData) (line 6599, FormData direct to api.post; no manual Content-Type; outer try/catch at line 6582 cleanup). 2 specific multipart tests verify FormData passed as second arg + no third-arg config.

Data-driven URL pass-through pattern — formally LOCKED v2.20 §9.11 (NEW, validated at WorldAdmin:5550). When N variant URLs are dispatched via config-array.map (or other data-driven enumeration in source) AND method, payload shape, and headers are uniform across variants, a single pass-through helper is canonical. Helper signature: export const verbNounOpApi = (endpoint, payload) => api.post(endpoint, payload).then(r => r.data). Distinct from v2.17 URL-branching split (which assumes call-site ternary/switch with hard-coded URLs at each branch), v2.13 method-branching split, and v2.18 combined-axis stacking. Structural conditions for applicability (ALL required): (1) method uniform across variants, (2) payload shape + headers uniform across variants, (3) variants enumerated in source as data (config array, lookup table, registry) — not as control flow, (4) URLs originate from inside the file (no external input — closes the SSRF surface). If any condition fails, fall back to v2.17 / v2.13 / v2.18 per shape. Helper naming: use a verb-noun-Op pattern (e.g., bulkWardrobeOpApi, not just bulkOpApi) — preserve domain context per Pattern F. Validated execution at CP13: all 4 structural conditions verified post-execution; config array preserved verbatim; 4-variant test.each parameterization passes; 1 helper covers 4 sites.

Service-module precedence inversion — three-data-point validation (UPDATED v2.20, supersedes v2.16 single-instance lock). v2.16 §9.11 service-module precedence inversion convention now validated across three data points: CP9 showService.js (first instance), CP13 WorldAdmin:5563 wardrobeService.js + 7 component consumers (highest consumer count observed in F-AUTH-1), CP13 WorldAdmin:6088 wardrobeService.js line 39. Convention scales unbroken at 7-component-consumer density. v2.16 lock language stands without modification; v2.20 records the data points. Discipline: when a service-module canonical exists for an endpoint, file-local helpers in pages duplicate the helper locally (per v2.12) rather than importing from the service; the service contract remains the upstream source of truth, but file-local idiom is preserved.

Partial-migration extension pattern (NEW v2.20 §9.11 observation). When a file has pre-existing apiClient adoption (from independent earlier migration, not from a prior Track 6 CP), new helpers preserve the file-local idiom. Validated at CP13: WorldAdmin had pre-existing api.post('/api/v1/wardrobe-library/analyze-image', fd, { signal: ac.signal, timeout: 120000 }) at line 6306 (NOT in CP13 zone). CP13 extended with 11 new helpers all using the same api import (not the global apiClient style). Test scaffolding uses vi.mock('../services/api', () => ({ default: { ... } })) consistent with file-local convention. Verification grep treats the file as partially-migrated rather than virgin: pre-existing apiClient site is NOT a CP deliverable; do not touch.

Outer try/catch cleanup observation (NEW v2.20 §9.11 note). When migrating from raw fetch with if(res.ok)/if(!res.ok) idioms to apiClient throws-on-non-2xx, an outer try/catch wrapping only the payload-construction-then-fetch block may become unmatched if the inner block was the only try consumer. Resolution: remove the outer try since payload construction (FormData append calls, JSON object construction, etc.) is pure JS that doesn't throw; inner try/catch on the network call handles all error paths. Validated at CP13 WorldAdmin:6582 (outer try wrapping FormData construction + upload became unmatched after multipart helper replaced inline fetch). Filed as observation; no new lock language needed (recognizable cleanup, not a convention). Surface analysis discipline: future surface reports should anticipate this cleanup when a migration zone has outer-try-then-fetch patterns.

Pattern G zero-trigger admin-page heuristic (NEW v2.20 §9.11 observation). Admin-page CPs default to zero Pattern G expectation; chat/AI-writer CPs default to high Pattern G expectation. Two consecutive admin-page instances confirm: CP11 PressPublisher BUG-only sites (zero Pattern G), CP13 WorldAdmin (zero Pattern G). Streaming-shape candidates concentrate in chat/AI-writer files (BookEditor, WriteMode, WriteModeAIWriter, AppAssistant, useStoryEngine — all 6 Pattern G locked sites). Surface analysis discipline: admin-page CPs surface-check Pattern G as low-prior; chat/AI-writer CPs surface-check Pattern G as high-prior.

- Pattern F prophylactic discipline confirmed correct (twelfth data point). All 11 helpers use *Api suffix; component-internal handlers use handle* / verb prefixes. No direct shadow conflicts.

- Cross-CP duplication: 4 sites in CP13 (sites 1, 2, 7, 9). listEpisodeTodoSocialApi reaches 2-fold cross-CP existence (CP9 + CP13). All other 7 helpers are FRESH.

- Path E candidates: 4 GET sites filed (1 fresh + 3 dedup-noted from prior CPs). All Step 3 backend audit will adjudicate per-route disposition.

- No HTTP method mismatches surfaced. CP13 is the 12th consecutive CP with zero method mismatches (CP3-CP13 cumulative). Total method-correction discoveries remain at 5 across 13 CPs.

- Pattern G allowlist UNCHANGED at 6 sites. Verification grep allowlist not updated in v2.20.

### Pacing model — 12 data points, CP3 zone validated at three data points (NEW v2.20, supersedes v2.19)

Twelve checkpoints across Track 6:

- CP2 (1 file, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (1 file, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (1 file, 18 sites): 1 session, 18 sites/session.

- CP5 (3 files uniform-simple, 28 sites): 1 session, 28 sites/session.

- CP6 (4 files heterogeneous, 38 sites): 1 session, 38 sites/session.

- CP7 (10 files long-tail simplest-first, 39 sites): 1 session, 39 sites/session.

- CP8 (10 files long-tail simplest-first, 38 sites): 1 session, 38 sites/session.

- CP9 (8 files long-tail simplest-first, 40 sites): 1 session, 40 sites/session.

- CP10 (8 files long-tail simplest-first, 42 sites): 1 session, 42 sites/session.

- CP11 (17 files cleanup-overlap, 51 BUG-class migrated): 1 session, 51 sites/session.

- CP12 (1 file dedicated high-density, 13 sites + 1 Pattern G locked): 1 session, 13 sites/session.

- CP13 (1 file dedicated high-density, 11 sites + 0 Pattern G): 1 session, 11 sites/session. Lower edge of CP3 zone.

CP3 zone band 11-13 sites/session validated at three data points: CP3 (33 sites + 2 G locked over 3 sessions, 11 sites/session); CP12 (13 sites + 1 G locked in 1 session, 13 sites/session); CP13 (11 sites + 0 G locked in 1 session, 11 sites/session). Band is empirically stable. Future high-density single CPs (CP14 EpisodeDetail at 10 sites) carry similar conservative forecasts in this band.

Conservative forecasting bias confirmed across 12 CPs: CP12 forecast 200-220 min, actual 105 min (~2x overestimate). CP13 forecast 120-145 min, actual 75 min (~1.7x overestimate). Surface-with-cost-estimation discipline accepts the conservative bias — better to under-promise than over-commit. Time savings come from helper-extraction-then-replace-call pattern being mechanical once helpers are defined; tests scale linearly with helper count, not site count. Future CP forecasts continue conservative bias as design feature, not bug.

- Throughput model unchanged — seven predictor zones. v2.20 strengthens CP3 zone confidence via three data points all within 11-13 sites/session band.

### Long-tail forecast updated to actuals — post-CP13 (UPDATED v2.20)

CP13 inventory reconciliation:

- Pre-CP13: 34 files / 102 sites

- Post-CP13: 33 files / 91 sites (WorldAdmin fully cleared from inventory — first complete file clearance since CP11 multi-file batch)

- Path E cluster (deferred to Step 3): WorldStudio.jsx 29 + LOCKED PUBLIC 5 + UIOverlaysTab external blob 1 = 35 sites

- Pattern G locked exceptions: 6 (UNCHANGED — BookEditor:58, WriteMode:1000, WriteMode:1191, WriteModeAIWriter:281, AppAssistant:239, useStoryEngine:358)

- Estimated BUG-class remaining for Track 6 migration: ~56 sites across ~26 files

Updated CP forecast: 2 more CPs to close Track 6 implementation (CP14-CP15). CP14 EpisodeDetail.jsx (10 sites; CP3-zone single; UNCLEAR-B mixed-paradigm spot-check). CP15 WorldSetupGuide.jsx (8 mixed PUBLIC+BUG; second F-AUTH-1 mixed instance applies CP11 PressPublisher convention) + tail residual filler (~7 small files). After CP15: Track 6 implementation closes; remaining 35 Path E sites are deferred to Step 3 backend audit (never migrated). Trajectory remains coherent.

Track 6 progress as of CP13: 413 sites migrated across 47 files. 6 Pattern G locked exceptions (UNCHANGED). Tests grew from 135 (Track 6 start) to 733 (+598). Current progress ~88% by site count (413 / ~469 corrected denominator). Remaining: CP14-CP15 (~56 sites across ~26 files). Track 6 implementation closure projected at CP15.

### Track 6 CP14 architectural findings (LOCKED v2.21, COMPLETE — EpisodeDetail.jsx dedicated high-density single; third consecutive high-density single; partial-migration extension graduates to two-data-point pattern; admin-page heuristic graduates to three-data-point validation; helper-reuse density observed)

CP14 completed at commit d2645cf9 (single squashed commit, 4 file-boundary WIPs collapsed; single session, ~50 min actual against 85-100 min forecast). 10 BUG-class fetch sites migrated in EpisodeDetail.jsx + 0 Pattern G locked (zero CP14-zone triggers, third consecutive admin-page CP confirming v2.20 admin-page heuristic). 6 module-scope helpers with Pattern F Api suffix (5 fresh + 1 cross-CP duplication: listWorldEventsApi reaches 2-fold cross-CP existence — CP13 + CP14). Helper-reuse density of 40% (6 helpers covering 10 sites — highest reuse density observed in F-AUTH-1 dedicated singles). 14 new tests added (6 helper-coverage + 2 helper-reuse coverage + 6 error propagation); full frontend suite at 747/747 passing across 80 test files. Backed up at d2645cf9 on claude/f-auth-1-backup. Third dedicated high-density single-file CP in a row (after CP12 useStoryEngine + CP13 WorldAdmin). EpisodeDetail.jsx fully cleared from inventory (file count 33 → 32). CP14 is the 13th consecutive CP with zero HTTP method mismatches.

UNCLEAR-B adjudication outcome: (A) PARTIAL-MIGRATION EXTENSION per v2.20 §9.11. Surface report adjudicated against the 5 candidate explanations with concrete evidence: file imports api from ../services/api at line 26; 2 pre-existing api.post() sites at lines 776 + 805 (both /world/:sid/episodes/:id/generate-story POST); 0 LOCKED PUBLIC sites; 0 Pattern G triggers; intra-BUG-class idiom variation only. Same shape as CP13 WorldAdmin (which had pre-existing api.post at line 6306). Migration zone bounded to 10 BUG-class raw fetch sites; pre-existing api.post sites verified UNTOUCHED post-execution.

Per-site execution (within-file simplest-first, helper-reuse-aware):

- Step 1 (Helper definitions block + Loaders, sites 1-3): all 6 helpers defined at top of file after imports. listEpisodeLibraryScenesApi (line 233 site 1), listWorldEventsApi (line 254 site 2, cross-CP dup CP13), getCharacterStateApi (line 268 site 3).

- Step 2 (handleSceneSelect cluster, sites 4-5): addEpisodeLibrarySceneApi (line 283 POST) + reload via listEpisodeLibraryScenesApi reuse (line 295 site 5).

- Step 3 (handleReorderScene cluster, sites 6-8): Promise.all parallel-execution of reorderEpisodeLibrarySceneApi twice (lines 318, 323 sites 6-7) + reload via listEpisodeLibraryScenesApi reuse (line 331 site 8).

- Step 4 (handleRemoveScene cluster, sites 9-10): removeEpisodeLibrarySceneApi (line 345 DELETE) + reload via listEpisodeLibraryScenesApi reuse (line 351 site 10).

Partial-migration extension pattern — graduates from observation to two-data-point pattern (UPDATED v2.21, supersedes v2.20 single-instance observation). v2.20 §9.11 partial-migration extension was first instance at CP13 WorldAdmin (single-instance observation). CP14 EpisodeDetail is second instance with the same shape: file imports api from ../services/api; has 1-2 pre-existing api.post() sites from independent earlier migration (not from prior Track 6 CP); BUG-class fetch sites are the migration zone. Pattern graduates to two-data-point pattern in v2.21. Discipline locked: when surface report encounters UNCLEAR-B file, partial-migration extension hypothesis is the default test. Adjudication takes ~30 seconds (read top-of-file imports + grep for api. calls + grep for raw fetch calls). CP14 surface adjudicated this in surface §3 with concrete evidence (imports, site count by class, idiom distribution, 5-candidate explanation table). New helpers preserve file-local idiom (NOT global apiClient. style).

Pattern G zero-trigger admin-page heuristic — graduates to three-data-point validation (UPDATED v2.21, supersedes v2.20 dual-instance observation). v2.20 §9.11 admin-page heuristic was first observed at CP11 PressPublisher BUG-only sites + CP13 WorldAdmin (zero Pattern G triggers in both). CP14 EpisodeDetail is third consecutive admin-page CP with zero Pattern G triggers. Heuristic graduates to three-data-point validation in v2.21. Streaming-shape candidates remain concentrated in 5 chat/AI-writer files (BookEditor:58, WriteMode:1000, WriteMode:1191, WriteModeAIWriter:281, AppAssistant:239, useStoryEngine:358 — all 6 Pattern G locked sites are in chat/AI-writer files). Heuristic, not lock — surface check still required per file regardless. Validated at CP11 + CP13 + CP14 across page-shape variations (PressPublisher domain-content admin, WorldAdmin show-management admin, EpisodeDetail episode-management admin).

Helper-reuse density forecasting heuristic (NEW v2.21 §9.11 observation). When surface analysis identifies CRUD + reload-after-mutation cluster pattern (single resource family with mount + create + update + delete + reload-after-each-mutation), helper count is 30-40% lower than site count. The loader gets called once at mount + once after each mutation = N+1 invocations from M+1 distinct call sites where M is the mutation count. Validated at CP14 EpisodeDetail (40% reduction; 6 helpers / 10 sites — 4× reuse on listEpisodeLibraryScenesApi across mount + 3 reload-after-mutation paths; 2× reuse on reorderEpisodeLibrarySceneApi in single Promise.all parallel-execution wrapper). Forecasting heuristic, NOT a new convention — file-local helper convention v2.12 already handles helper reuse natively. Surface analysis discipline: when CRUD + reload pattern detected, session-time-per-site forecast can be reduced ~30% from CP3-zone baseline; helper-count forecast reduced 30-40% from site count. Tests cover the helper once per behavioral assertion + 1-2 explicit reuse-coverage tests; do NOT duplicate per-call-site coverage.

Decreasing-cost trend across CP12-CP14 (NEW v2.21 §4.6 pacing observation). Cost per site decreases monotonically across the three consecutive dedicated high-density singles: CP12 (14 sites + 1 Pattern G locked, 105 min, 7.5 min/site); CP13 (11 sites, 75 min, 6.8 min/site); CP14 (10 sites, 50 min, 5.0 min/site). Trend reflects three coupled factors: (a) decreasing site count per CP, (b) decreasing pattern composability complexity (CP12: 5 patterns including Pattern G adjudication + callback-cluster preservation; CP13: 4 patterns + 1 new lock for Data-driven URL pass-through; CP14: 3 patterns, no new locks), (c) increasing helper-reuse density (CP12: 8% reduction, CP13: 0%, CP14: 40%). Conservative forecasting bias holds steady (CP12 ~2.0x, CP13 ~1.7x, CP14 ~1.7x). Forecasts continue honest, not optimistic.

- Pattern F prophylactic discipline confirmed correct (thirteenth data point). All 6 helpers use *Api suffix; component-internal handlers use handle*/fetch* prefixes. No direct shadow conflicts.

- Cross-CP duplication: 1 site in CP14 (site 2). listWorldEventsApi reaches 2-fold cross-CP existence (CP13 + CP14). All other 5 helpers are FRESH.

- Path E candidates: 3 GET sites filed (2 fresh: /episodes/:id/library-scenes + /characters/:char/state; 1 dedup-noted: /world/:show/events from CP13).

- No HTTP method mismatches surfaced. CP14 is the 13th consecutive CP with zero method mismatches (CP3-CP14 cumulative). Total method-correction discoveries remain at 5 across 14 CPs.

- Pattern G allowlist UNCHANGED at 6 sites. Verification grep allowlist not updated in v2.21.

- Pre-existing api.post() sites at lines 776 + 805 verified UNTOUCHED post-execution. Verification grep at end-of-CP returned 0 raw-fetch matches in EpisodeDetail.jsx; pre-existing sites do not appear in CP14 diff. Partial-migration extension discipline maintained.

### Pacing model — 14 data points, CP3 zone reframes to 10-13 sites/session (NEW v2.21, supersedes v2.20)

Fourteen checkpoints across Track 6:

- CP2 (1 file, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (1 file, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (1 file, 18 sites): 1 session, 18 sites/session.

- CP5 (3 files uniform-simple, 28 sites): 1 session, 28 sites/session.

- CP6 (4 files heterogeneous, 38 sites): 1 session, 38 sites/session.

- CP7 (10 files long-tail simplest-first, 39 sites): 1 session, 39 sites/session.

- CP8 (10 files long-tail simplest-first, 38 sites): 1 session, 38 sites/session.

- CP9 (8 files long-tail simplest-first, 40 sites): 1 session, 40 sites/session.

- CP10 (8 files long-tail simplest-first, 42 sites): 1 session, 42 sites/session.

- CP11 (17 files cleanup-overlap, 51 BUG-class migrated): 1 session, 51 sites/session.

- CP12 (1 file dedicated high-density, 13 sites + 1 Pattern G locked): 1 session, 13 sites/session, 7.5 min/site.

- CP13 (1 file dedicated high-density, 11 sites + 0 Pattern G): 1 session, 11 sites/session, 6.8 min/site.

- CP14 (1 file dedicated high-density, 10 sites + 0 Pattern G): 1 session, 10 sites/session, 5.0 min/site. CP3 zone lower edge with high helper-reuse density (40%).

CP3 zone reframes to 10-13 sites/session band (UPDATED v2.21, supersedes v2.20 11-13 framing). Three high-density single data points (CP12, CP13, CP14) span 10-13 sites/session. Lower edge (10 sites/session at CP14) is achieved with high helper-reuse density (≥30%); upper edge (13 sites/session at CP12) is achieved at moderate reuse density (~8%) with composability stack of 5 patterns. Band reframing: 10-13 sites/session for high-density single CPs, with helper-reuse density as the primary lower-edge enabler. Future high-density single CPs (CP15 has multi-file shape, not single) carry forecasts in this band conditional on file shape.

Conservative forecasting bias confirmed across 14 CPs: CP12 forecast 200-220 min, actual 105 min (~2.0x overestimate). CP13 forecast 120-145 min, actual 75 min (~1.7x). CP14 forecast 85-100 min, actual 50 min (~1.7x). Surface-with-cost-estimation discipline accepts the conservative bias as design feature. Time savings come from helper-extraction-then-replace-call pattern being mechanical once helpers are defined; tests scale with helper count, not site count; helper-reuse density compounds the savings on cluster-pattern files. Future CP forecasts continue conservative bias.

- Throughput model unchanged — seven predictor zones. v2.21 widens CP3 zone to 10-13 sites/session via three data points (CP3, CP12, CP13, CP14 — four data points spanning the full band).

### Long-tail forecast updated to actuals — post-CP14 (UPDATED v2.21)

CP14 inventory reconciliation:

- Pre-CP14: 33 files / 91 sites

- Post-CP14: 32 files / 81 sites (EpisodeDetail fully cleared from inventory — third consecutive file fully cleared by dedicated single CP)

- Path E cluster (deferred to Step 3): WorldStudio.jsx 29 + LOCKED PUBLIC 5 + UIOverlaysTab external blob 1 = 35 sites

- Pattern G locked exceptions: 6 (UNCHANGED)

- Estimated BUG-class remaining for Track 6 migration: ~46 sites across ~25 files

Updated CP forecast: 1 more CP to close Track 6 implementation (CP15 — FINAL CP). CP15 = WorldSetupGuide.jsx (8 mixed PUBLIC+BUG; second F-AUTH-1 mixed-disposition instance after CP11 PressPublisher; applies CP11 convention) + tail residual filler (~7 small files, ~38 sites). Multi-file shape, CP7-10 zone throughput (35-55 sites/session). Forecast: 1 session, 60-90 min. Mixed PUBLIC+BUG convention v2.18 applies to WorldSetupGuide. After CP15: Track 6 implementation closes. Remaining ~35 Path E sites are deferred to Step 3 backend audit (never migrated).

Track 6 progress as of CP14: 423 sites migrated across 47 files. 6 Pattern G locked exceptions (UNCHANGED). Tests grew from 135 (Track 6 start) to 747 (+612). Current progress ~90% by site count (423 / ~469 corrected denominator). Remaining: CP15 ONLY (~46 sites across ~25 files). Track 6 implementation closure imminent at CP15.

### Track 6 CP15 architectural findings (LOCKED v2.22, COMPLETE — TRACK 6 IMPLEMENTATION CLOSURE; multi-file long-tail batch — 43 sites across 23 files)

CP15 completed at commit 04777edd (single squashed commit, 23 file-boundary WIPs collapsed; single session, ~120 min actual within 110-150 min forecast). 43 BUG-class fetch sites migrated across 23 files via ~30 module-scope helpers with Pattern F Api suffix. Final CP for Track 6 implementation closure. 0 Pattern G locked (zero CP15-zone triggers across all 23 files — admin-page heuristic v2.21 confirmed for fourth consecutive multi-file batch). 66 new tests added (+22 test files + 1 existing-test-file amendment); full frontend suite at 813/813 passing across 102 test files. Backed up at 04777edd on claude/f-auth-1-backup. Five architectural decisions executed cleanly: WorldSetupGuide all-BUG reclassification; Path A cross-CP ceiling discipline (8-fold listRegistriesApi); ProductionOverlaysTab:108 external blob deferral; Decision 4 variable-URL adjudication (3 sites: 2 → v2.14 internal-helper-refactor, 1 → standard helper); batch composition simplest-first multi-file long-tail per CP7+ precedent. CP15 is the 14th consecutive CP with zero HTTP method mismatches, closing the Track 6 streak intact (CP3-CP15 cumulative).

Per-tier execution (simplest-first multi-file long-tail per CP7+ discipline):

- Tier 1 (1-site files, 9 files, warm-up cadence): useRegistries (hook, listRegistriesApi 7-fold), FeedEnhancements, UniverseProductionPage (listShowsApi 5-fold), ScriptIntelligencePanel, ScriptBridgePanel, SceneLibraryPicker, RelationshipEngine/WebView, MemoryConfirmation (v2.14 internal-helper-refactor — apiFetch wrapper preserved), DecisionEchoPanel (standard helper extraction).

- Tier 2 (2-site fresh files, 8 files): StoryInspector (helper-reuse 2×), DesignAgent, DreamMap (helper-reuse: 1 GET + 1 PUT), ShowDistributionTab, CharacterDilemmaEngine, ScenesPanel, OutfitCalendar, ChapterJourney.

- Tier 3 (2-site partial-migration files, 3 files — context-switch overhead): SocialProfileGenerator (3rd partial-migration instance — 9+ pre-existing helpers), FeedBulkImport (4th instance — apiClient line 7), EpisodeScriptTab (5th instance — 5 pre-existing api.* sites).

- Tier 4 (2-site cross-CP-heavy files, 2 files): ChapterStructureEditor (CP3 dup), MemoryBankView (listRegistriesApi reaches 8-fold cross-CP existence + v2.14 internal-helper-refactor at line 57).

- Tier 5 (Anchor — WorldSetupGuide.jsx 8 sites): all 8 migrated to apiClient per Decision 1 reclassification. 6 helpers covering 8 sites with 3-way reuse on getPageContentApi (sites 1, 2, 4) — second helper-reuse-density data point after CP14 EpisodeDetail. listShowsApi reaches 6-fold cross-CP existence.

WorldSetupGuide reclassification — Decision 1 outcome (LOCKED v2.22 §4.2 amendment). The "mixed PUBLIC+BUG" label in inventory v2 §4.2 was provisional, predating the cross-CP evidence accumulated through CP14. CP15 surface adjudicated all 8 sites with concrete cross-CP evidence: /page-content/* (CP11 usePageData uses apiClient), /calendar/events (CP10/CP11 use apiClient), /world/locations (CP8/CP11 use apiClient), /social-profiles (CP9 uses apiClient), /shows (CP2/CP5/CP10/CP11 — 4-fold), /world/:show/events (CP13/CP14 use apiClient). Every endpoint is auth-required across the codebase. CP15 migrated all 8 sites to apiClient — no LOCKED PUBLIC retention, no CP11 PressPublisher convention applied. The second F-AUTH-1 mixed-disposition instance does not exist — CP11 PressPublisher remains the only mixed-disposition file in F-AUTH-1. Discipline locked: when surface report encounters a "mixed PUBLIC+BUG" inventory label, treat as provisional pending cross-CP cross-reference; the inventory label may be superseded by cross-CP evidence.

ProductionOverlaysTab:108 reclassification — Decision 3 outcome (LOCKED v2.22 §4.2 amendment). Site fetches user-content URL (S3-hosted overlay PNG) for client-side download via resp.blob() — application-controlled URL pointing at external blob storage, NOT a backend API call. Same structural shape as UIOverlaysTab.jsx external blob deferral. CP15 reclassified ProductionOverlaysTab:108 as deferred external blob; site UNTOUCHED in CP15 zone. Deferred external blob cluster grows to 2 sites (UIOverlaysTab + ProductionOverlaysTab). v2.22 §4.2 records the reclassification.

Cross-CP duplication ceiling exceeded — Decision 2 outcome (NEW v2.22 §9.11 ceiling-semantics clarification). Path A (continue v2.12 §9.11 file-local convention regardless of count) applied through CP15. Final cross-CP duplication counts: listRegistriesApi reaches 8-fold cross-CP existence (StoryEvaluationEngine + WriteMode + RelationshipEngine + CharacterTherapy + StoryProposer + Home + MemoryBankView + useRegistries) — exceeds v2.17 §9.11 6-fold "ceiling" by 2; listShowsApi reaches 6-fold (SceneSetsTab + SeriesPage + CulturalCalendar + CultureEvents + UniverseProductionPage + WorldSetupGuide) — meets ceiling exactly. v2.22 §9.11 ceiling semantics clarified: the 6-fold "ceiling" was always a soft observation about scaling pressure, not a hard cap. CP15 confirms operationally — file-local convention scales unbroken at 8-fold density without coupling concerns. v2.22 records the new high-water marks; ceiling-revisit (Path B cross-file import precedent) deferred to v2.23+ topic conditional on Step 3 backend sweep findings (e.g., if backend audit surfaces that listRegistriesApi has different per-route disposition that makes a service-module canonical genuinely useful, that's the right time to consider Path B; not before).

Variable-URL adjudication outcomes — Decision 4 (NEW v2.22 §9.11 lock for surface-time discipline). Three sites flagged for sample-time adjudication during CP15 execution. Outcomes:

- MemoryConfirmation.jsx:51 (apiFetch wrapper called 5× with varying methods GET/POST/DELETE) — v2.20 condition (1) FAILS (methods vary) → v2.14 internal-helper-refactor pattern applied: wrapper preserved, internal fetch swapped for apiClient.request. Fourth v2.14 data point.

- DecisionEchoPanel.jsx:31 (single ECHOES_API URL, single POST method) — v2.20 N/A (single URL, not data-driven dispatch) → standard helper extraction (plantEchoApi).

- MemoryBankView.jsx:57 (apiFetch wrapper, 6× call sites with varying methods) — v2.20 condition (1) FAILS (methods vary) → v2.14 internal-helper-refactor pattern applied. Fifth v2.14 data point.

Surface-time discipline LOCKED v2.22 §9.11: when surface report flags variable-URL sites as v2.20 candidates, sample-time inspection MUST verify all four structural conditions before applying v2.20. If condition (1) method uniformity fails (which is the most common failure mode for apiFetch-wrapper shapes), fallback is v2.14 internal-helper-refactor (wrapper preserved, internal fetch swapped). v2.20 stays at 1 implementation data point (CP13 WorldAdmin only); v2.14 reaches 5 data points (CP3 + CP6 + CP15 × 2). The discipline is: surface flags candidates; execution adjudicates per site; fallback patterns apply when conditions fail.

Partial-migration extension pattern — graduates to FIVE-data-point pattern (UPDATED v2.22, supersedes v2.21 two-data-point validation). v2.21 §9.11 partial-migration extension was validated at two data points (CP13 WorldAdmin + CP14 EpisodeDetail). CP15 contributes three new instances: SocialProfileGenerator.jsx (9+ pre-existing exported helpers at lines 30-41 + downstream callers; CP15 zone added 2 BUG-class sites at lines 1213, 1229), FeedBulkImport.jsx (apiClient imported line 7 + downstream usage; CP15 zone added 2 sites at lines 177, 210), EpisodeScriptTab.jsx (5 pre-existing api.* sites at lines 152/161/177/191/194; CP15 zone added 2 sites at lines 143, 144). All three pre-existing apiClient zones verified UNTOUCHED post-execution. Pattern graduates to five-data-point validation in v2.22. Robust across page (CP13/CP14), partially-migrated-page (CP15 SocialProfileGenerator at 9+ pre-existing helpers — highest pre-existing density observed), and component (CP15 FeedBulkImport, EpisodeScriptTab) shapes. Surface analysis discipline locked: when UNCLEAR-B file is encountered, partial-migration extension hypothesis is the default test; adjudication takes ~30 seconds (read top-of-file imports + grep for api. or apiClient. calls + grep for raw fetch calls).

Pattern G zero-trigger admin-page heuristic — graduates to FOUR-data-point validation (UPDATED v2.22, supersedes v2.21 three-data-point). CP15 23-file zone surfaced ZERO Pattern G triggers across all 23 in-scope files (admin pages, production pages, components, hooks all clean). Heuristic graduates to four-data-point validation: CP11 PressPublisher BUG-only sites + CP13 WorldAdmin + CP14 EpisodeDetail + CP15 (entire 23-file zone). Streaming-shape candidates remain concentrated in 5 chat/AI-writer files (BookEditor:58, WriteMode:1000, WriteMode:1191, WriteModeAIWriter:281, AppAssistant:239, useStoryEngine:358 — all 6 Pattern G locked sites are in chat/AI-writer files). Surface analysis discipline: admin-page CPs surface-check Pattern G as low-prior; chat/AI-writer CPs surface-check Pattern G as high-prior. Heuristic, not lock — surface check still required per file regardless.

Helper-reuse density pattern — graduates to two-data-point pattern (UPDATED v2.22, supersedes v2.21 single-instance observation). v2.21 §9.11 helper-reuse density observation was first instance at CP14 EpisodeDetail (4× reuse on listEpisodeLibraryScenesApi across mount + 3 reload-after-mutation paths; 40% reduction). CP15 WorldSetupGuide is second instance: 3-way reuse on getPageContentApi across sites 1, 2, 4 (multi-tab status-check shape; 25% reduction at the 3-of-8 sites covered by reuse, with 6 helpers/8 sites = 25% file-level reduction). Pattern graduates to two-data-point pattern in v2.22. Two distinct underlying shapes: CRUD + reload-after-mutation (CP14) and multi-tab status-check (CP15) — both produce helper-count reduction via single loader covering multiple call sites. Forecasting heuristic, NOT a new convention — file-local helper convention v2.12 already handles helper reuse natively. Surface analysis discipline: when CRUD + reload OR multi-tab status-check pattern detected, helper-count forecast reduced 25-40% from site count; session-time forecast can be reduced ~20-30% from CP3-zone baseline.

v2.14 internal-helper-refactor pattern — five-data-point validation (UPDATED v2.22, supersedes prior data-point references). Pattern reaches five data points: CP3 (first instance), CP6 (second), CP15 MemoryConfirmation:51 (fourth — apiFetch wrapper, 5 call sites with varying methods), CP15 MemoryBankView:57 (fifth — apiFetch wrapper, 6 call sites with varying methods). Pattern application: when a file has a wrapper function that calls fetch internally and the wrapper is invoked from multiple call sites with varying methods/payloads, preserve the wrapper signature externally and swap the internal fetch for apiClient.request. Wrapper external API unchanged; auth bypass closed. Validated robust across 5 data points spanning CP3 + CP6 + 2× CP15 (fourth instance was at CP3 originally counted only once until CP15 explicit re-survey; the canonical count is 5 instances at end of Track 6 implementation phase).

- Pattern F prophylactic discipline confirmed correct (fourteenth data point). All ~30 helpers use *Api suffix; component-internal handlers use file-local prefixes. No direct shadow conflicts.

- Cross-CP duplication: heavy density across CP15 (largest single-CP cross-CP duplication zone in F-AUTH-1). listRegistriesApi reaches 8-fold (3 new instances in CP15: MemoryBankView + useRegistries + Home pre-CP15 6th); listShowsApi reaches 6-fold (2 new instances: WorldSetupGuide + UniverseProductionPage). All applied per v2.12 file-local convention.

- Path E candidates: ~15 fresh + ~10 dedup-noted GET sites filed for §9.12 Step 3 sweep awareness. Track 6 Path E running list final state recorded for backend audit phase.

- No HTTP method mismatches surfaced. CP15 is the 14th consecutive CP with zero method mismatches (CP3-CP15 cumulative). Total method-correction discoveries remain at 5 across 15 CPs. Track 6 implementation closes with the streak intact.

- Pattern G allowlist UNCHANGED at 6 sites. Verification grep allowlist unchanged in v2.22.

### TRACK 6 IMPLEMENTATION CLOSURE DECLARATION (NEW v2.22 §4.6 marker)

Track 6 implementation phase is COMPLETE.

Backbone state at closure: feature/f-auth-1 HEAD 04777edd; backup at 04777edd; v2.22 fix plan on origin/dev. 466 sites migrated across 15 checkpoints. 813 frontend tests passing across 102 test files (Track 6 grew tests from 135 baseline to 813, +678 new tests). 6 Pattern G locked sites maintained throughout. 22 fix plan revisions (v1.7 → v2.22) without a single corrupted state.

Final inventory state (38 sites across 9 files — all deferred-by-discipline, NOT migratable):

- WorldStudio.jsx (29 sites) — Path E LOCKED PUBLIC cluster, deferred to Step 3 backend audit

- 6 Pattern G locked sites: BookEditor.jsx:58 (keepalive), WriteMode.jsx:1000 (streaming SSE), WriteMode.jsx:1191 (streaming SSE), WriteModeAIWriter.jsx:281 (streaming), AppAssistant.jsx:239 (streaming), useStoryEngine.js:358 (streaming) — cannot migrate to axios per Pattern G locked-exception class

- PressPublisher.jsx:119 (1 site) — CP11 LOCKED PUBLIC retained (intentionally unauthenticated; F-Auth-3 degradeOnInfraFailure exemption)

- External blob fetches (2 sites): UIOverlaysTab.jsx + ProductionOverlaysTab.jsx:108 — S3 user-content URL fetches, not backend API; same disposition class

Track 6 final progress: 466/469 by site count = 99.4% = 100% of migratable scope complete. The 38 deferred sites are all ineligible for migration by structural class (LOCKED PUBLIC, Pattern G locked, external blob).

Pattern library locked across CP2-CP15:

- Patterns A/B/C/D/E (Track 5 era — auth disposition classes)

- Pattern F (v2.6) — Api suffix prophylactic

- Pattern G (v2.10/v2.19) — "can't-migrate-to-axios" exception class with default-on-matching-precedent discipline

- File-local duplication (v2.12) — duplicate locally rather than import; ceiling semantics clarified at v2.22 (8-fold operational, no hard cap)

- Method-branching split (v2.13)

- Multipart upload pattern (v2.14)

- Internal-helper-refactor (v2.14, 5-data-point validation at v2.22)

- Existing-test-file amendment (v2.15/v2.17/v2.19)

- Hook module-scope helper (v2.16/v2.19, 3-data-point validation)

- Service-module precedence inversion (v2.16/v2.20, 3-data-point validation)

- URL-branching split (v2.17)

- Mixed PUBLIC+BUG within file (v2.18) — CP11 PressPublisher only F-AUTH-1 instance

- Combined-axis branching split — stacking validated (v2.18)

- Callback-cluster preservation (v2.19 observation)

- Data-driven URL pass-through (v2.20 formal lock, 1 implementation at CP13 — distinct from internal-helper-refactor)

- Outer try/catch cleanup (v2.20 observation)

- Pattern G zero-trigger admin-page heuristic (v2.20/v2.21/v2.22 — 4-data-point validation)

- Partial-migration extension (v2.20/v2.21/v2.22 — 5-data-point validation)

- Helper-reuse density forecasting heuristic (v2.21/v2.22 — 2-data-point validation)

Disciplines validated across 15 checkpoints: §9.13 Rule 2 backup-push discipline (15 same-turn pushes after each CP approval); Rule 6 integrator main-sync auto-merge benign (multiple force-overwrites across the arc); surface-with-cost-estimation (locked v2.8, conservative bias 1.4-2.0x across CP12-CP15 actuals); two-tier branch separation (feature/f-auth-1 implementation vs origin/dev docs); fix-plan revision atomicity (one revision per CP closure, integrator-side commits with explicit version bump).

HTTP method mismatch streak: 14 consecutive zero CPs (CP3-CP15). Total method-correction discoveries: 5 across 15 CPs (3 from CP2 mid-flow + 1 from CP7 surface + 1 from CP9 surface verification). Pattern remains: file-level variation, not systemic. Track 6 implementation closes with the streak intact.

Next phase: Step 3 backend sweep. Different scope and shape than Track 6 implementation. Step 3 work includes per-route backend disposition adjudication (PUBLIC vs requireAuth), Path E candidate classification (running list of GET sites filed across CP2-CP15 for backend-side adjudication), HTTP method correction backend-side, security review, and reconciliation of the WorldSetupGuide reclassification + ProductionOverlaysTab reclassification into the canonical inventory. The pattern library locked across CP2-CP15 carries forward as documentation but does not drive Step 3 architectural decisions in the same way; the discipline that does carry forward is surface-with-cost-estimation, §9.13 backup-push discipline, and the conservative-forecasting bias.

### Pacing model — 15 data points, Track 6 final state (NEW v2.22, supersedes v2.21)

Fifteen checkpoints across Track 6:

- CP2 (1 file, 64 sites): 4 sessions, ~16 sites/session.

- CP3 (1 file, 33 sites + 2 Pattern G): 3 sessions, ~11 sites/session.

- CP4 (1 file, 18 sites): 1 session, 18 sites/session.

- CP5 (3 files uniform-simple, 28 sites): 1 session, 28 sites/session.

- CP6 (4 files heterogeneous, 38 sites): 1 session, 38 sites/session.

- CP7 (10 files long-tail simplest-first, 39 sites): 1 session, 39 sites/session.

- CP8 (10 files long-tail simplest-first, 38 sites): 1 session, 38 sites/session.

- CP9 (8 files long-tail simplest-first, 40 sites): 1 session, 40 sites/session.

- CP10 (8 files long-tail simplest-first, 42 sites): 1 session, 42 sites/session.

- CP11 (17 files cleanup-overlap, 51 BUG-class migrated): 1 session, 51 sites/session.

- CP12 (1 file dedicated high-density, 13 sites + 1 Pattern G locked): 1 session, 13 sites/session, 7.5 min/site.

- CP13 (1 file dedicated high-density, 11 sites + 0 Pattern G): 1 session, 11 sites/session, 6.8 min/site.

- CP14 (1 file dedicated high-density, 10 sites + 0 Pattern G): 1 session, 10 sites/session, 5.0 min/site.

- CP15 (23 files multi-file long-tail, 43 sites): 1 session, 43 sites/session, 2.8 min/site. Lowest cost-per-site observed in F-AUTH-1.

Track 6 final pacing characteristics:

- Total session count across 15 CPs: 22 sessions (CP2 4-session + CP3 3-session + 13 single-session). Implementation phase elapsed time: distributed across multiple Evoni work sessions over the development period.

- CP3 zone (high-density single, 10-13 sites/session): 4 data points (CP3, CP12, CP13, CP14). CP15 closes the dedicated-single shape.

- CP11 zone reframes (long-tail multi-file with heavy duplication, 43-55 sites/session): 2 data points (CP11 51 sites/session at 17 files; CP15 43 sites/session at 23 files). Lower edge of band achieved by larger file count + smaller average file site count.

- Conservative forecasting bias confirmed across 15 CPs: CP12 ~2.0x; CP13 ~1.7x; CP14 ~1.7x; CP15 ~1.0x (within forecast range, lower estimate). Average forecast/actual ratio: 1.5-2.0x. Surface-with-cost-estimation discipline accepts this bias as design feature throughout Track 6.

- Decreasing-cost trend across CP12-CP14 (7.5 → 6.8 → 5.0 min/site) for dedicated-single shape; CP15 at 2.8 min/site is heaviest cross-CP duplication density (mechanical translation drives per-site cost lowest).

### Long-tail forecast — Track 6 implementation FINAL state (LOCKED v2.22)

Track 6 implementation phase complete. Final inventory state:

- Pre-Track 6 (start): ~603 sites flagged BUG-class via Track 5 raw-fetch triage

- Corrected denominator (post-CP3 reconciliation): ~469 actual

- Sites migrated across CP2-CP15: 466 sites

- Sites deferred-by-discipline (post-CP15 inventory): 38 sites across 9 files (29 WorldStudio Path E + 6 Pattern G + 1 PressPublisher LOCKED PUBLIC + 2 external blob)

- Track 6 progress final: 466/469 = 99.4% by site count = 100% of migratable scope

- Pattern G locked exceptions: 6 (UNCHANGED throughout CP12-CP15 — last addition at CP12 useStoryEngine:358)

- Frontend test suite: 813/813 passing across 102 test files (Track 6 grew tests +678 from baseline 135)

- Backbone state: HEAD 04777edd on feature/f-auth-1; backup 04777edd on claude/f-auth-1-backup; fix plan v2.22 on origin/dev.

No remaining migration work for Track 6 implementation phase. All migratable scope is complete. The 38 deferred sites do not migrate by structural class (LOCKED PUBLIC, Pattern G locked, external blob) — they require Step 3 backend sweep adjudication (Path E classification, mixed-disposition reconciliation) and/or remain as locked exceptions indefinitely.

## §5 — Step 3 Backend Sweep Fix Plan (NEW v2.23, locks Step 3 implementation phase)

Step 3 backend sweep closes the F-AUTH-1 keystone (codebase-wide auth bypass at middleware/auth.js per Audit Handoff v8 §4.1). Track 6 closed the frontend side — every BUG-class fetch site migrated to apiClient with Bearer token. Step 3 closes the backend side — every write handler currently on optionalAuth or no-auth gets requireAuth (or admin-tier middleware where appropriate). Without Step 3, the F-AUTH-1 keystone remains open: optionalAuth lets unauth requests through to handlers that consume req.user via the silent-null fallback pattern (req.user?.sub).

Step 3 planning phase COMPLETE. Backend route surface inventory + Path E reconciliation matrix + scope adjudication + CP structure proposal + inventory amendments folded — all locked in Step_3_Planning_Inventory.md (generated on feature/f-auth-1, summarized in v2.23). 17 adjudication items locked. Step 3 fix plan section folds the planning output into canonical fix-plan structure.

### §5.1 — Step 3 sweep surface (NEW v2.23, derived from Step 3 planning inventory)

Backend route surface inventory:

- 142 backend route files under src/routes/ (including 9 in memories/ subdir)

- ~135 distinct mount points in src/app.js

- 1,397 total handlers across all route files

- 894 write handlers (POST/PUT/PATCH/DELETE)

- ~16 writes already on requireAuth + ~75 on authenticateToken (Cognito strict)

- F-AUTH-1 sweep surface (writes on optionalAuth or no-auth): ~803 handlers

- 22 mixed-middleware files + 29 no-auth files (handlers > 0, all middleware counts 0 — wide-open auth bypass at file level)

- Path E candidates filed across CP2-CP15: ~106 distinct endpoints (~120 with CP15 fresh additions)

- F-AUTH-3 degradeOnInfraFailure consumers TODAY: 0 (factory built, no routes opt in; press.js + manuscript-export.js are the 9 expected consumers per CP11 PressPublisher precedent)

- F-AUTH-5 sites verified: 6/6 confirmed in current codebase (decisionLogs:22, cursorPathController:22, iconCueController:22, musicCueController:20, productionPackageController:22, thumbnails:80) — all resolve naturally as F-AUTH-1 byproducts

- HTTP method corrections from Track 6: 5 (CP2 ×3 mid-flow + CP7 ×1 surface + CP9 ×1 surface) — backend route declarations need verification + correction

Concentrated sweep zones (top 10 by write-handler count): sceneSetRoutes.js 51, worldEvents.js 38, worldStudio.js 35 (Path E LOCKED PUBLIC), characterRegistry.js 31, episodes.js 46-mixed (15 authenticateToken + 4 optionalAuth + 3 requireAuth + ~55 no-auth + 2 commented-out — highest-risk file), storyteller.js 24, tierFeatures.js 24, socialProfileRoutes.js 24, wardrobe.js 25 (mixed; controller-bound routes have no auth), memories/* aggregator 52 across 6 sub-routers.

### §5.2 — Step 3 disposition tier matrix (NEW v2.23 architectural lock)

Step 3 sweep applies one of 5 disposition tiers per handler. Tier assignment is the central architectural decision per route. The matrix is the canonical reference for which middleware applies where; per-CP surface reports enumerate handlers by tier.

- Tier 1 — requireAuth (default). Per-user data, mutations, AI generation, all routes that consume req.user as authenticated identity. The bulk of the ~803-handler sweep surface. Migration shape: replace optionalAuth (or add to no-auth handlers) with requireAuth from middleware/auth.js. Test impact: route-health tests gain requireAuth assertion (401 without token, 200/201 with valid token).

- Tier 2 — requireAuth + authorize(['ADMIN']). Admin tooling, internal infrastructure, audit logs, internal financial/system data. Pattern is mature in codebase already (middleware/auth.js:300 authorize() helper, in production use across admin.js + auditLogs.js + templates.js + assets.js). Routes locked to Tier 2: site-organizer, design-agent, auditLogs, templates (5 handlers — partial-migration target), seed.js (in non-prod), queue-monitor (Bull-board UI), cfoAgentRoutes, aiUsageRoutes. Migration shape: authenticate, authorize(['ADMIN']) applied at handler or router-mount level.

- Tier 3 — optionalAuth({ degradeOnInfraFailure: true }). LOCKED PUBLIC routes that consume req.user (e.g., for personalization-when-authenticated, audience-growth scenarios). Frontend retains raw fetch with PUBLIC marking. Per CP11 PressPublisher precedent. Routes locked to Tier 3: press.js (6 GETs), manuscript-export.js (3 GETs) — F-AUTH-3 expected consumers; WorldStudio cluster subset (where req.user consumption surfaces). Migration shape: replace plain optionalAuth with optionalAuth({ degradeOnInfraFailure: true }) factory invocation. F-AUTH-3 consumer count goes from 0 to 9+ in CP1.

- Tier 4 — plain optionalAuth (LOCKED PUBLIC where req.user not consumed). Published-only data routes that don't personalize per-user. Routes locked to Tier 4: WorldStudio cluster subset (the 29-site Path E LOCKED PUBLIC cluster, split between Tier 3 and Tier 4 per req.user consumption analysis at CP3 surface). Migration shape: leave optionalAuth as-is, ADD // PUBLIC: published-only data — see Audit Handoff §4.1 comment with brief rationale (so future audits don't re-classify as bugs).

- Tier 5 — env-gated mount (development-only). Routes that should not be reachable in production. Routes locked to Tier 5: seed.js (3 handlers — DB seed endpoints). Migration shape: app.js mount expression becomes if (process.env.NODE_ENV !== 'production') app.use(...); non-prod still requires Tier 2 (admin-role). Belt-and-suspenders.

Two-tier sweep, not single-tier. Step 3 isn't just optionalAuth → requireAuth. Each handler gets per-route adjudication into one of the 5 tiers. Per-CP surface reports must enumerate handlers by tier; per-CP closure reports verify no handlers fell through unclassified.

### §5.3 — Adjudication items locked (17 items from planning phase)

17 adjudication items locked from planning phase (Step_3_Planning_Inventory.md). Listed in adjudication-item order for traceability:

- Item 1 (Step 3 scope IN/OUT): LOCKED. F-AUTH-1 sweep IN, Path E disposition IN, F-AUTH-2 boot-fail IN parallel (CP1 must land before CP2-CP10), F-AUTH-3 exemption list IN (CP1), F-AUTH-5 IN as F-AUTH-1 byproduct, HTTP method corrections IN (CP11 cleanup), inventory v2 reconciliation IN as prerequisite. jwtAuth path OUT per Decision D20 (compositions.js JWT subset stays as-is; the 22 no-auth subset within compositions.js is IN at CP7).

- Item 2 (Track 7 timing): LOCKED Option C (hybrid). Step 3 + Track 7 share planning + classification matrix; execute as separate CP series. After each Step 3 CP locks PUBLIC routes, a follow-up Track 7 mini-CP reverts the corresponding frontend sites. Path E classification is the work product both phases consume — sharing avoids redoing analysis.

- Items 3 + 4 (site-organizer + design-agent GETs): LOCKED Tier 2 (requireAuth + authorize(['ADMIN'])). Public-internet-reachable per Evoni empirical inspection (mounted at /api/v1/site-organizer + /api/v1/design-agent unconditionally; nginx /api proxies without IP allowlist or basic auth). Route exposes runFullScan / runFullAudit output (route map, file structure, design-token compliance) — sensitive surface even for authenticated non-admin. CP10 scope.

- Items 5 + 6 (auditLogs + templates): LOCKED Tier 2 (requireAuth + authorize(['ADMIN'])). Both files are partial-migration targets — auditLogs.js lines 64+128 already use authenticate + authorize(['ADMIN']); templates.js partial 3-of-5. Apply existing pattern uniformly across all handlers in each file. CP10 scope. Existing partial-migration shape collapses item 6 into item 5 disposition.

- Item 7 (seed.js): LOCKED Tier 5 + Tier 2. Env-gated mount expression: if (process.env.NODE_ENV !== 'production') app.use('/api/v1/seed', authenticate, authorize(['ADMIN']), seedRoutes);. Combined gate: prod skip + non-prod still requires admin-role. CP10 scope.

- Item 8 (queue-monitor): LOCKED Tier 2 at mount line. Bull-board sub-router (router.use('/', serverAdapter.getRouter())) bypasses Express-route-level auth; auth must apply at mount line in app.js. Mount expression: app.use('/admin/queues', authenticate, authorize(['ADMIN']), queueMonitorRoutes);. Production keeps Bull-board available for ops; admin-role is the access gate. NOT disabled in prod. CP10 scope.

- Item 9 (thumbnails GETs): LOCKED Tier 1 (requireAuth). Per-user content; no admin-role required. CP9 scope.

- Item 10 (compositions 22 no-auth handlers): LOCKED Tier 1 (requireAuth) on the 22 no-auth subset. The 7 jwtAuth handlers stay as-is per D20 (out of F-AUTH-1 scope). Mixed-middleware shape acceptable — auth.js itself has the same shape (login/refresh public + /me/logout JWT). CP7 scope.

- Item 11 (Cadence option lock): LOCKED Hybrid 10 domain CPs + 1 cleanup CP. Per-route-file (~132 CPs) too granular; per-disposition-class (3 CPs) too coarse; per-domain (10-15) matches Track 6 cadence. Hybrid threads the needle.

- Item 12 (CP1 scoping): LOCKED combined F-AUTH-2 + F-AUTH-3 in single CP1. F-AUTH-2 lazy-init refactor (~30 LOC change at middleware/auth.js) + F-AUTH-3 9-handler degradeOnInfraFailure migration share dependency (F-AUTH-3 depends on F-AUTH-2 being production-safe). Both touch auth middleware infrastructure. No CP0 split.

- Item 13 (CP boundaries): LOCKED with re-cluster. Files moved per Q13 redistribution: franchiseBrainRoutes + pdfIngestRoute → CP7; onboarding + shows + uiOverlayRoutes + todoListRoutes → CP2; universe → CP6; layers → CP9; authorNoteRoutes → CP7. Drafted CP10 duplicates removed (tierFeaturesRoutes, wantFieldRoutes, wardrobeEventRoutes, manuscript-export, press, episodeScriptWriterRoutes, feedPipelineRoutes, feedEnhancedRoutes). Final CP file/handler counts: CP2 21/170, CP6 18/118, CP7 28/160, CP9 19/84, CP10 20/75. Total Step 3 estimate ~20-22 sessions unchanged.

- Item 14 (Episodes.js commented-out auth): LOCKED handle in CP2. Lines 400 + 473 with // ✅ COMMENTED OUT FOR TESTING markers resolved when episodes.js is on the operating table at CP2. No deferral to CP11 cleanup.

- Item 15 (WorldStudio backend marking pattern): LOCKED two-tier within Tier 3/Tier 4 split. Routes consuming req.user → Tier 3 (optionalAuth({ degradeOnInfraFailure: true }) + PUBLIC comment with rationale). Routes NOT consuming req.user → Tier 4 (plain optionalAuth + PUBLIC comment with rationale). Per-route adjudication at CP3 surface report. Brief rationale required on every PUBLIC marking so future audits don't re-classify as bugs.

- Item 16 (wardrobeLibrary.js:18 env-conditional middleware): LOCKED fix in CP5 wardrobe cluster. Replace const authMiddleware = isDevelopment ? <noop> : authenticate with uniform authenticate everywhere; remove the conditional. Same domain, same CP.

- Item 17 (press.js + manuscript-export.js lazy-noop fallback removal): LOCKED tied to CP1 F-AUTH-2 fix. The lazy-noop fallback IS the auth bypass mechanism that fires if F-AUTH-2 boot-fail triggers. Remove try/catch require pattern; fail-fast on auth import. Once F-AUTH-2 lazy-init makes auth.js boot-safe, the defensive try/catch becomes unnecessary AND a security liability. CP1 closes both halves of F-AUTH-2/3 double-jeopardy; partial fix is worse than no fix because it creates false sense of safety.

### §5.4 — Step 3 CP structure (LOCKED v2.23, 11 CPs)

Domain partitions per Item 13 lock. Each CP = 1 commit, 1-2 sessions (CP10 forecast holds at 2 sessions post-recluster):

- CP1 — F-AUTH-2 + F-AUTH-3 (small, focused). middleware/auth.js lazy-init refactor (~30 LOC) + press.js 6 handlers + manuscript-export.js 3 handlers Tier 3 migration + lazy-noop fallback removal in both files. ~9 handlers + lazy-init. 1 session.

- CP2 — Episodes cluster. episodes.js (highest-risk file — landmines at lines 400+473 + 55 no-auth writes), episodeBriefRoutes.js (reference model), episodeOrchestrationRoute.js, episodeScriptWriterRoutes.js, gameShows.js, iconCues.js, cursorPaths.js, musicCues.js, productionPackage.js, lalaScripts.js, scriptParse.js, timelineData.js, wardrobeApproval.js, phonePlaythroughRoutes.js, phoneAIRoutes.js, phoneMissionRoutes.js, sceneStudioEpisodeRoutes.js, + onboarding.js, shows.js, uiOverlayRoutes.js, todoListRoutes.js (Q13 redistribution). 21 files / ~170 handlers (upper edge of session budget). Mount-collision on /api/v1/episodes (9 routers share prefix) — surface report enumerates all 9 routers explicitly. Episodes.js commented-out auth resolved at CP2 (Item 14). 2 sessions.

- CP3 — World cluster. world.js, worldEvents.js (5 AI-cost POSTs already on requireAuth — reference model), worldStudio.js (29-site Path E LOCKED PUBLIC cluster — Tier 3/Tier 4 split per Item 15), worldTemperatureRoutes.js (zero handlers, no sweep). 4 files / ~85 handlers. Per-route Tier 3 vs Tier 4 adjudication at surface. 2 sessions.

- CP4 — Scene cluster. sceneSetRoutes.js (largest single-file sweep zone, 51 writes), scenes.js (5 dev/test no-auth — remove or promote), sceneTemplates.js, sceneLibrary.js, sceneLinks.js, sceneProposeRoute.js. 6 files / ~85 handlers. 2 sessions.

- CP5 — Wardrobe cluster. wardrobe.js (controller-bound routes have no auth — full per-handler audit), wardrobeLibrary.js (env-conditional authMiddleware removal — Item 16), wardrobeBrands.js, wardrobeEventRoutes.js, outfitSets.js (audit §4.1(b) sub-form closure), hairLibraryRoutes.js, makeupLibraryRoutes.js. 7 files / ~80 handlers. 2 sessions.

- CP6 — Character cluster. characterRegistry.js (largest no-auth-write surface, ~26 no-auth writes), characterAI.js, characterCrossingRoutes.js, characterDepthRoutes.js, characterFollowRoutes.js, characterGenerationRoutes.js, characterGenerator.js, characterGrowthRoute.js, characterSparkRoute.js, characters.js, entanglementRoutes.js, relationships.js, therapy.js, consciousness.js, mirrorFieldRoutes.js, wantFieldRoutes.js, feedRelationshipRoutes.js, + universe.js (Q13 redistribution — universe upstream of character generation). 18 files / ~118 handlers. 2 sessions.

- CP7 — Storyteller + memories cluster. storyteller.js, memories/* × 7 (assistant, core, engine, extras, interview, planning, stories, voice — sweep must touch each sub-router individually since memories/index.js is an aggregator), stories.js, storyEvaluationRoutes.js, storyHealth.js, markers.js, beats.js, decisions.js, decisionLogs.js (F-AUTH-5 site), decisionAnalytics.js, arcRoutes.js, arcTrackingRoutes.js, evaluation.js, continuityEngine.js, novelIntelligenceRoutes.js, eventGeneratorRoute.js, templateStudio.js, compositions.js no-auth subset (Item 10 — Tier 1 on 22 handlers; jwtAuth subset stays as-is per D20), + franchiseBrainRoutes.js, pdfIngestRoute.js, authorNoteRoutes.js (Q13 redistribution). 28 files / ~160 handlers. 2 sessions, upper edge.

- CP8 — Social-profiles + feed cluster. socialProfileRoutes.js, socialProfileBulkRoutes.js, feedSchedulerRoutes.js, feedPostRoutes.js, feedPipelineRoutes.js, feedEnhancedRoutes.js, undergroundRoutes.js, tierFeatures.js, pageContent.js (resolve duplicate import — Anomaly #9), calendarRoutes.js. 10 files / ~115 handlers. 2 sessions.

- CP9 — Production tooling cluster. thumbnails.js (Item 9 — Tier 1 on 6 GETs; F-AUTH-5 site at line 80), thumbnailTemplates.js, metadata.js, assets.js, imageProcessing.js, roles.js, editMaps.js, footage.js, animatic.js, audio-clips.js, character-clips.js, scriptGenerator.js, scriptAnalysis.js, scripts.js, lala-scene-detection.js, youtube.js, texture-layer, season-rhythm, + layers.js (Q13 redistribution). 19 files / ~84 handlers. 2 sessions.

- CP10 — Admin/internal cluster. admin.js, aiUsageRoutes.js (Tier 2), cfoAgentRoutes.js (Tier 2), siteOrganizerRoutes.js (Tier 2 — Item 3), designAgentRoutes.js (Tier 2 — Item 4), auditLogs.js (Tier 2 — Item 5), seed.js (Tier 5 + Tier 2 — Item 7), session.js, propertyRoutes.js, auth.js /me-/logout review, jobs.js, files.js, search.js, processing.js, queue-monitor.js (Tier 2 at mount line — Item 8), amberSessionRoutes.js, amberDiagnosticRoutes.js, upgradeRoutes.js, opportunityRoutes.js, feedRelationshipRoutes.js. 20 files / ~75 handlers. Re-clustered per Q13 (drafted duplicates removed; 8 files relocated to CP2/CP6/CP7/CP9). All admin/system/internal-tooling — coherent domain. 2 sessions.

- CP11 — Cleanup CP. HTTP method corrections (5 routes from CP2/CP7/CP9 frontend surfaces — verify backend route declarations match) + cross-domain edge cases + verification grep + post-sweep audit. Small, focused. 1 session.

Total Step 3 estimate: 11 CPs / ~20-22 sessions. Conservative bias applied (1.5-2.0x per CP12-CP15 trajectory). Backend sweep CPs may run faster than frontend (mechanical middleware swap is ~5 LOC per handler vs ~15-30 LOC per frontend migration), but per-route adjudication overhead is higher (each route needs Tier 1-5 classification check).

### §5.5 — Step 3 anomalies (NEW v2.23, requires explicit handling per CP)

9 critical anomalies surfaced during planning phase — each requires explicit handling at the CP that touches the relevant file:

- Anomaly 1: memories/index.js aggregator composes 6 sub-routers; sweep must touch each file individually (~72 handlers in memories/*). CP7 surface report enumerates per sub-router.

- Anomaly 2: wardrobeLibrary.js:18 env-conditional middleware. Item 16 lock applies — fix in CP5.

- Anomaly 3: episodes.js lines 400+473 commented-out auth. Item 14 lock applies — resolve in CP2.

- Anomaly 4: press.js + manuscript-export.js lazy-noop fallback (F-AUTH-2 double-jeopardy). Item 17 lock applies — fix in CP1.

- Anomaly 5: scaffolded route files (luxuryFilterRoutes, seasonRhythmRoutes, worldTemperatureRoutes — registered in app.js but ZERO handlers). NO sweep action. Filed in CP3 (worldTemperature) + CP9 (seasonRhythm) for documentation.

- Anomaly 6: queue-monitor.js Bull-board sub-router bypass. Item 8 lock applies — auth at mount line in CP10.

- Anomaly 7: pdfIngestRoute.js:257 Express error handler (NOT auth middleware — counted as no-auth in inventory). Document in CP7 closure.

- Anomaly 8: /api/v1/episodes mount overlap (9 routers share the prefix; app.use order disambiguates). Surface report at CP2 enumerates all 9 routers with per-router handler counts and middleware classes; silent shadowing risk if path patterns conflict.

- Anomaly 9: pageContent.js duplicate import (router.use(optionalAuth) AND imports authenticateToken — redundant). Resolve in CP8.

Critical callout: outfitSets.js confirms audit §4.1(b) sub-form. CP5 sweep makes the audit finding closure-quality.

### §5.6 — Step 3 readiness checklist

- State verified: HEAD 04777edd (Track 6 closure), backup matches, working tree clean

- v2.23 fix plan landed on origin/dev with Step 3 plan + adjudications recorded

- All 17 planning-phase adjudication items locked

- Step 3 disposition tier matrix locked (5 tiers; per-CP surface reports enumerate handlers by tier)

- Backend test suite baseline captured (pre-Step-3 pass count for delta tracking)

- Per-route route-health test stubs reviewed (existing tests at tests/unit/routes/* and npm run validate)

- Step 3 CP1 surface report kickoff message ready (covers F-AUTH-2 lazy-init + F-AUTH-3 exemption list + lazy-noop fallback removal)

- Track 7 timing locked Option C (hybrid) — Track 7 mini-CPs follow each Step 3 CP with PUBLIC route classifications

After v2.23 lands on origin/dev, Step 3 CP1 kicks off in fresh Claude Code session on feature/f-auth-1. CP1 is small + focused (F-AUTH-2 lazy-init refactor + F-AUTH-3 9-handler migration + lazy-noop removal); 1 session forecast.

### §5.7 — Step 3 CP1 architectural findings (LOCKED v2.24, COMPLETE — F-AUTH-2 lazy-init + F-AUTH-3 5-handler migration + lazy-noop fallback removal)

CP1 completed at commit 05cd536d (single squashed commit, 4 work-product WIPs collapsed; single session, ~75 min actual within ~105-130 min Option A forecast — 1.4-1.7x conservative bias confirmed for backend Step 3 cadence). Three distinct work products in one commit: WP1 F-AUTH-2 lazy-init refactor at src/middleware/auth.js (+22 LOC net via getCognitoConfig/getIdTokenVerifier/getAccessTokenVerifier lazy getters with memoized module-scope caches); WP2 F-AUTH-3 5-handler migration to Tier 3 (consumer count 0 → 5); WP3 lazy-noop fallback removal at press.js + manuscript-export.js (replaced try/catch require pattern with direct destructuring import). Strict execution sequence WP1 → WP3 → WP2 followed. Backend test suite: 1402 → 1417 passing (+15 tests, +1 suite, 0 regressions, 0 failed). Backed up at 05cd536d on claude/f-auth-1-backup.

Per-work-product execution outcomes:

- WP1 — F-AUTH-2 lazy-init refactor (middleware/auth.js): eager const idTokenVerifier + accessTokenVerifier (lines 11-23 pre-CP1) replaced with lazy getters; getCognitoConfig() shared helper extracted (Decision 4 refinement); runtime guard at lines 50-54 consolidated into getter env-var check; structured AUTH_CONFIG_MISSING runtime error replaces module-load boot crash. Pattern: let _verifier = null; const get = () => { if (!_verifier) { /* env check + throw or instantiate */ } return _verifier; }. Module-load safety newly testable via jest.resetModules + env manipulation pattern (see §5.8 below).

- WP2 — F-AUTH-3 5-handler factory invocation: 5 handlers migrated to Tier 3 (optionalAuth({ degradeOnInfraFailure: true })): press.js GETs at lines 455 /characters + 501 /characters/:slug; manuscript-export.js GETs at lines 123 /book/:bookId/meta + 153 /book/:bookId/docx + 561 /book/:bookId/pdf. Per Item 1 lock OPTION A — 4 press.js POST handlers (lines 361 /seed-characters, 531 /advance-career, 607 /generate-post, 696 /generate-scene) DEFERRED to CP10 with Tier 1 + aiRateLimiter on AI POSTs. F-AUTH-3 consumer count 0 → 5 verified by closure grep.

- WP3 — Lazy-noop fallback removal: press.js try/catch require pattern (5 lines pre-CP1) replaced with const { optionalAuth } = require('../middleware/auth'); direct destructuring import. manuscript-export.js same shape (7 lines pre-CP1). Both files now fail-fast on auth import error; defensive cruft removed. F-AUTH-2/F-AUTH-3 double-jeopardy at the 2 files closed.

Press.js scope correction (NEW v2.24 §5.5 amendment, supersedes v2.23 §5.5 wording). v2.23 §5.5 + planning §A.7 + CP1 kickoff stated "press.js (6 handlers — all GETs)". CP1 surface-time empirical inspection caught the misclassification: press.js has 6 handlers = 2 GETs + 4 POSTs. The 4 POSTs are state mutations + AI-cost incurring operations — NOT semantically equivalent to "press kit GET during outage." Tier 3 disposition would have created security regression worse than current state (uncontrolled state changes + uncontrolled API spend during Cognito outage). Item 1 OPTION A locked the correction: 5 of 6 handlers in CP1, 4 POSTs deferred to CP10 with Tier 1 + aiRateLimiter on AI POSTs. Surface-before-execute discipline confirmed essential for Step 3 — every CP's surface report MUST verify per-handler classification empirically; never assume planning phase or fix-plan classifications hold.

Press.js partial-migration first Step 3 instance (NEW v2.24 §9.11 lock — partial-migration extension extends to Step 3). Track 6 graduated partial-migration extension to five-data-point pattern at v2.22 (CP13 + CP14 + CP15 × 3). CP1 contributes the first Step 3 instance: press.js (5 of 6 handlers migrated in CP1, 4 POSTs in CP10). Pattern robust across phase boundaries — partial-migration extension is now a six-data-point pattern spanning Track 6 frontend + Step 3 backend. Surface analysis discipline: when CP surface report encounters a route file with handlers spanning multiple disposition tiers, partial-migration extension is the default test; per-handler tier classification at surface determines per-handler CP assignment.

- All 3 verification greps pass: (1) F-AUTH-3 consumer count = 5 in src/routes/ (was 0); (2) Lazy-noop fallback in press.js + manuscript-export.js = 0 (was 2); (3) F-AUTH-2 lazy-init pattern present at src/middleware/auth.js (getIdTokenVerifier + getAccessTokenVerifier + getCognitoConfig).

- Backend test suite delta: +15 tests (vs surface forecast of ~7) — defensive scaffolding emerged in execution per locked expectation. 13 structural tests in new tests/unit/routes/press-manuscript-degrade.test.js (per-handler factory invocation assertions) + 2 module-load safety tests in auth-gaps.test.js. Tests anticipated count remains FLOOR not ceiling per v2.24 §9.11 carry-forward.

- No HTTP method mismatches surfaced. CP1 didn't change any methods (backend method corrections deferred to CP11 cleanup). Track 6 streak (14 consecutive zero CPs CP3-CP15) closed at Track 6 boundary; Step 3 starts its own counter at 1.

### §5.8 — Lazy-noop fallback removal universal discipline (NEW v2.24 §9.11 lock — Step 3 universal pattern correction)

CP1 surface-time grep across all route files revealed the lazy-noop fallback pattern is endemic across ~40 additional route files — NOT isolated to press.js + manuscript-export.js as planning §A.7 + Audit Handoff v8 §4.1 stated. Each is a F-AUTH-2/F-AUTH-3 double-jeopardy site by the same mechanism CP1 just closed at 2 files: defensive try/catch require + noop middleware fallback. If F-AUTH-2 boot-fail triggers (regex tightens, env var goes missing, lib upgrade incompatibility), every one of those ~40 files silently degrades to no-auth.

Lazy-noop fallback removal universal discipline (LOCKED v2.24 §9.11). When sweeping a route file in any Step 3 CP, the lazy-noop try/catch require + noop fallback pattern (if present) MUST be replaced with direct destructuring import in the same commit. Pattern: const { optionalAuth } = require('../middleware/auth'); (or similar destructuring per file's middleware needs). Pre-CP grep + post-CP grep verifies cleanup. Lazy-noop removal is structurally tied to the F-AUTH-2/F-AUTH-3 fix at CP1; without it, F-AUTH-2 boot-fail silently degrades the affected files to no-auth.

CP-level distribution of lazy-noop sites (cross-referenced against v2.23 §5.4 CP scope; per-CP surface report MUST re-grep at execution time to catch any missed by CP1 surface):

- CP2 (Episodes cluster): scriptParse.js, lala-scene-detection.js, onboarding.js, todoListRoutes.js (~4 files)

- CP3 (World cluster): world.js, worldEvents.js, worldStudio.js (~3 files)

- CP4 (Scene cluster): none surfaced in CP1 grep; re-grep at CP4 surface for completeness

- CP5 (Wardrobe cluster): wardrobe.js, wardrobeBrands.js, wardrobeLibrary.js (~3 files)

- CP6 (Character cluster): characterAI.js, characterDepthRoutes.js, characterFollowRoutes.js, characterGenerator.js, characterRegistry.js, characterSparkRoute.js, consciousness.js, relationships.js, therapy.js, universe.js (~10 files — largest concentration)

- CP7 (Storyteller + memories cluster): arcRoutes.js, evaluation.js, generate-script-from-book.js, memories/* × 8 (assistant, core, extras, stories, voice, engine, interview, planning), storyEvaluationRoutes.js, storyHealth.js, storyteller.js, careerGoals.js (~14 files — largest concentration)

- CP8 (Social-feeds cluster): feedSchedulerRoutes.js, socialProfileRoutes.js, socialProfileBulkRoutes.js, tierFeatures.js (~4 files)

- CP9 (Production tooling cluster): none surfaced in CP1 grep; re-grep at CP9 surface for completeness

- CP10 (Admin/internal cluster): opportunityRoutes.js (~1 file)

Per-CP overhead: ~5-10 minutes per file for lazy-noop removal (mechanical 5-7 line try/catch → 1 line direct import). Total Step 3 estimate stays at ~20-22 sessions; CP2-CP10 each absorb ~30-60 min of additional work depending on file count per cluster. CP1's bias-under-forecast (1.4-1.7x) provides buffer.

Per-CP discipline: surface report at each CP MUST re-grep for lazy-noop fallback in scope files; closure report MUST verify removal grep returns 0 in CP zone. Discipline carries forward unbroken from CP1 verification grep template.

### §5.9 — Module-load safety test pattern (NEW v2.24 §9.11 lock — Step 3 testing primitive)

CP1 introduced the first module-load safety test pattern in F-AUTH-1 program. Pattern: jest.resetModules() + env-var manipulation + require('../module') assertion (success on empty env = no boot crash; runtime call throws structured error on missing env). The pattern is reusable for any future lazy-init refactor across Step 3 (or future tracks).

Two CP1 module-load safety tests in tests/unit/middleware/auth-gaps.test.js:

- Case 1 — require() with no Cognito env vars succeeds (no boot crash): delete env vars, jest.resetModules, require module, expect not to throw. Verifies F-AUTH-2 boot-fail closure.

- Case 2 — call path throws wrapped AUTH_CONFIG_MISSING when env vars absent: NODE_ENV=production force, delete env vars, require module, call verifyToken, expect rejected with cause.code AUTH_CONFIG_MISSING. Verifies runtime error replaces silent module-load crash.

Pattern application discipline (LOCKED v2.24 §9.11). Module-load safety tests are required for any Step 3 CP that introduces a lazy-init refactor (or modifies an existing one). The pattern verifies the boot-safety property — that require() of the modified module succeeds with empty env. Step 3 CPs that include lazy-init refactors: CP1 (auth.js, complete). Future CPs that may include lazy-init refactors: TBD per surface analysis. The pattern is the architectural primitive for module-load resilience verification.

### §5.10 — Step 3 pacing model — first data point (NEW v2.24)

CP1 establishes Step 3 baseline: 1 session, ~75 min actual vs ~105-130 min forecast (Option A). 1.4-1.7x conservative bias confirmed for backend Step 3 cadence.

- CP1 (3 work products in single commit): 1 session, 5 Tier 3 handlers + lazy-init refactor + lazy-noop removal at 2 files. ~75 min actual within forecast range, lower estimate. Cost-per-work-product: WP1 ~15 min / WP2 ~5 min / WP3 ~5 min / test scaffolding ~25 min / squash + verification + closure ~10 min / baseline + post test runs ~15 min combined.

Step 3 backend cadence characteristics (preliminary, single data point):

- Backend mechanical edits faster than frontend migrations (per CP1 actuals). Single-line middleware swap is ~5 LOC vs frontend's ~15-30 LOC per migration. Per-handler cost ~5 min vs Track 6's 2.8-7.5 min/site.

- Per-route adjudication overhead higher than expected (each route needs Tier 1-5 classification check). Forecasting bias should account for surface-time disposition adjudication separate from execution-time mechanical edits.

- Conservative bias confirmed at first Step 3 data point: forecast ~105-130 min Option A, actual ~75 min = 1.4-1.7x. Track 6 trajectory (CP12 ~2.0x, CP13 ~1.7x, CP14 ~1.7x, CP15 ~1.0x) shows similar conservative bias trajectory; backend may run lower edge.

- Tests anticipated count is FLOOR not ceiling: surface forecast 7, actual 15 (defensive scaffolding emerged in execution). Carry-forward discipline locked v2.24.

Step 3 forecast revision (post-CP1): total estimate stays at ~20-22 sessions across 11 CPs. Lazy-noop fallback removal expansion (~40 files across CP2-CP10) absorbed by CP1's bias-under-forecast (~30 min saved per CP × 10 CPs = ~5 hours buffer). Per-CP overhead remains bounded at 1-2 sessions per domain CP.

### §5.11 — Step 3 architectural findings filed for v2.24 §9.12

CP1 surfaced 5 architectural findings filed for v2.24 §9.12 + §9.11:

- Finding 1: press.js scope correction (v2.23 §5.5 amendment). Empirical surface-time inspection caught planning-phase miscount. Surface-before-execute discipline locked.

- Finding 2: Module-load safety test pattern (NEW v2.24 §9.11 lock). Step 3 testing primitive. See §5.9.

- Finding 3: Lazy-noop fallback pattern endemic (~40 files; NEW v2.24 §9.11 universal discipline). Major Path E expansion. See §5.8.

- Finding 4: F-AUTH-2 boot-fail was already silently mitigated by placeholder env-var fallback ('us-east-1_XXXXXXXXX' / 'xxxxxxxxxxxxxxxxxxxxxxxxxx'). CP1 fix removes silent-mask AND moves to lazy path. Either failure mode (regex tightens OR env var missing) now produces structured runtime error — no more silent module-load mitigation.

- Finding 5: Press.js partial-migration first Step 3 instance. Six-data-point pattern across Track 6 + Step 3 phase boundary (CP13 + CP14 + CP15 × 3 + CP1). v2.24 §9.11 partial-migration extension graduates to cross-phase pattern.

CP10 surface report inheritance: when CP10 picks up press.js POSTs (lines 361, 531, 607, 696), surface report MUST explicitly enumerate them as inherited scope from CP1 partial-migration. Tier 1 disposition + aiRateLimiter on AI POSTs (lines 607, 696) per worldEvents reference model. Cross-CP inheritance handling becomes Step 3 surface-report discipline.

### §5.12 — Step 3 CP2 architectural findings (LOCKED v2.25, COMPLETE — Episodes cluster sweep)

CP2 completed at commit d73599f8 (single squashed commit, 27 work-product WIPs collapsed at file boundaries; single session, ~90 min actual vs 4-6 hour forecast — ~3-4x conservative bias confirmed for largest-CP backend cadence). Largest single Step 3 CP by file count and handler count: 22 files / 227 handlers / 91 new tests / 0 regressions. WP1 lazy-noop removal at 4 files (scriptParse, todoListRoutes, onboarding, lala-scene-detection per v2.24 §5.8 universal discipline); WP2 Tier 1 sweep at 22 files (222 handlers promoted to requireAuth); WP3 Tier 2 admin carve-outs (5 handlers per D1 + D2 locks); WP4 structural test file (91 tests passing in episodes-cluster-tier-promotion.test.js — 4th instance of FLOOR-not-ceiling pattern). Strict execution sequence WP1 → WP2 → WP3 → WP4 followed. Backend test suite: 1417 → 1508 passing (+91 tests, +1 suite, 0 regressions, 0 failed). Backed up at d73599f8 on claude/f-auth-1-backup.

Six adjudication decisions executed cleanly:

- D1 wardrobeApproval GET /approval-status: Tier 2 (requireAuth + authorize(['ADMIN'])) consistent with file's 3 other admin handlers. 4 admin handlers total at file.

- D2 uiOverlayRoutes GET /:showId/debug: Tier 2 (requireAuth + authorize(['ADMIN'])) per queue-monitor admin-tooling precedent.

- D3 episodeOrchestrationRoute POST /generate-episode-orchestration: Tier 1 + aiRateLimiter (creator-facing AI-cost mutation; joins worldEvents + episodeBriefRoutes + episodes.js as aiRateLimiter consumers).

- D4 shows.js sweep posture: Full Tier 1 sweep (all 18 no-auth handlers promoted to requireAuth). No partial-migration split — uniform tier. shows.js had cover-image multer ordering corrected (auth before multer per Express middleware best practice).

- D5 episodes.js commented-out auth resolution: lines 400 + 473 uncommented + Tier 1 promotion; lines 313-317 (PUT /:id) + 372-376 (DELETE /:id) promoted from optionalAuth to requireAuth; obsolete 6-line comment block at lines 307-312 removed. F-AUTH-4 obsolescence inversion finding (see §5.15 below). Sentinel grep: 0 hits for // ✅ COMMENTED OUT FOR TESTING markers.

- D6 phonePlaythroughRoutes: authenticate → requireAuth (unified contract). 4 handlers migrated.

Per-tier handler distribution post-CP2:

- Tier 1 (requireAuth): 222 handlers across 22 files (97.8% of CP2 zone)

- Tier 2 (requireAuth + authorize(['ADMIN'])): 5 handlers (4 wardrobeApproval admin + 1 uiOverlayRoutes debug)

- Tier 1 + aiRateLimiter: 1 NEW (D3 episodeOrchestrationRoute) + 5 preserved (3 episodeBriefRoutes + 2 episodes.js)

- Tier 3 / 4 / 5: 0 (Episodes cluster is creator-owned; no public/admin-mount/env-gated handlers)

All 4 verification greps pass: (1) degradeOnInfraFailure consumer count = 5 in routes + 2 in middleware/auth.js docstrings = 7 total (UNCHANGED from CP1 close — Episodes cluster has 0 Tier 3 handlers); (2) requireAuth consumer count 6 → 259 (matches CP2 promotion scope); (3) lazy-noop fallback in CP2 zone = 0 (was 4); (4) authenticateToken active hits in CP2 zone = 0 (was 19; remaining hits in non-CP2 files defer to CP3-CP10).

- Mount-collision verification (NEW for CP2): 11 routers at /api/v1/episodes enumerated with mount order from app.js; no exact-path collisions across sibling routers; cross-mount routers (gameShows.js + scriptParse.js mounted at 2 prefixes simultaneously) tracked. v2.24 §5.5 Anomaly 8 wording "9 routers" superseded by empirical surface-time evidence.

- F-AUTH-5 4-site resolution (CP2 zone): cursorPathController:22, iconCueController:22, musicCueController:20, productionPackageController:22 — all 4 sites resolved naturally as F-AUTH-1 byproducts (req.user non-null after Tier 1 promotion). The ?.sub fallback chains remain as defense-in-depth no-ops post-CP2 (will never fire because requireAuth at the route guarantees req.user existence).

- No HTTP method mismatches surfaced. CP2 didn't change any methods (Step 3 backend method corrections deferred to CP11). Step 3 zero-method-mismatch streak: 2 consecutive CPs (CP1 + CP2).

### §5.13 — Mount-collision discipline (NEW v2.25 §9.11 lock — Step 3 universal pattern, propagates to CP6/CP8/CP10)

CP2 surface-time empirical inspection caught the v2.24 §5.5 Anomaly 8 miscount: 11 routers share /api/v1/episodes prefix, NOT 9. The 11: episodeRoutes (anchor), timelineDataRoutes, wardrobeApprovalRoutes, scriptGeneratorRoutes (out-of-scope — CP9), lalaScriptRoutes, scriptParseRoutes (cross-mount), gameShowRoutes (cross-mount), iconCueRoutes, cursorPathRoutes, musicCueRoutes, productionPackageRoutes. Mount-collision is structurally inherent in Express's app.use() pattern when multiple routers share a path prefix; sibling routers must claim distinct path segments to avoid silent shadowing.

Mount-collision discipline (LOCKED v2.25 §9.11). CP6/CP8/CP10 surface reports MUST enumerate all routers sharing a mount prefix before any sweep edits. Per-router enumeration includes: mount line in app.js, mount path, router file, handler count, middleware class summary, path-segment claim list. Path-segment claim verification: every sibling router's path patterns must be distinct from siblings; if path-pattern overlap exists, app.use order disambiguates and silent-shadowing risk is documented in surface report.

Future Step 3 mount-collision zones (per v2.23 §5.4 + v2.25 §5.13 lock):

- CP6 (Character cluster): /api/v1/character-registry has multiple routers (characterRegistry.js + characterSparkRoute.js + others); /api/v1/characters / /api/v1/relationships clusters require enumeration

- CP8 (Social-feeds cluster): /api/v1/social-profiles has multiple routers (socialProfileRoutes.js + socialProfileBulkRoutes.js + mirrorFieldRoutes.js + undergroundRoutes.js); /api/v1/calendar + /api/v1/feed-* mounts require enumeration

- CP10 (Admin/internal cluster): /api/v1/admin + /api/v1/auth + /admin/queues mounts have potential cross-mount complexity; /api/v1/seed env-gated mount per v2.23 Item 7

CP3-CP5 + CP9 generally have simpler mount topology (1-2 routers per prefix); per-CP surface reports verify no mount-collision exists or document if surfacing.

### §5.14 — Cross-mount router pattern (NEW v2.25 §9.11 architectural finding)

CP2 surface caught two cross-mount routers — files mounted at multiple prefixes simultaneously:

- gameShows.js mounted at BOTH /api/v1/episodes:954 AND /api/v1/shows:955. Same router instance, two URL surfaces.

- scriptParse.js mounted at BOTH /api/v1/scripts:919 (POST /parse) AND /api/v1/episodes:920 (/:id/parse-script + /:id/apply-scene-plan). Same router instance, two URL surfaces.

Cross-mount router pattern (LOCKED v2.25 §9.11 architectural finding). Files mounted at multiple prefixes simultaneously have Tier promotion that affects ALL URL surfaces, not just the primary mount. Handler-level middleware doesn't know about mount prefix — it applies uniformly to every request reaching the handler regardless of which mount routed the request. Pattern: when sweep modifies router-file handler middleware, the change propagates to every mount of that router file in app.js. Per-CP surface reports MUST enumerate cross-mount routers + flag in commit messages.

Discovery primitive: grep -n "require.*\('./routes/<file>\'\)" src/app.js returns the full mount list for a given route file. Multiple results = cross-mount router.

### §5.15 — F-AUTH-4 obsolescence inversion (NEW v2.25 §9.11 finding — supersedes v2.24 §5.7 paraphrase)

CP2 surface caught a v2.24-era paraphrase error in adjudication. The v2.24 surface report described the episodes.js line 307 obsolete comment as "downgraded to optionalAuth for token-expiry tolerance" with F-AUTH-4 obsolescence rationale. CP2 mid-execution corrected this: the actual 6-line comment block at lines 307-312 was a "consistency-with-existing-write-paths" argument, NOT a token-expiry argument. Verbatim:

"Uses optionalAuth to match the rest of the write endpoints in this codebase (world events, generate-episode, scene-sets, etc.). The previous strict authenticateToken caused a hard redirect to /login every time a creator's token expired even though every other write path tolerates a missing token. The controller already handles req.user?.id with optional chaining and an 'unknown' fallback."

F-AUTH-4 obsolescence inversion: F-AUTH-1 itself inverts the consistency baseline. After CP2-CP10 close, every write path requires auth (Tier 1+). The "every other write path tolerates a missing token" baseline ceases to exist — the comment becomes obsolete by virtue of the fix landing, not because of F-AUTH-4 interceptor handling. Comment removal at CP2 is correct disposition; rationale is consistency-baseline-inversion, not interceptor-supersedes-tolerance.

Discipline lesson (LOCKED v2.25 §9.11). When a surface report quotes commentary that drives architectural decisions, request literal text not paraphrase. Adjudication on rationale must reference verbatim comment content, not summary descriptions.

CP3-CP10 surface reports include multi-line F-AUTH-4 obsolescence grep variant (locked single-line grep at v2.24 §5.7 missed the 6-line block at episodes.js:307-312):

grep -nP -B0 -A8 "tolerat|expir|missing token|weakened|TESTING" src/routes/

catches multi-line comment blocks within ~8-line context. Surface report at each CP grep + manual review of any multi-line hits.

### §5.16 — F-AUTH-5 ?.id field-name expansion (NEW v2.25 §9.11 finding — Audit Handoff v8 §4.1 amendment)

Audit Handoff v8 §4.1 catalogued F-AUTH-5 as "6 sites" using req.user?.sub silent-null fallback pattern. CP2 surface verified 4 of those 6 in CP2-zone controllers (cursorPathController:22, iconCueController:22, musicCueController:20, productionPackageController:22). Mid-CP2 finding: a separate silent-null pattern uses req.user?.id || '<fallback>' — same mechanism, different field name. episodeController.js alone has 16 sites of this pattern: lines 349 (createEpisode → 'anonymous' fallback), 571 (updateEpisode → 'unknown'), 654 (deleteEpisode → 'unknown'), 1230 (addCharacter or similar → 'system'), plus 12 bare ?.id reads in logger calls.

F-AUTH-5 catalog amendment (LOCKED v2.25 §9.11). The Audit Handoff v8 §4.1 6-site F-AUTH-5 inventory is undercounted by ~16+ in episodeController.js alone; the actual silent-null risk class includes ?.id field-name patterns in equivalent measure to ?.sub patterns. Both field names are silent-null patterns with literal-fallback chains.

CP2 disposition: Tier 1 promotion at the route layer renders both ?.sub and ?.id always-resolved. The || '<fallback>' literals stay as defense-in-depth no-ops post-CP2; they will never fire because requireAuth at the route guarantees req.user existence. CP3-CP10 surface reports MUST grep for both patterns:

grep -rnE "req\.user\?\.(sub|id)\s*\|\|" src/

returns all silent-null + literal-fallback sites across both field names. Per-CP surface report enumerates hits in CP zone files; closure report confirms tier promotion at route layer renders these always-resolved.

### §5.17 — Surface-correction four-data-point validation (NEW v2.25 §9.11 — discipline lock)

Surface-before-execute discipline (locked at v2.24 §5.7) reaches four data points across F-AUTH-1 program. Each instance: empirical surface-time inspection caught what fix-plan revisions and planning phase missed.

- Data point 1 (CP15, v2.21 → v2.22 surface lock): WorldSetupGuide reclassification — provisional "mixed PUBLIC+BUG" inventory v2 §4.2 label superseded by cross-CP evidence; all 8 sites BUG-class.

- Data point 2 (CP1, v2.23 → v2.24 surface lock): press.js scope correction — v2.23 §5.5 + planning §A.7 said "6 handlers all GETs"; surface caught 2 GETs + 4 POSTs.

- Data point 3 (CP2, v2.24 → v2.25 surface lock): file count + handler count + mount-collision count — three corrections at one CP. v2.23 §5.4 said "21 files / ~170 handlers"; surface counted 22 / 227. v2.24 §5.5 Anomaly 8 said "9 routers"; surface counted 11.

- Data point 4 (CP2, v2.24 → v2.25 surface lock): Grep 1 baseline — surface §10 forecast 5; actual 7 (5 routes + 2 middleware/auth.js docstrings). Outcome correct (Episodes cluster has 0 Tier 3 handlers); forecast number was off by 2.

Surface-correction pattern formal lock (LOCKED v2.25 §9.11). Four data points across two phases (Track 6 CP15 + Step 3 CP1/CP2). Empirical surface-time inspection is structurally essential for Step 3 — fix-plan revisions and planning phase consistently miss details that surface-time empirical inspection catches. CP3-CP11 surface reports apply the discipline: per-handler tier classification verified empirically; per-router enumeration verified empirically; baseline forecasts verified before adjudication; comment text quoted verbatim before rationale-locking.

### §5.18 — Step 3 pacing model second data point (UPDATED v2.25, supersedes v2.24 §5.10)

CP1 first data point: 1 session, ~75 min actual vs ~105-130 min forecast = 1.4-1.7x conservative bias (small focused CP — 5 handlers + lazy-init refactor + lazy-noop removal at 2 files).

CP2 second data point: 1 session, ~90 min actual vs 4-6 hour (240-360 min) forecast = ~3-4x conservative bias for largest-CP backend cadence (22 files, 227 handlers, 91 new tests, mount-collision discipline + 5 architectural decisions).

Per-CP cost-per-handler analysis:

- CP1: ~5 handlers in 75 min = ~15 min/handler (high architectural overhead — lazy-init refactor + lazy-noop removal + 4-decision adjudication absorbed disproportionately)

- CP2: 227 handlers in 90 min = ~24 sec/handler (mechanical-edit dominance — single-line middleware swap × 222 + 6 adjudication-driven edits absorbed in margin)

Step 3 pacing characteristics (two data points):

- Conservative bias confirmed at both data points; backend cadence consistently bias-under-forecast (CP1: 1.4-1.7x; CP2: ~3-4x).

- Per-handler cost diverges by orders of magnitude based on CP shape: small architectural CPs (CP1) at minutes-per-handler; large mechanical CPs (CP2) at seconds-per-handler.

- Total Step 3 estimate stays at ~20-22 sessions across 11 CPs. CP1 + CP2 = 2 sessions actual = ~10% of estimate; ~9 CPs remaining at ~18-20 sessions estimate (post-CP2 buffer ~5+ hours from bias-under-forecast).

- WIP-and-resume protocol available but unused at CP1 + CP2 (single-session execution at both). Available for CP3-CP10 if mid-flow cost overrun signals.

### §5.19 — Tests-FLOOR-not-ceiling four-data-point validation (UPDATED v2.25, supersedes v2.24 §9.11)

v2.24 §9.11 locked the "tests anticipated count is FLOOR not ceiling" pattern at three data points (CP12 + CP13 + CP14). CP1 + CP2 add two more, graduating the pattern to four+ data points across phase boundaries:

- Track 6 CP12: forecast not specifically tracked; Track 6 CP13/CP14 surface forecast vs actual ratio established the FLOOR pattern.

- Step 3 CP1: surface forecast ~7 new tests; actual 15 (2.1x).

- Step 3 CP2: surface forecast 30-50 new tests; actual 91 (1.8-3.0x).

Pattern formal lock (LOCKED v2.25 §9.11): Surface-time test count forecasts are FLOOR estimates, not ceiling estimates. Defensive scaffolding emerges during execution as edge cases surface and per-handler structural assertions accumulate. Per-CP forecast inflation factor: ~1.8-3.0x for backend route-health test files.

CP3-CP11 surface reports forecast tests with explicit "FLOOR" label; closure reports record actual vs forecast for ongoing pattern validation.

### §5.20 — Step 3 CP3 architectural findings (LOCKED v2.26, COMPLETE — World cluster sweep)

CP3 completed at commit 61f8a658 (single squashed commit, 5 file-boundary WIPs collapsed; single session, ~75 min actual vs 1-session forecast — on-forecast for mixed-disposition CP cadence). Smaller than CP2 by file count (4 vs 22) but architecturally distinct: 4 files / 120 handlers / 42 new tests / 0 regressions. First mixed Tier 1+3+4 within single file in F-AUTH-1 program (worldStudio.js). WP1 lazy-noop removal at 3 files (world.js, worldEvents.js with unique double-fallback covering BOTH optionalAuth + requireAuth, worldStudio.js); WP2 Tier 1 promotion sweep at 67 handlers (4 world.js + 59 worldEvents.js + 2 worldEvents partial-AI promoted + 2 worldTemperatureRoutes); WP3 worldStudio.js mixed Tier 1+3+4 split (1 Tier 3 line 2483 + 18 Tier 4 GETs + 34 Tier 1 mutations); WP4 structural test file (42 tests passing — first BELOW-FLOOR data point at 0.35x; methodology divergence per §5.26). Strict execution sequence WP1 → WP2 → WP3 → WP4 followed. Backend test suite: 1508 → 1550 passing (+42 tests, +1 suite, 0 regressions, 0 failed). Backed up at 61f8a658 on claude/f-auth-1-backup.

Five adjudication decisions executed cleanly:

- D1 WorldStudio mixed disposition (REVISED FROM STRICT MATRIX): 1 Tier 3 (line 2483 generate-ecosystem-preview — req.user consumed for ownership tagging) + 17 Tier 4 GETs (read-only published catalog) + 34 mutation handlers Tier 1 (22 POST + 6 PUT + 6 DELETE; mutations require auth regardless of req.user-consumption matrix). Read vs write disposition discipline established — see §5.22.

- D2 PUBLIC comment text: Group-level rationale per surface §4 categorization (e.g., "World character catalog; published-only data; no creator attribution"). Per Item 15 lock: brief rationale required on every PUBLIC marking; group rationale satisfies. 19 PUBLIC comments total in worldStudio.js post-CP3.

- D3 worldTemperatureRoutes Tier 1 default: Both handlers (lines 15 GET + 33 POST) promoted to requireAuth. No "public data" justification surfaced; default applies.

- D4 worldEvents partial-aiRateLimiter promotion: Lines 1701 + 1903 (pre-edit; post-edit 1687 + 1889) promoted from optionalAuth + aiRateLimiter to requireAuth + aiRateLimiter. Uniform AI cost gating across all 4 worldEvents AI POSTs. Reference model state (post-CP3): all 4 AI POSTs at requireAuth + aiRateLimiter — see §5.27.

- D5 Anomaly 5 amendment: worldTemperatureRoutes.js has 2 handlers (NOT 0 as v2.25 §5.5 stated). Custom router var (worldTempRouter) hid handlers from standard ^router.<verb> grep. v2.26 §5.5 records amendment.

Per-tier handler distribution post-CP3:

- Tier 1 (requireAuth): 101 handlers across 4 files (84.2% of CP3 zone; 4 world.js + 59 worldEvents.js + 34 worldStudio.js mutations + 2 worldTemperatureRoutes + 2 worldEvents partial-AI promoted to requireAuth + aiRateLimiter)

- Tier 1 + aiRateLimiter: 4 handlers (2 preserved verbatim at worldEvents.js:748 + 1779 post-edit; 2 promoted at worldEvents.js:1687 + 1889 post-edit per D4)

- Tier 3 (optionalAuth + degradeOnInfraFailure): 1 handler (worldStudio.js:2483 generate-ecosystem-preview per D1)

- Tier 4 (plain optionalAuth + PUBLIC): 18 handlers (all worldStudio.js GETs per D1)

- Tier 2 / Tier 5: 0 handlers (no admin tooling or env-gated mounts in CP3 zone)

All 5 verification greps pass: (1) degradeOnInfraFailure consumer count 7 → 8 (added 1 Tier 3 at worldStudio.js:2483); (2) requireAuth consumer count 259 → 359 (+100, matches CP3 zone Tier 1 promotion + 4 imports); (3) lazy-noop fallback in CP3 zone = 0 (was 3); (4) authenticateToken active hits in CP3 zone = 0 (was 0; planning's "1 hit" confirmed false positive on lazy-noop fallback); (5) NEW PUBLIC comments in CP3 zone = 19 (1 Tier 3 + 18 Tier 4).

- F-AUTH-4 multi-line grep: zero auth-weakening comment blocks in CP3 zone. All hits in surface §8 confirmed false positives at execution (DB schema tolerance, cache TTL "expires", lazy-noop fallback string). No D5-style comment removal needed (unlike CP2 episodes.js:307-312).

- F-AUTH-5 ?.id resolution at CP3 zone: 1 site (worldStudio.js:2624 within Tier 3 handler at line 2483). req.user?.id resolved when token present after Tier 3 factory invocation; req.ip fallback preserved as defense-in-depth (intended Tier 3 contract).

- Cross-mount router check (per v2.25 §5.14): 0 cross-mount routers in CP3 zone. World cluster mount topology simpler than Episodes — 3 routers share /api/v1 with /world/... internal path conventions, but no exact-path collisions; worldTemperatureRoutes uses distinct /api/v1/world-temperature mount. Different shape than CP2 — see §5.13 amendment.

- Mount-collision shape variant (NEW v2.26 §5.13 amendment): CP2 = multiple routers at SAME mount prefix with distinct path-segment claims; CP3 = multiple routers at SHARED ROOT prefix (/api/v1) with internal path-prefix discrimination at the handler level. Same architectural concern (silent-shadowing risk), different shape. v2.25 §5.13 lock applies to both shapes; surface report enumerates the topology variant.

- No HTTP method mismatches surfaced. CP3 didn't change any methods (Step 3 backend method corrections deferred to CP11). Step 3 zero-method-mismatch streak: 3 consecutive CPs (CP1 + CP2 + CP3).

### §5.21 — Mixed Tier 1+3+4 within single file (NEW v2.26 §9.11 architectural primitive)

CP3 establishes the first single-file mixed Tier 1+3+4 disposition in F-AUTH-1 program. worldStudio.js architectural precedent: 53 handlers split across three Tiers within one file:

- 1 Tier 3 (line 2483 POST /world/generate-ecosystem-preview): optionalAuth({ degradeOnInfraFailure: true }) + specific PUBLIC comment with rationale citing audience-growth use case

- 18 Tier 4 (all worldStudio.js GET handlers): plain optionalAuth + group-level PUBLIC comments per categorization (world character catalog, world scene catalog, preview reads, ecosystem reads, etc.)

- 34 Tier 1 (22 POST + 6 PUT + 6 DELETE, excluding line 2483): requireAuth (mutations require auth regardless of req.user-consumption matrix per §5.22 read vs write disposition discipline)

Mixed Tier 1+3+4 architectural primitive (LOCKED v2.26 §9.11). When a file has mixed disposition spanning Tier 1 + Tier 3 + Tier 4, per-handler adjudication required at surface; PUBLIC comments with group-level rationale (per Item 15 lock); commit message enumerates per-handler tier assignment. The pattern combines: (1) per-route req.user consumption analysis for read disposition (Tier 3 vs Tier 4 split); (2) write disposition default to Tier 1 (per §5.22); (3) group-level PUBLIC comments for Tier 4 cohort cohesion.

Future Step 3 CPs requiring this primitive: CP4-CP11 surface reports flag any file with mixed Tier 1/3/4 disposition; the discipline is established at CP3 and carries forward. Most Step 3 files have uniform tier disposition (CP1 + CP2 dominantly Tier 1); mixed disposition is the exception when a file mixes published-data reads + creator-data writes within the same router (worldStudio.js precedent).

### §5.22 — Read vs write disposition discipline (NEW v2.26 §9.11 lock + §5.2 amendment)

CP3 D1 adjudication established a discipline that the v2.25 §5.2 disposition tier matrix didn't make explicit: the req.user-consumption matrix (Tier 3 vs Tier 4 split) applies to READ disposition only. WRITE disposition defaults to Tier 1 (requireAuth) unless the domain owner explicitly adjudicates a different disposition (e.g., Tier 2 admin-tooling write, Tier 3 + degradeOnInfraFailure write).

Rationale: a handler that mutates state but does not consume req.user is a handler with a missing creator-attribution implementation, NOT a handler that is intentionally public-mutation. Strict req.user-consumption matrix application to mutations would create security regressions: cascading DELETE, no-ownership-check DELETE, S3 writes without rate limit, state mutations without creator attribution become un-authenticated by design — none of which match domain owner intent.

CP3 D1 reclassified 34 worldStudio.js mutation handlers (22 POST + 6 PUT + 6 DELETE, excluding line 2483 Tier 3) from Tier 4 (strict matrix) to Tier 1 (read vs write discipline). Surface report had marked all 53 worldStudio handlers as Tier 4 candidates per strict req.user-consumption matrix; D1 lock corrected the disposition framework.

Read vs write disposition discipline (LOCKED v2.26 §9.11 + §5.2 amendment). Future CPs apply the discipline at surface: per-route classification for mutations defaults Tier 1 unless explicit domain-owner adjudication; per-route classification for reads applies the req.user-consumption matrix.

### §5.23 — Track 7 in-cycle coordination requirement (NEW v2.26 §9.11 lock)

Track 7 was locked Option C (hybrid — separate execution from Step 3 backend) at v2.0. CP3 reveals an edge case requiring tighter coordination: when backend Tier 1 disposition lands AND frontend correspondent uses raw fetch() (no auth headers), the frontend correspondent will start 401-ing at backend backup-push.

CP3 + WorldStudio.jsx is the first such instance. CP3 backend sweep promoted 34 worldStudio mutation handlers to Tier 1 (requireAuth). WorldStudio.jsx contains 29 raw fetch() calls; ~11 are mutation calls that will start 401-ing post-CP3 backup push. The backend has changed the contract; frontend hasn't caught up yet.

Track 7 in-cycle coordination requirement (LOCKED v2.26 §9.11). When backend disposition shift is Tier 1+ (requireAuth) AND frontend correspondent uses raw fetch (no auth headers), Track 7 mini-CP for the frontend correspondent must follow IMMEDIATELY after the backend backup-push (separate commit, same backup-push cycle). For backend Tier 3/Tier 4 dispositions, no Track 7 coordination required (frontend raw fetch continues to work because backend tolerates anonymous).

CP3 disposition: file Track 7 mini-CP for WorldStudio.jsx ~11 mutation sites as IMMEDIATE follow-up after CP3 backup-push. Scope: ~11 raw fetch() → apiClient migration (Bearer token) + corresponding test scaffolding. Separate commit on feature/f-auth-1; backup-push to claude/f-auth-1-backup overwrites CP3 squash. v2.27 captures Track 7 mini-CP closure.

Future CPs apply the coordination requirement at surface: per-CP frontend-correspondent audit (raw fetch vs apiClient); per-CP Track 7 mini-CP scope estimate; backup-push cycle plan (CP backend + Track 7 mini-CP same cycle when Tier 1+ + raw fetch present).

### §5.24 — Surface-correction eight-data-point validation (UPDATED v2.26 §5.17)

v2.25 §5.17 locked the surface-correction pattern at four data points (CP15 + CP1 + CP2 × 3). CP3 contributes four more corrections, graduating the pattern to eight cumulative data points across CP15 + CP1 + CP2 + CP3:

- Data points 1-4 (per v2.25 §5.17): CP15 WorldSetupGuide reclassification + CP1 press.js scope + CP2 file count + CP2 handler count + CP2 mount-collision + CP2 grep baseline = 5 corrections (correction count amended; v2.25 §5.17 had 4 listed, 5 actual when grep baseline counted separately)

- Data point 5 (CP3): handler count correction — planning forecast ~85; surface counted 120 (+41% over forecast)

- Data point 6 (CP3): worldEvents AI POST count correction — planning said 5 already on requireAuth; surface revealed 4 total (2 already correct + 2 partial needing promotion). v2.25 §A.7 wording superseded

- Data point 7 (CP3): authenticateToken in CP3 zone — planning said 1 hit in worldEvents.js; surface confirmed at execution that hit was lazy-noop fallback false positive; actual = 0

- Data point 8 (CP3): worldTemperatureRoutes anomaly — v2.25 §5.5 Anomaly 5 said 0 handlers; surface counted 2 (custom router var hid handlers from standard grep). Anomaly 5 amendment locked

Surface-correction pattern formal lock graduates (LOCKED v2.26 §5.17). Eight cumulative data points across two phases (Track 6 CP15 + Step 3 CP1/CP2/CP3). Empirical surface-time inspection consistently catches what fix-plan revisions and planning phase miss. CP3 alone contributed 4 corrections — highest single-CP correction count to date. CP4-CP11 surface reports apply the discipline rigorously: empirical handler enumeration (don't trust planning forecast); empirical middleware classification (verify lazy-noop false positives); empirical mount-collision counts (don't trust v2.x §5.5 anomaly numbers without re-verification); custom-router-variable detection (use file-content-search, not pattern-restricted grep).

### §5.25 — Step 3 pacing model third data point (UPDATED v2.26, supersedes v2.25 §5.18)

CP1 first data point: 1 session, ~75 min actual vs ~105-130 min forecast = 1.4-1.7x conservative bias.

CP2 second data point: 1 session, ~90 min actual vs 4-6 hour forecast = ~3-4x conservative bias for largest-CP backend cadence.

CP3 third data point: 1 session, ~75 min actual vs 1-session forecast (~120 min equivalent) = on-forecast for mixed-disposition CP cadence.

Per-CP cost-per-handler analysis (three data points):

- CP1: ~5 handlers in 75 min = ~15 min/handler (high architectural overhead — lazy-init refactor + lazy-noop removal + 4-decision adjudication absorbed disproportionately)

- CP2: 227 handlers in 90 min = ~24 sec/handler (mechanical-edit dominance — single-line middleware swap × 222 + 6 adjudication-driven edits absorbed in margin)

- CP3: 120 handlers in 75 min = ~38 sec/handler (mixed-disposition adjudication overhead — 5 D-decisions + per-handler tier classification at worldStudio.js + group PUBLIC comments + lazy-noop removal at 3 files)

Step 3 pacing characteristics (three data points):

- Conservative bias holds at all three data points; backend cadence consistently bias-under-forecast or on-forecast (CP1: 1.4-1.7x; CP2: ~3-4x; CP3: on-forecast).

- Per-handler cost diverges by CP shape (15 min vs 24 sec vs 38 sec): small architectural CPs at minutes-per-handler; large mechanical CPs at seconds-per-handler; mixed-disposition CPs at ~30-40 sec/handler.

- Total Step 3 estimate stays at ~20-22 sessions across 11 CPs. CP1 + CP2 + CP3 = 3 sessions actual = ~14% of estimate; ~8 CPs remaining at ~17-19 sessions estimate.

- WIP-and-resume protocol available but unused at CP1 + CP2 + CP3 (single-session execution at all three). Available for CP4-CP11 if mid-flow cost overrun signals; mixed-disposition CPs (potential CP6/CP8/CP10 candidates) most likely to need it.

### §5.26 — Tests-FLOOR methodology amendment (UPDATED v2.26 §5.19)

v2.25 §5.19 locked the "tests anticipated count is FLOOR not ceiling" pattern at four data points. CP3 contributes the first BELOW-FLOOR data point in 4 backend-CP cycles — surface forecast 120, actual 42, multiplier 0.35x. Methodology divergence: CP3 test design used aggregate-counter assertions instead of per-handler-implies-1-test. Test COVERAGE preserved (aggregate-count assertions catch deviation in any single handler) but test COUNT 3-5x lower.

Tests-FLOOR methodology amendment (LOCKED v2.26 §5.19). FLOOR pattern applies to per-handler-implies-1-test methodology only. Aggregate-counter methodology is acceptable when test coverage is preserved. CP3 establishes aggregate-counter as a valid alternative; future CPs can choose either methodology based on what makes the tests most maintainable.

Updated forecast inflation factor (post-CP3 four+ data points):

- Per-handler methodology: 1.8-3.0x inflation factor confirmed at CP1 (2.1x) + CP2 (1.8x) + Track 6 CP12-CP15 (1.5x average)

- Aggregate-counter methodology: 0.3-0.4x deflation factor at CP3 (0.35x) — first data point; pattern requires more data points to formally lock

CP4-CP11 surface reports specify chosen methodology + label forecast accordingly (FLOOR for per-handler; AGGREGATE for aggregate-counter). Closure reports record actual vs forecast for ongoing pattern validation across both methodologies.

### §5.27 — WorldEvents reference model status update (NEW v2.26)

worldEvents.js was the v2.23 §5.4 CP3 description's "5 AI POSTs already on requireAuth" reference model. CP3 surface revealed the actual state: 4 AI POSTs total (NOT 5), split 2 already correct + 2 partial needing promotion. CP3 D4 promoted the 2 partials to uniform requireAuth + aiRateLimiter.

WorldEvents reference model state post-CP3 (LOCKED v2.26 §5.27): all 4 AI POSTs uniformly use requireAuth + aiRateLimiter pattern.

- worldEvents.js:748 (post-edit) POST /events/:eventId/generate-script: requireAuth + aiRateLimiter (preserved verbatim — was already correct pre-CP3)

- worldEvents.js:1687 (post-edit) POST /events/:eventId/generate-episode: requireAuth + aiRateLimiter (PROMOTED at CP3 D4)

- worldEvents.js:1779 (post-edit) POST /events/generate-episode-from-many: requireAuth + aiRateLimiter (preserved verbatim — was already correct pre-CP3)

- worldEvents.js:1889 (post-edit) POST /events/:eventId/regenerate-episode: requireAuth + aiRateLimiter (PROMOTED at CP3 D4)

Architectural inconsistency eliminated: anonymous bypass of aiRateLimiter via optionalAuth no longer possible. Reference model now uniform — future Step 3 CPs reference the post-CP3 state of worldEvents.js when making AI cost gating disposition decisions.

Cross-CP correspondences:

- CP1 referenced worldEvents reference model in adjudication of episodeBriefRoutes 4 AI POSTs (already requireAuth + aiRateLimiter — preserved at CP1)

- CP2 referenced worldEvents reference model for D3 adjudication of episodeOrchestrationRoute (Tier 1 + aiRateLimiter; joins worldEvents AI POSTs as aiRateLimiter consumer)

- CP3 closes the inconsistency at the reference model itself: worldEvents 4 AI POSTs uniformly correct

- CP4-CP10 surface reports identify any AI-cost POSTs in CP zone files; apply the worldEvents post-CP3 uniform reference model (requireAuth + aiRateLimiter)

### §5.28 — Track 7 mini-CP architectural findings (LOCKED v2.27, COMPLETE — first Track 7 in-cycle execution)

Track 7 mini-CP completed at commit 3e447814 (single squashed commit, 2 file-boundary WIPs collapsed; single session, ~45 min actual vs 60-100 min forecast — on or under forecast). First Track 7 in-cycle execution since v2.0 Option C lock. CP3 regression window CLOSED — backend 34 mutation handlers in worldStudio.js Tier 1 promoted at CP3; WorldStudio.jsx 15 corresponding mutation sites migrated to apiClient (Bearer token via interceptor) at Track 7 mini-CP. Pattern A canonical migration per Track 6 CP2-CP15 precedent applied uniformly.

WP1 15 site Pattern A migration: 14 canonical mutations + 1 Tier 3 site (M1 line ~745 per D2 lock); WP2 32 new structural assertions extending WorldStudio.test.jsx (existing 3 Track 4 helper tests preserved; 35 tests in file total). Frontend test suite: 813 → 845 passing (+32 tests, 0 regressions, 0 failed). Backed up at 3e447814 on claude/f-auth-1-backup.

Three adjudication decisions executed cleanly:

- D1 (3 path-bug sites at lines 1099, 1118, 1704): SKIPPED + filed PE-9 in §9.12. Pre-existing /api/world/... (no /api/v1/) bug; 404 by default; not part of CP3 regression window. Bug-fix in future polish CP.

- D2 (Tier 3 site M1 at line ~745): MIGRATED to apiClient. Backend Tier 3 at worldStudio.js:2483 consumes req.user?.id for ownership tagging when authed. apiClient sends Bearer token when user has valid token; backend tags ownership properly. Anonymous + Cognito-infra-failure behaviors preserved per Tier 3 contract.

- D3 (4 character-depth sites at lines 238, 255, 266, 278): STAYED RAW FETCH. Out of Track 7 mini-CP scope (different backend cluster — Character cluster, CP6 zone). When CP6 lands, another Track 7 mini-CP may be needed for character-depth frontend correspondences depending on backend disposition decisions there.

All 3 verification greps pass: (1) fetch( count in WorldStudio.jsx 29 → 14 (-15 = migration count; remaining 14 = 7 Tier 4 GET + 4 character-depth + 3 path-bug); (2) apiClient.(post|put|delete)( count 1 → 16 (+15 = migration count; baseline 1 from pre-existing Track 4 helper); (3) apiClient import in WorldStudio.jsx 1 → 1 (apiClient was already imported via Track 4; no new import needed — surface §6 amendment caught this).

- Sentinel sub-grep: 0 /world/* mutation fetches remaining (zero `fetch(`${API}/world/...`, { method: 'POST|PUT|DELETE' })` patterns in WorldStudio.jsx).

- Pattern A applicability per-site: all 15 migrated sites used canonical Pattern A. No Pattern G streaming exceptions surfaced (consistent with v2.22 Pattern G locked-6-sites list excluding WorldStudio.jsx). Pattern A variations handled: no-body POSTs (single-arg apiClient.post(url)); fire-and-forget batch (.catch(() => {}) preserved); status-code reporting (e.response?.status used in error message).

- Frontend test count delta forecast vs actual: 15-30 forecast (per-site methodology); 32 actual = 1.07x at-forecast. First per-site methodology data point — see §5.26 amendment.

- No new Path E candidates surfaced during execution. PE-9 already filed at surface adjudication.

### §5.29 — Tier 3 → apiClient frontend migration discipline (NEW v2.27 §9.11 lock + extension of v2.26 §5.23)

v2.26 §5.23 locked Track 7 in-cycle coordination requirement: "when backend Tier 1 disposition lands AND frontend correspondent uses raw fetch, Track 7 mini-CP must follow IMMEDIATELY after the backend backup-push." Track 7 mini-CP D2 adjudication revealed an extension: Tier 3 backend disposition also requires frontend apiClient migration when frontend correspondent uses raw fetch.

Rationale: Tier 3 backend handlers consume req.user?.id when authed (per Tier 3 contract: optionalAuth + degradeOnInfraFailure). If frontend stays raw fetch (no Bearer token), backend always treats as anonymous regardless of whether user has a valid token. Ownership tagging breaks; F-AUTH-5 silent-null fallback chains kick in. Migrating frontend to apiClient ensures Bearer token reaches backend when authed; backend Tier 3 contract still gracefully handles anonymous (no token in localStorage → apiClient sends without auth header → backend req.user undefined → ownerId fallback to req.ip per defense-in-depth).

Tier 3 → apiClient frontend migration discipline (LOCKED v2.27 §9.11). When backend disposition shift is Tier 1 OR Tier 3 AND frontend correspondent uses raw fetch, Track 7 mini-CP for the frontend correspondent must follow IMMEDIATELY after the backend backup-push (separate commit, same backup-push cycle). Tier 4 alone does NOT trigger Track 7 mini-CP (frontend stays raw fetch — Pattern E equivalent; backend tolerates anonymous AND does not consume req.user).

Tier-trigger matrix (post-v2.27 lock):

- Backend Tier 1 (requireAuth) + frontend raw fetch → Track 7 mini-CP REQUIRED (frontend would 401 without Bearer token)

- Backend Tier 2 (requireAuth + authorize) + frontend raw fetch → Track 7 mini-CP REQUIRED (same as Tier 1 from frontend perspective)

- Backend Tier 3 (optionalAuth + degradeOnInfraFailure) + frontend raw fetch → Track 7 mini-CP REQUIRED for proper ownership tagging (NEW v2.27 lock)

- Backend Tier 4 (plain optionalAuth + PUBLIC) + frontend raw fetch → Track 7 mini-CP NOT REQUIRED (Pattern E equivalent; backend tolerates anonymous AND does not consume req.user)

- Backend Tier 5 (env-gated mount) + frontend raw fetch → context-dependent (likely no production frontend correspondence)

Future CPs apply the matrix at surface: per-CP frontend-correspondent audit categorizes raw fetch sites by backend tier; Track 7 mini-CP scope = sum of Tier 1 + Tier 2 + Tier 3 frontend correspondences in that CP zone.

### §5.30 — Per-site structural assertion methodology (NEW v2.27 §5.26 amendment — third methodology variant)

v2.26 §5.26 locked tests-FLOOR methodology amendment with two variants: per-handler-implies-1-test (FLOOR pattern, 1.8-3.0x inflation) and aggregate-counter (deflation pattern, 0.3-0.4x). Track 7 mini-CP introduces a third methodology variant: per-site structural assertion. WP2 produced 32 tests for 15 mutation sites (forecast 15-30) = 1.07x at-forecast accuracy.

Per-site structural assertion methodology (LOCKED v2.27 §5.26 amendment). Source-text structural assertions verify migration via grep-style checks against source file content (e.g., "assert apiClient.post('/api/v1/world/scenes/generate', ...) appears in source"). Appropriate when migration is in-place (handlers stay component-internal; not refactored to Pattern D module-scope helpers). Test methodology variant choice depends on file scope + future test maintenance burden.

Methodology decision tree (post-v2.27):

- Pattern D refactor + behavioral tests: when migration is large enough to justify refactoring component-internal logic into module-scope helpers (Track 6 CP13 precedent — file-level effort)

- In-place migration + structural assertions (per-site): when migration is small/contained and refactor cost exceeds benefit (Track 7 mini-CP first instance; ~1.0x at-forecast accuracy)

- Per-handler-implies-1-test (FLOOR): when migration is per-handler and assertions naturally distribute across handler boundaries (CP1 + CP2 precedents; 1.8-3.0x inflation)

- Aggregate-counter: when migration is uniform and assertions aggregate naturally (CP3 precedent; 0.3-0.4x deflation; reduces test count without losing coverage)

Updated forecast accuracy table:

- Per-handler methodology: 1.8-3.0x inflation factor confirmed at CP1 (2.1x) + CP2 (1.8x) + Track 6 CP12-CP15 (1.5x average)

- Aggregate-counter methodology: 0.3-0.4x deflation factor at CP3 (0.35x) — single data point

- Per-site structural assertion methodology: ~1.0x at-forecast at Track 7 mini-CP (1.07x) — single data point

CP4-CP11 + future Track 7 mini-CPs choose methodology based on migration shape; closure reports record actual vs forecast for ongoing pattern validation across all three methodologies.

### §5.31 — Frontend pacing first data point (NEW v2.27 amendment to §5.25 Step 3 pacing model)

Step 3 pacing model in v2.26 §5.25 captured three backend data points (CP1 + CP2 + CP3). Track 7 mini-CP introduces the first frontend phase data point to the cadence-tracking framework.

Track 7 mini-CP: 1 session, ~45 min actual vs 60-100 min forecast = on or under forecast. 15 sites in 45 min = ~3 min/site for uniform Pattern A migration.

Cost-per-unit comparison across Step 3 phases (four data points):

- CP1 (backend, architectural): ~5 handlers in 75 min = ~15 min/handler (lazy-init refactor + lazy-noop removal + 4-decision adjudication absorbed disproportionately)

- CP2 (backend, mechanical): 227 handlers in 90 min = ~24 sec/handler (single-line middleware swap dominance)

- CP3 (backend, mixed-disposition): 120 handlers in 75 min = ~38 sec/handler (per-handler tier classification + group PUBLIC comments + 5 D-decisions)

- Track 7 mini-CP (frontend, uniform Pattern A): 15 sites in 45 min = ~3 min/site (apiClient.method() swap + literal /api/v1 path migration + r.data response shape)

Frontend cadence characteristic (Track 7 mini-CP first data point):

- Frontend Pattern A migration ~3 min/site is faster than backend mechanical sweep on a per-unit basis (CP2 backend ~24 sec/handler at scale would suggest equivalence, but small-scope frontend bypasses CP2-style sed bulk efficiency).

- Pattern A uniform substitution + apiClient interface stable target = predictable cadence. Future Track 7 mini-CPs (CP6/CP8/CP10 candidates) likely fit similar ~3-5 min/site range for non-Pattern-G sites.

- Test scaffolding overhead absorbed in single-session forecast: WP2 ~20 min for 32 tests at per-site methodology = ~38 sec/test creation, comparable to per-handler test creation cost at backend CPs.

Total Step 3 + Track 7 estimate update: CP1 + CP2 + CP3 = 3 sessions actual + Track 7 mini-CP 1 session = 4 sessions used. ~8 backend CPs remaining (CP4-CP11) + estimated 1-3 Track 7 mini-CPs = ~9-11 sessions remaining at conservative bias. Total Step 3 + Track 7 trajectory: ~13-15 sessions estimate vs original v2.23 §5.4 lock of ~20-22 sessions = ~30-40% under original forecast at this trajectory.

### §5.32 — Track 7 mini-CP first-execution discipline (NEW v2.27 §9.11 lock — template for future Track 7 mini-CPs)

Track 7 mini-CP at WorldStudio.jsx is the first Track 7 in-cycle execution. The discipline established here is the template for any future Track 7 mini-CPs that surface during CP4-CP11 (CP6/CP8/CP10 most likely candidates given Character/Social-feeds/Admin-internal mount complexity).

Track 7 mini-CP first-execution discipline (LOCKED v2.27 §9.11). Per-site Pattern A applicability check at surface; per-site enumeration with backend handler correspondence; tier-trigger matrix applied (Tier 1 OR Tier 3 + raw fetch = migrate; Tier 4 + raw fetch = Pattern E equivalent stay raw fetch); per-site structural assertion methodology for in-place migrations; backup-push cycle in same session as backend CP backup-push; v2.x update captures closure.

Pre-execution checklist for future Track 7 mini-CPs:

- Backend CP closure surfaces frontend regression window scope (per-CP closing report counts raw fetch correspondences in CP zone files)

- Per-site enumeration verifies backend handler correspondence + tier classification at surface

- Tier-trigger matrix categorizes per-site disposition (migrate vs stay raw fetch)

- Path E candidates surfaced incidentally are filed in §9.12 (do NOT fix during mini-CP)

- Out-of-scope sites (different backend cluster) noted but untouched

- Pattern G streaming check (none in Track 7 mini-CP at WorldStudio.jsx; future Track 7 mini-CPs verify)

- apiClient interface verification (local name, available methods, auth header injection mechanism)

- Frontend test baseline capture before WP1 begins

- Verification grep template (3 greps minimum: raw fetch count, apiClient method count, apiClient import presence)

- Single-session forecast with WIP-and-resume protocol available

- Backup-push immediately following Evoni approval (same-turn per §9.13 Rule 2)

Future Track 7 mini-CP candidates (per v2.23 §5.4 + v2.27 §5.29 tier-trigger matrix):

- CP4 Scene cluster: TBD at CP4 surface (potential mixed-tier disposition; surface verifies frontend correspondence)

- CP6 Character cluster: likely candidate (Character cluster mount complexity per v2.25 §5.13; CharacterDepth + WorldStudio.jsx character-depth sites at lines 238/255/266/278 may need migration depending on CP6 backend disposition)

- CP8 Social-feeds cluster: likely candidate (multiple frontend pages — SocialProfile.jsx, SocialFeed.jsx, etc.; multiple raw fetch sites likely)

- CP10 Admin-internal cluster: possible candidate depending on admin-tooling frontend correspondence

### §5.33 — Step 3 CP4 architectural findings (LOCKED v2.28, COMPLETE — Scene cluster, three architectural firsts)

CP4 completed at commit 5c13531e (single squashed commit, 7 file-boundary WIPs collapsed; single session, ~80 min actual vs forecast 100-130 min — on or under forecast). Cleanest CP closure in Step 3 backend phase: three architectural firsts in single CP. 6 files / 126 handlers / 61 new tests / 0 regressions. WP1 NO-OP (zero lazy-noop in zone — first such CP); WP2 Tier 1 promotion sweep at 113 handlers; WP3 AI POST reference model application at 13 handlers (sceneProposeRoute × 1 + sceneSetRoutes × 12 — ADD requireAuth + aiRateLimiter); WP4 aggregate-counter test methodology (61 tests passing — 1.07x at-forecast). Backend test suite: 1550 → 1611 passing (+61 tests, +1 suite, 0 regressions, 0 failed). Frontend unchanged at 845 (CP4 backend-only sweep; NO Track 7 coordination needed). Backed up at 5c13531e on claude/f-auth-1-backup.

Three architectural firsts at single CP:

- First WP1 NO-OP CP: zero lazy-noop in CP4 zone (planning §A.7 forecast 2-4 files); v2.24 §5.8 universal discipline holds at zero-removal state. WP1 phase skipped entirely; direct WP2 → WP3 → WP4 sequence.

- First NO-Track-7-coordination CP: frontend ideal state — Scene cluster API calls flow through 3 service modules (sceneService.js × 46 + sceneLibraryService.js × 5 + sceneLinksService.js × 4 = 55 apiClient calls); 0 raw fetch in frontend pages/components. v2.27 §5.29 tier-trigger matrix: Tier 1 + service-module-apiClient does NOT trigger Track 7 mini-CP. CP4 closes cleanly with NO regression window opened.

- First pure Tier 1 sweep CP in Step 3: all 126 handlers default Tier 1 per v2.26 §5.22 read vs write disposition discipline. No Tier 2/3/4/5 candidates surface. Mixed Tier 1+3+4 within-single-file primitive (v2.26 §5.21) does NOT apply at CP4. Pure Tier 1 + AI POST reference model overlay = cleanest backend CP shape.

Five adjudication decisions executed cleanly:

- D1 (13 AI POSTs ADD reference model): All 13 promoted to requireAuth + aiRateLimiter uniformly per worldEvents reference model (v2.26 §5.27). aiRateLimiter import added to sceneProposeRoute.js + sceneSetRoutes.js. ADD shape (had neither requireAuth nor aiRateLimiter pre-CP4) vs CP3 D4 PROMOTE shape (had aiRateLimiter; needed requireAuth). Both shapes apply same reference model — see §5.27 amendment.

- D2 (sceneLinks.js mount-path anomaly): Filed PE-10 in §9.12. Mount path /api/scene-links (no /api/v1/ prefix) preserved at CP4; future polish CP addresses with frontend coordination. Tier 1 promotion at sceneLinks.js applies regardless of mount path.

- D3 (sceneTemplates.js Tier 1 default): 5 bare handlers promoted to Tier 1 per §5.22 read vs write disposition. No public catalog or personalization shape surfaced; default applies.

- D4 (Test methodology aggregate-counter): 61 tests at aggregate-counter methodology per v2.27 §5.30. Forecast 50-60 (FLOOR); actual 61 (1.07x at-forecast). Second aggregate-counter data point (CP3 first at 0.35x deflation; CP4 at 1.07x at-forecast — accuracy varies by aggregation density; see §5.30 amendment).

- D5 (scenes.js dev/diagnostic endpoints): /test-direct/:id, /ultra-test, /db-test promoted to Tier 1 default. PE-11 candidate filed: Tier 5 env-gated mount candidates if execution-time analysis confirms dev-only (no production callers); future polish CP adjudication.

Per-tier handler distribution post-CP4:

- Tier 1 (requireAuth): 113 handlers across 6 files

- Tier 1 + aiRateLimiter (NEW promotions): 13 handlers (1 sceneProposeRoute + 12 sceneSetRoutes per D1)

- Tier 2 / Tier 3 / Tier 4 / Tier 5: 0 handlers (Scene cluster is creator-owned production tooling without admin subset, public catalog, or env-gated mounts)

All 5 verification greps pass: (1) degradeOnInfraFailure consumer count 8 → 8 (UNCHANGED — no Tier 3 in CP4); (2) requireAuth consumer count 359 → 491 (+132 = 6 imports + 126 handlers); (3) lazy-noop fallback in CP4 zone = 0 (UNCHANGED — WP1 no-op); (4) authenticateToken active hits in CP4 zone = 0 (was 3 in sceneLibrary.js — eliminated); (5) NEW aiRateLimiter consumers in CP4 zone = +15 (2 imports + 13 handlers; matches D1 lock).

- F-AUTH-4 multi-line grep zero hits in CP4 zone (matches CP3 pattern; no auth-weakening comment blocks).

- F-AUTH-5 expansion: 10 sites in scene controllers (sceneController.js × 2 + sceneStudioController.js × 8) with ?.id || 'system' / ?.id || null fallback chains. Tier 1 promotion at routes renders all 10 fallback chains as defense-in-depth no-ops. v2.26 §5.16 ?.id field-name pattern continues to surface.

- Cross-mount router observation: sceneProposeRoute at /api/v1/memories shares mount with 6 other routers (memoriesRoutes, scriptFromBook, storyEvaluationRoutes, characterGrowthRoute, episodeOrchestrationRoute [CP2-DONE], eventGeneratorRoute). Sibling path-segment claims distinct from sceneProposeRoute paths (/propose-scene, /scene-proposals/...). No collision; Tier 1 promotion affects only sceneProposeRoute handlers.

- Surface execution-time discovery: per-handler-block analysis caught 2 additional bare handlers in sceneSetRoutes.js that surface report's 8-line-window grep had not isolated. Methodology refinement filed as PE-12 — see §5.30 amendment.

- No HTTP method mismatches surfaced. Step 3 zero-method-mismatch streak: 4 consecutive CPs (CP1 + CP2 + CP3 + CP4).

### §5.34 — Mount-collision third topology variant: distinct-mounts (NEW v2.28 §5.13 amendment)

CP4 surface enumeration revealed a third mount-collision topology variant. v2.25 §5.13 + v2.26 §5.13 amendment locked two variants (CP2-shape + CP3-shape); CP4 contributes the third:

- CP2-shape: multiple routers at SAME mount prefix (e.g. /api/v1/episodes) with distinct path-segment claims. 11 routers at CP2; cross-mount risk + path-collision risk both architectural concerns.

- CP3-shape: multiple routers at SHARED ROOT prefix (/api/v1) with internal /scenes/... or /world/... path-prefix discrimination at handler level. 3 routers at CP3 (worldRoutes + worldEventRoutes + worldStudioRoutes); same architectural concerns, different shape.

- Distinct-mounts variant (NEW v2.28): each Scene cluster router has unique mount path (/api/v1/scenes, /api/v1/scene-templates, /api/v1/scene-library, /api/v1/scene-sets, /api/scene-links, /api/v1/memories cross-mount). No same-prefix collision; cross-mount router check applies only when a router shares mount with siblings (CP4: sceneProposeRoute at /api/v1/memories with 6 siblings — verified distinct path-segment claims; no collision).

Mount-collision discipline (LOCKED v2.28 §5.13 amendment). CP5-CP11 surface reports identify mount-collision topology variant per CP zone: CP2-shape (same-prefix sibling routers), CP3-shape (shared-root with internal path discrimination), or distinct-mounts (each router unique mount). Cross-mount router check applies regardless of variant — any router sharing mount with siblings requires sibling path-segment enumeration.

### §5.35 — AI POST reference model second application instance: ADD shape vs PROMOTE shape (NEW v2.28 §5.27 amendment)

v2.26 §5.27 locked the worldEvents reference model uniform state (all 4 AI POSTs at requireAuth + aiRateLimiter post-CP3). CP3 D4 was the first reference-model application instance: PROMOTE shape (handlers had aiRateLimiter; needed requireAuth). CP4 D1 is the second instance: ADD shape (handlers had neither; needed both).

Reference model application shapes (LOCKED v2.28 §5.27 amendment):

- PROMOTE shape (CP3 D4 first instance): handlers have aiRateLimiter present, missing requireAuth. Disposition: optionalAuth → requireAuth (preserve aiRateLimiter). 2 handlers at worldEvents.js promoted CP3 D4.

- ADD shape (CP4 D1 second instance): handlers have neither requireAuth nor aiRateLimiter. Disposition: ADD both + import aiRateLimiter at file top. 13 handlers across sceneProposeRoute.js + sceneSetRoutes.js ADDed at CP4 D1.

Cumulative AI POST cluster at uniform reference model post-CP4 (~28 handlers):

- worldEvents.js: 4 handlers (CP3 closure)

- episodeBriefRoutes.js: 4 handlers (preserved at CP1 surface)

- episodes.js: 2 handlers (preserved at CP2; lines 869 + 1108 post-edit)

- episodeOrchestrationRoute.js: 1 handler (added at CP2 D3)

- sceneProposeRoute.js: 1 handler (added at CP4 D1 — ADD shape)

- sceneSetRoutes.js: 12 handlers (added at CP4 D1 — ADD shape)

- press.js: 4 handlers deferred to CP10 partial-migration disposition

Reference model now uniform across ~28 AI POSTs in 6 files. CP5-CP10 surface reports identify any AI-cost POSTs in CP zone files; apply ADD or PROMOTE shape per current handler state.

### §5.36 — Frontend ideal state characteristics (NEW v2.28 §5.29 amendment — first NO-Track-7-coordination CP)

CP4 is the first CP where backend Tier 1 promotion lands cleanly with NO Track 7 mini-CP coordination needed. v2.27 §5.29 locked the tier-trigger matrix: backend Tier 1/2/3 + frontend raw fetch → Track 7 mini-CP REQUIRED; backend Tier 4 + frontend raw fetch → Pattern E equivalent (no coordination). CP4 reveals a third state: backend Tier 1+ + frontend service-module-apiClient = ideal state, NO coordination needed.

Frontend ideal state characteristics (LOCKED v2.28 §5.29 amendment):

- Service modules wrap all backend API calls (e.g., sceneService.js + sceneLibraryService.js + sceneLinksService.js for Scene cluster)

- Service modules use apiClient (Bearer token via Track 1 interceptor)

- Frontend pages/components route through service modules (no direct fetch to backend paths)

- Track 7 mini-CP NOT triggered when this state is in place

Architectural target. The cumulative work of Track 1 (apiClient interceptor) + Track 6 frontend migration + service-module pattern compound to produce the ideal state. CP4 demonstrates the target shape; CP5-CP11 surface reports check for this state at frontend correspondence audit.

Frontend correspondence audit decision tree (post-v2.28):

- Backend Tier 1+ + frontend service-module-apiClient → IDEAL STATE; no Track 7 coordination needed (CP4 first instance)

- Backend Tier 1+ + frontend raw fetch → Track 7 mini-CP REQUIRED (CP3 + WorldStudio.jsx first instance)

- Backend Tier 4 + frontend raw fetch → Pattern E equivalent; no coordination needed (worldStudio.js GETs at CP3)

Future Track 7 mini-CP candidates per v2.28 §5.36 ideal state evaluation: CP5-CP11 surface reports verify whether frontend correspondence is ideal state or raw-fetch state. Track 7 mini-CP scope = sum of raw-fetch sites where backend disposition is Tier 1/2/3.

### §5.37 — Surface-discovery methodology refinement (NEW v2.28 §5.30 amendment + PE-12)

CP4 execution surfaced a methodology divergence: surface report's 8-line-window Python grep for bare handlers identified 1 bare handler in sceneSetRoutes.js, but execution-time per-handler-block analysis caught 3 inline bare GETs (`/:id/spec`, `/:id/canvas`, `/:id/angles/:angleId/depth-map`). Window-based grep missed handlers when they were tightly clustered in 8-line span.

Surface-discovery methodology refinement (LOCKED v2.28 §5.30 amendment + PE-12). CP5-CP11 surface reports default to per-handler-block analysis (using router.<verb> next-line as block boundary) over fixed-line-window grep for bare-handler identification. Per-handler-block scan more rigorous; catches tightly-clustered handlers that window-based grep may miss.

Methodology comparison:

- Fixed-line-window grep (CP1-CP3 surface methodology): grep with -A8 or similar; window-bounded; may miss tightly-clustered handlers

- Per-handler-block analysis (CP4 execution + LOCKED v2.28 §5.30): identify each `router.<verb>(...` as block start; next `router.<verb>(...` is block end; analyze middleware within each block independently

CP5-CP11 surface reports apply per-handler-block analysis as default; fixed-line-window grep available as fallback for cross-handler aggregate counts.

### §5.38 — Surface-correction 14-data-point validation (UPDATED v2.28 §5.17 / §5.24)

v2.27 §5.24 graduated surface-correction pattern to 9 cumulative data points across CP15 + CP1 + CP2 + CP3 + Track 7 mini-CP. CP4 contributes 5 more, graduating the pattern to 14 cumulative data points across CP15 + CP1 + CP2 + CP3 + Track 7 mini-CP + CP4:

- Data points 1-9 (per v2.27 §5.24): WorldSetupGuide reclassification + press.js scope + file count + handler count + mount-collision count + Grep 1 baseline + handler count + AI POST count + worldTemperatureRoutes anomaly + apiClient local name + per-category site count

- Data point 10 (CP4): file count correction — planning forecast 8; surface counted 6 (-25%)

- Data point 11 (CP4): handler count correction — planning forecast ~140; surface counted 126 (-10%)

- Data point 12 (CP4): lazy-noop count correction — planning §A.7 forecast 2-4 files; actual 0 (first WP1 NO-OP CP)

- Data point 13 (CP4): AI POST count finding — not in planning forecast; surface enumerated 13 candidates (D1 promoted all uniformly)

- Data point 14 (CP4): F-AUTH-5 controller site count — not enumerated in planning; surface counted 10 sites (sceneController × 2 + sceneStudioController × 8)

Surface-correction pattern formal lock graduates (LOCKED v2.28 §5.17 / §5.24). 14 cumulative data points across two phases (Track 6 CP15 + Step 3 CP1/CP2/CP3 + Track 7 mini-CP + CP4). Empirical surface-time inspection consistently catches what fix-plan revisions and planning phase miss. Pattern density: ~2-3 corrections per CP. CP3 highest at 4; CP4 at 5 (highest single-CP correction count to date). CP5-CP11 surface reports apply rigorous empirical verification: per-handler-block analysis (per §5.30); custom-router-variable detection; AI POST enumeration; F-AUTH-5 site cataloguing.

### §5.39 — Step 3 pacing fourth backend data point (UPDATED v2.28, supersedes v2.26 §5.25 + v2.27 §5.31)

Step 3 pacing model now has four backend data points + one frontend data point:

- CP1 (backend, architectural): ~5 handlers in 75 min = ~15 min/handler

- CP2 (backend, mechanical): 227 handlers in 90 min = ~24 sec/handler

- CP3 (backend, mixed-disposition): 120 handlers in 75 min = ~38 sec/handler

- Track 7 mini-CP (frontend, uniform Pattern A): 15 sites in 45 min = ~3 min/site

- CP4 (backend, pure Tier 1 + AI POST overlay): 126 handlers in 80 min = ~38 sec/handler

Backend pacing convergence (four data points): ~80 min ±15 min mean per backend CP (CP1 75 / CP2 90 / CP3 75 / CP4 80). v2.23 §5.4 forecast all backend CPs at "1-2 sessions"; actual all 1 session for first 4 backend CPs in a row. Conservative bias 2x→1x sessions confirmed for fourth consecutive CP.

Total Step 3 + Track 7 estimate update post-CP4: 4 backend CPs + 1 Track 7 mini-CP = 5 sessions used. ~7 backend CPs remaining (CP5-CP11) + estimated 0-3 Track 7 mini-CPs (depending on per-CP frontend correspondence audit) = ~7-10 sessions remaining at conservative bias. Total Step 3 + Track 7 trajectory: ~12-15 sessions estimate vs original v2.23 §5.4 lock of ~20-22 sessions = ~30-45% under original forecast at this trajectory.

Backend cost-per-handler analysis (post-v2.28):

- Architectural overhead CPs (CP1 shape): ~15 min/handler (small handler count, refactor work dominates)

- Mechanical-edit dominant CPs (CP2 shape): ~24 sec/handler (large handler count, sed-bulk efficiency)

- Mixed-disposition CPs (CP3 shape): ~38 sec/handler (per-handler tier classification + adjudication overhead)

- Pure Tier 1 + AI POST overlay CPs (CP4 shape): ~38 sec/handler (uniform sweep + 13 AI POST overlay)

### §5.40 — Step 3 CP5 architectural findings (LOCKED v2.29, COMPLETE — Wardrobe cluster, Item 16 escalation + audit Sweep b full closure)

CP5 completed at commit 1a2d433d (single squashed commit, 8 file-boundary WIPs collapsed; single session, ~95 min actual vs forecast 100-120 min — on or under forecast). Cleanest mid-scale CP closure in Step 3 backend phase: 7 files / 86 handlers / 69 new tests / 0 regressions / pure Tier 1 disposition (2nd consecutive after CP4). WP1 lazy-noop removal at 3 files (back to non-NO-OP after CP4 first WP1 NO-OP); WP2 Tier 1 promotion sweep at 74 handlers; WP3 AI POST reference model application at 12 handlers (5 files); WP4 aggregate-counter test methodology (69 tests passing — 1.06x at-forecast, slightly above forecast 55-65). Backend test suite: 1611 → 1680 passing (+69 tests, +1 suite, 0 regressions, 0 failed). Frontend unchanged at 845 (CP5 backend-only sweep; 2nd consecutive NO-Track-7-coordination CP). Backed up at 1a2d433d on claude/f-auth-1-backup.

Two architectural lock items closed at CP5:

- Item 16 closure ESCALATED: original v1.x Item 16 lock specified replacement of wardrobeLibrary.js:18 env-conditional with `authenticate`; CP5 D2 escalates to `requireAuth` per Step 3 Tier 1 default + §5.22 read vs write disposition discipline. `requireAuth` is the canonical Step 3 Tier 1 middleware. Net effect at wardrobeLibrary.js: dev-mode auth-bypass eliminated (isDevelopment + authMiddleware const + dev-user literal + authenticate legacy alias all removed); 5 affected handlers (and 25 total in file) require valid auth in ALL environments post-CP5. Architectural improvement on original lock — see §5.41 amendment.

- outfitSets §4.1(b) FULL audit Sweep b closure: CP5 D3 ADDed requireAuth import + applied requireAuth to all 5 outfitSets.js routes. Combined with CP2 D5 (episodes.js /:id/outfits half at lines 99/105/113/117): full audit §4.1(b) Sweep b closure achieved at CP5. Both halves of audit handoff §4.1(b) sub-form now resolved — see §5.42 amendment.

Five adjudication decisions executed cleanly:

- D1 (12 AI POSTs ADD reference model): All 12 promoted to requireAuth + aiRateLimiter uniformly per worldEvents reference model. ADD shape (no existing aiRateLimiter to PRESERVE). aiRateLimiter import added to 5 files (wardrobe + wardrobeLibrary + wardrobeBrands + hairLibraryRoutes + makeupLibraryRoutes). 8 sites in wardrobe.js + 1 each in 4 other files. Third reference-model application instance after CP3 D4 PROMOTE + CP4 D1 ADD; cumulative 29 handlers across 11 files at uniform pattern — see §5.43 amendment.

- D2 (Item 16 escalation to requireAuth): LOCKED with escalation note. Mechanism: removed isDevelopment + authMiddleware const block + 5 handlers escalated from authMiddleware to requireAuth in single edit. Architectural improvement; see §5.41.

- D3 (outfitSets.js §4.1(b) Sweep b closure): All 5 routes ADDed requireAuth (GET / + GET /:id + POST / + PUT /:id + DELETE /:id). Combined with CP2 D5: full audit Sweep b closure; see §5.42.

- D4 (Test methodology aggregate-counter): 69 tests at aggregate-counter methodology per v2.27 §5.30. Forecast 55-65; actual 69 (1.06x at-forecast — slightly above forecast). Third aggregate-counter data point (CP3 0.35x deflation; CP4 1.07x at-forecast; CP5 1.06x at-forecast). Aggregate-counter accuracy varies by aggregation density; CP4+CP5 show ~1.0x norm — see §5.30 amendment continued.

- D5 (wardrobe.js 7 bare AI POSTs single-edit ADD shape): Single edit applies both requireAuth + aiRateLimiter simultaneously per CP4 ADD shape canonical pattern. NOT a two-step process. Pattern preserved across 12 ADD sites at CP5.

Per-tier handler distribution post-CP5:

- Tier 1 (requireAuth): 74 handlers across 7 files (wardrobe 26 + wardrobeLibrary 24 + wardrobeBrands 6 + wardrobeEventRoutes 3 + outfitSets 5 audit closure + hairLibrary 5 + makeupLibrary 5)

- Tier 1 + aiRateLimiter (NEW promotions): 12 handlers (wardrobe 8 + wardrobeLibrary 1 + wardrobeBrands 1 + hairLibrary 1 + makeupLibrary 1 per D1)

- Tier 2 / Tier 3 / Tier 4 / Tier 5: 0 handlers (Wardrobe cluster is creator-owned production tooling without admin subset, public catalog, or env-gated mounts; matches CP4 pure Tier 1 shape)

All 5 verification greps pass: (1) degradeOnInfraFailure consumer count 8 → 8 (UNCHANGED — no Tier 3 in CP5); (2) requireAuth consumer count 491 → 584 (+93 = 7 imports + 86 handlers); (3) lazy-noop fallback in CP5 zone 3 → 0 (3 files cleaned at WP1); (4) authenticateToken active hits in CP5 zone = 0 (UNCHANGED); (5) NEW aiRateLimiter consumers in CP5 zone = +22 (5 imports × 2 match counts + 12 handlers).

- F-AUTH-4 multi-line grep zero hits in CP5 zone (matches CP3 + CP4 pattern; no auth-weakening comment blocks).

- F-AUTH-5 expansion: 13 sites in wardrobe controllers (5 in wardrobeApprovalController.js — CP2 zone, already always-resolved post-CP2 Tier 2 admin promotion; 8 in wardrobeLibraryController.js — CP5 zone, defense-in-depth no-ops post-CP5 Tier 1 promotion). Cumulative F-AUTH-5 site cataloguing across F-AUTH-1: ~50+ controller fallback chains rendered always-resolved by route-tier promotion.

- Mount-collision distinct-mounts variant verified (CP4 third-shape precedent applies). 7 routers each with unique /api/v1/<domain> mount path; no cross-mounts in CP5 zone.

- Frontend ideal state confirmed at 2nd consecutive CP: wardrobeService.js × 9 apiClient calls + 0 raw fetch to Wardrobe cluster paths in frontend pages/components. Track 6 frontend migration + service-module pattern + apiClient interceptor combine for default ideal-state shape across multiple production-tooling clusters — see §5.44 amendment.

- No HTTP method mismatches surfaced. Step 3 zero-method-mismatch streak: 5 consecutive CPs (CP1 + CP2 + CP3 + CP4 + CP5).

- PE-13 filed (from surface): wardrobe.js:1289-1294 schema-drift comment ("RDS table may have been created from a simpler migration that lacks approval_status, worn_at, etc.") — defensive schema coding pattern; methodology finding, not security finding.

- PE-14 filed (NEW at execution): wardrobe.js:217 /:id/upscale + wardrobe.js:239 /bulk/upscale — likely AI POSTs not in D1 lock; promoted to Tier 1 (requireAuth) per locked plan but WITHOUT aiRateLimiter; aiRateLimiter ADD candidate for future polish CP. Surface-discovery methodology refinement candidate (extend AI POST keyword set to include `upscale|denoise|interpolate`).

### §5.41 — Item 16 lock escalation: authenticate → requireAuth (NEW v2.29 §5.5 amendment)

Original v1.x Item 16 lock at v1.7 fix plan specified replacement of wardrobeLibrary.js:18 env-conditional middleware (`const authMiddleware = isDevelopment ? <noop> : authenticate`) with uniform `authenticate` everywhere. CP5 D2 surface adjudication recognized that Step 3's canonical Tier 1 middleware is `requireAuth`, not `authenticate`. Applying `authenticate` would have created a tier-mismatch with the rest of CP5's Tier 1 promotion. CP5 escalates Item 16 closure to `requireAuth`.

Architectural improvement (LOCKED v2.29 §5.5 amendment). Item 16 closure ESCALATED from `authenticate` to `requireAuth` per Step 3 Tier 1 default + §5.22 read vs write disposition discipline. The original v1.x Item 16 lock was correct for the v1.x fix plan scope (single-file fix); CP5 D2 recognizes that within Step 3 cluster sweeps, Tier 1 default applies to all handlers in scope.

Net effect at wardrobeLibrary.js: dev-mode auth-bypass eliminated. All 25 handlers in file (the 5 originally using authMiddleware + 4 optionalAuth + 16 bare) now wrap requireAuth. The dev-user injection (`req.user = { id: 'dev-user', email: 'dev@example.com', name: 'Dev User' }`) that the env-conditional installed is gone. Production safety: even if NODE_ENV is misconfigured, no dev-user injection path exists.

Pattern for future lock escalations (LOCKED v2.29 §5.5 amendment): when v1.x or v2.x lock specifies a middleware replacement that pre-dates Step 3 Tier 1 default, CP-level adjudication may escalate to `requireAuth` if the target file falls within a Step 3 cluster sweep. Surface report flags candidate; closing report records escalation rationale.

### §5.42 — Audit §4.1(b) Sweep b FULL closure (NEW v2.29 §4 amendment)

Audit handoff v8 §4.1(b) Sweep b identified two halves of the same auth gap: (1) outfitSets.js — 5 routes with no auth middleware declared; (2) episodes.js — sub-form mount of outfit-set controller at lines 99/105/113/117. Sweep b lock specified ADD requireAuth to both halves.

Closure trajectory:

- CP2 D5 (commit d73599f8): episodes.js /:id/outfits half closed. Lines 99/105/113/117 promoted to Tier 1 within Episodes cluster sweep.

- CP5 D3 (commit 1a2d433d): outfitSets.js half closed. ADD requireAuth import + 5 routes wrapped requireAuth.

Combined closure (LOCKED v2.29 §4 amendment). Audit §4.1(b) Sweep b is FULLY CLOSED at CP5. Both halves of the sub-form resolved through coordinated work across CP2 + CP5. No remaining outfit-set route handlers without Tier 1 disposition.

Pattern for future multi-CP audit closures (LOCKED v2.29 §4 amendment): when audit findings span multiple clusters, mark each half's CP closure individually + record full closure at the second CP's fix plan revision. Combined-closure pattern serves audit handoff verification: v9 audit handoff (when generated) can reference §5.42 for §4.1(b) Sweep b resolution.

### §5.43 — AI POST reference model third application instance: cumulative 29 handlers across 11 files (UPDATED v2.29 §5.27)

CP3 D4 (PROMOTE shape, 2 handlers in worldEvents.js) + CP4 D1 (ADD shape, 13 handlers in sceneProposeRoute + sceneSetRoutes) + CP5 D1 (ADD shape, 12 handlers across 5 wardrobe files) = 29 handlers cumulative at uniform requireAuth + aiRateLimiter pattern across 11 files. Reference model now extends across:

- worldEvents.js: 4 handlers (CP3 closure)

- episodeBriefRoutes.js: 4 handlers (preserved at CP1 surface)

- episodes.js: 2 handlers (preserved at CP2)

- episodeOrchestrationRoute.js: 1 handler (CP2 D3)

- sceneProposeRoute.js: 1 handler (CP4 D1 — ADD shape)

- sceneSetRoutes.js: 12 handlers (CP4 D1 — ADD shape)

- wardrobe.js: 8 handlers (CP5 D1 — ADD shape)

- wardrobeLibrary.js: 1 handler (CP5 D1 — ADD shape)

- wardrobeBrands.js: 1 handler (CP5 D1 — ADD shape)

- hairLibraryRoutes.js: 1 handler (CP5 D1 — ADD shape)

- makeupLibraryRoutes.js: 1 handler (CP5 D1 — ADD shape)

- press.js: 4 handlers deferred to CP10 partial-migration disposition

Reference model application shape distribution:

- PROMOTE shape (had aiRateLimiter; needed requireAuth): 2 handlers at worldEvents.js (CP3 D4)

- ADD shape (had neither): 26 handlers across 10 files (CP4 D1 × 13 + CP5 D1 × 12 + CP1/CP2 inline preservations)

CP6-CP11 surface reports identify any AI-cost POSTs in CP zone files; apply ADD or PROMOTE shape per current handler state. Reference model uniform across the 29-handler cluster post-CP5.

### §5.44 — Frontend ideal state at 2nd consecutive CP (UPDATED v2.29 §5.36)

CP4 was the first instance of frontend ideal state (Scene cluster — service modules using apiClient cover all backend paths; 0 raw fetch). v2.28 §5.36 locked the characteristics + amendment. CP5 confirms repeatability for Wardrobe cluster (different domain, different file set).

Pattern reliable across multiple production-tooling clusters (LOCKED v2.29 §5.36 amendment). CP4 (Scene) + CP5 (Wardrobe) + retroactive CP2 verification (Episodes + shows) confirm: when Track 6 frontend migration is complete + service-module pattern is in place + apiClient interceptor handles Bearer token attachment, backend Tier 1 promotion lands cleanly with NO regression window. Ideal state is the default shape for production-tooling clusters in this codebase, not an outlier.

Cumulative ideal-state observations:

- CP4 Scene cluster: 55 service-module apiClient calls + 0 raw fetch

- CP5 Wardrobe cluster: 9 service-module apiClient calls + 0 raw fetch

- Retroactive CP2 verification (Episodes + shows): episodeService.js + showService.js exist; 0 raw fetch to /api/v1/shows or /api/v1/episodes anywhere in frontend/src/

- CP3 World cluster: WorldStudio.jsx (anomalous case) used raw fetch — Track 7 mini-CP coordination required (commit 3e447814)

Track 7 mini-CP scope (LOCKED v2.29 §5.36 amendment). Track 7 mini-CPs are exception-class work, not default-class. Scope = sum of raw-fetch sites where backend disposition is Tier 1/2/3 in CP zone. CP6-CP11 surface reports continue checking; ideal state expected to remain default; Track 7 mini-CP triggered only when raw fetch surfaces.

AUDIT-GAP CALLOUT (NEW v2.29 §5.36 amendment — important architectural note). v2.27 §5.29 + v2.28 §5.36 ideal-state characteristic locks specified "service modules + apiClient + Bearer token attachment" as sufficient for ideal-state disposition. CP5 closure surfaced an architectural finding (F-AUTH-X1, see §10): Bearer token attachment is necessary but NOT sufficient — token format must also match requireAuth's verifier expectation. F-AUTH-1's requireAuth uses CognitoJwtVerifier (RS256 only); frontend's actual login flow issues HS256 tokens via routes/auth.js + tokenService.js. Bearer token IS attached + IS HS256 + IS rejected by Cognito-only verifier. Track 7 frontend correspondence audit verified attachment shape, not token format compatibility. v2.29 §5.36 amends ideal-state characteristic to: "service modules + apiClient + Bearer token attachment + token format compatibility with requireAuth verifier." See §10 for F-AUTH-X1 finding details.

### §5.45 — Pure Tier 1 sweep at 2nd consecutive CP (UPDATED v2.29 §5.22)

CP4 (Scene cluster) + CP5 (Wardrobe cluster) both pure Tier 1 sweeps (no Tier 2/3/4/5 candidates). Both creator-owned production tooling clusters. CP3 was mixed disposition (worldStudio.js had Tier 4 PUBLIC scene catalog routes); CP1 was Tier 3-only at architectural-overhead scale.

Pure Tier 1 sweep as default disposition shape (LOCKED v2.29 §5.22 amendment). Pure Tier 1 sweep is the default disposition shape for creator-owned production tooling clusters without genuinely public catalogs. CP3's mixed disposition was the exception (worldStudio.js had explicitly-public scene catalog routes); CP4 + CP5 demonstrate that production tooling without genuinely public catalogs uniformly disposes Tier 1.

CP6-CP11 default expectation: pure Tier 1 sweep unless surface reveals genuinely public catalog routes (Tier 4 candidates) or admin-only workflow (Tier 2 candidates). Mixed Tier 1+3+4 within single file (v2.26 §5.21 architectural primitive) remains available if specific files require, but is exception-class.

### §5.46 — Surface-correction 19-data-point validation (UPDATED v2.29 §5.17 / §5.24)

v2.28 §5.38 graduated surface-correction pattern to 14 cumulative data points across CP15 + CP1 + CP2 + CP3 + Track 7 mini-CP + CP4. CP5 contributes 5 more, graduating the pattern to 19 cumulative data points across CP15 + CP1 + CP2 + CP3 + Track 7 mini-CP + CP4 + CP5:

- Data points 1-14 (per v2.28 §5.38)

- Data point 15 (CP5): file count correction — planning forecast 7; surface counted 7 (matches; first CP with no file-count correction since CP1)

- Data point 16 (CP5): handler count correction — planning forecast ~80; surface counted 86 (+7.5%; smallest delta of any CP)

- Data point 17 (CP5): wardrobe.js anchor file handler count — planning §5.5 forecast ~25; surface counted 34 (+36%; largest single-file correction surfaced to date)

- Data point 18 (CP5): lazy-noop count correction — planning §A.7 didn't enumerate Wardrobe-zone; actual 3 files (back to non-NO-OP after CP4 first WP1 NO-OP)

- Data point 19 (CP5): AI POST count finding — not in planning forecast; surface enumerated 12 ADD-shape candidates (D1 promoted all uniformly)

Surface-correction pattern formal lock graduates (LOCKED v2.29 §5.17 / §5.24). 19 cumulative data points across two phases (Track 6 CP15 + Step 3 CP1/CP2/CP3/CP4/CP5 + Track 7 mini-CP). Pattern density: ~2-3 corrections per CP. Highest single-CP correction count: CP4 + CP5 tied at 5 each. CP6-CP11 surface reports apply rigorous empirical verification.

### §5.47 — Step 3 pacing fifth backend data point (UPDATED v2.29, supersedes v2.28 §5.39)

Step 3 pacing model now has five backend data points + one frontend data point:

- CP1 (backend, architectural): ~5 handlers in 75 min = ~15 min/handler

- CP2 (backend, mechanical): 227 handlers in 90 min = ~24 sec/handler

- CP3 (backend, mixed-disposition): 120 handlers in 75 min = ~38 sec/handler

- Track 7 mini-CP (frontend, uniform Pattern A): 15 sites in 45 min = ~3 min/site

- CP4 (backend, pure Tier 1 + AI POST overlay): 126 handlers in 80 min = ~38 sec/handler

- CP5 (backend, pure Tier 1 + lazy-noop + Item 16 + audit closure + AI POST overlay): 86 handlers in 95 min = ~66 sec/handler

Backend pacing convergence (five data points): ~83 min ±15 min mean per backend CP (CP1 75 / CP2 90 / CP3 75 / CP4 80 / CP5 95). v2.23 §5.4 forecast all backend CPs at "1-2 sessions"; actual all 1 session for first 5 backend CPs in a row. Conservative bias 2x→1x sessions confirmed for fifth consecutive CP.

CP5 is the slowest backend CP to date (95 min vs ~80 min mean). Cause: WP1 lazy-noop removal at 3 files + Item 16 closure (single edit combining WP1 + escalation) + outfitSets §4.1(b) closure (NEW import + 5 ADDs) + 12 AI POST applications across 5 files (vs CP4's 13 across 2 files — cross-file coordination overhead). Total per-handler cost ~66 sec vs ~38 sec at CP3/CP4 reflects the additional architectural lock items.

Total Step 3 + Track 7 estimate update post-CP5: 5 backend CPs + 1 Track 7 mini-CP = 6 sessions used. ~6 backend CPs remaining (CP6-CP11) + estimated 0-2 Track 7 mini-CPs (depending on per-CP frontend correspondence audit) = ~6-8 sessions remaining at conservative bias. Total Step 3 + Track 7 trajectory: ~12-14 sessions estimate vs original v2.23 §5.4 lock of ~20-22 sessions = ~35-45% under original forecast at this trajectory. Plus F-AUTH-X1 + F-SOCKET-1 separate work streams (see §10).

### §10 — NEW MAJOR FINDINGS surfaced during CP5 closure (NOT in F-AUTH-1 scope; separate work streams)

CP5 closure conversation surfaced two architectural findings outside F-AUTH-1's original scope. Both are filed as separate work streams; do not affect F-AUTH-1's CP cadence or scope.

### §10.1 — F-AUTH-X1 (parallel HS256 JWT track — Cognito requireAuth verifier rejects HS256 tokens)

Surface trigger: dev environment login redirect-loop. User reports successful login at dev.primepisodes.com followed by immediate bounce back to login page. Network panel investigation revealed:

- Frontend POST to /api/v1/auth/login succeeds (200)

- Token issued (Bearer JWT, HS256-signed: alg=HS256, typ=JWT)

- Frontend stores token in localStorage.authToken

- apiClient interceptor attaches Authorization: Bearer <HS256 JWT> on subsequent requests

- Backend requireAuth middleware (uses CognitoJwtVerifier — RS256 only) rejects HS256 token with 401

- Frontend treats 401 as session-invalid → redirects to login → loop

Architectural diagnosis (LOCKED v2.29 §10.1). Two independent auth systems coexist in the codebase: Cognito track (F-AUTH-1's target — middleware/auth.js requireAuth/optionalAuth use CognitoJwtVerifier RS256) and Local HS256 JWT track (pre-existing, untouched by F-AUTH-1 — middleware/jwtAuth.js + services/tokenService.js + routes/auth.js:41 POST /login + frontend localStorage). F-AUTH-1's Tier 1 promotions (491+ handlers across CP1-CP5) silently broke real user activity in dev environment because frontend issues HS256 tokens; Cognito-only verifier rejects them.

Three architectural options:

- Option A — Migrate frontend to Cognito (long-term target). Replace custom login flow with Cognito SDK (amazon-cognito-identity-js or aws-amplify); replace routes/auth.js:41 POST /login issuance with Cognito-direct flow; deprecate services/tokenService.js + middleware/jwtAuth.js entirely. Substantial work — multi-week effort. Closes ALL auth surface to single trusted system.

- Option B — Dual-verifier in requireAuth (short-term unblock). middleware/auth.js requireAuth tries Cognito verifier first; on failure, falls back to local HS256 verification using JWT_SECRET. Pragmatic; preserves both tracks. ~1-2 day effort. Unblocks dev environment immediately. Architectural debt.

- Option C — Remove custom JWT track entirely, frontend stays on Cognito. Same as A in target state.

Recommendation (LOCKED v2.29 §10.1). Option B short-term (this week, unblock dev environment) + Option A long-term (after F-AUTH-1 closes, multi-week project). Frontend rework for Cognito migration cannot run as next sprint; Option B unblocks now. F-AUTH-1 CP6-CP11 cadence continues normally — Tier 1 promotions still apply correctly to both token types under dual-verifier.

Audit gap explanation. F-AUTH-1's premise was "codebase-wide auth bypass on writes via optionalAuth → requireAuth migration." The premise assumed requireAuth was the right gate. It is — for routes whose callers send Cognito tokens. The gap: nobody asked "what auth system does the frontend actually use?" Track 7 frontend correspondence audit at v2.27 §5.29 + v2.28 §5.36 verified Bearer token attachment, not token format compatibility. v2.29 §5.36 amends ideal-state characteristic to include token format compatibility check.

F-AUTH-X1 work stream scope:

- Phase 1 (this week): Option B implementation. Modify middleware/auth.js requireAuth to try Cognito verifier first, fall back to local HS256 verification. Verify dev environment login works post-fix.

- Phase 2 (post-F-AUTH-1): Option A planning. Frontend migration to Cognito SDK. Multi-week effort. Document architectural debt for resolution.

- Phase 3 (post-A): Option C cleanup. Deprecate services/tokenService.js + middleware/jwtAuth.js + routes/auth.js:41 POST /login custom issuance.

### §10.2 — F-SOCKET-1 (P0 hardcoded JWT_SECRET fallback)

Surface trigger: same conversation as F-AUTH-X1. Backend grep `grep -rn "jsonwebtoken\|jwt.sign\|HS256\|process.env.JWT_SECRET" src/` revealed:

- src/services/SocketService.js:19 — `const JWT_SECRET = process.env.JWT_SECRET || 'your-secret-key';`

- Implication: if JWT_SECRET environment variable is unset (deploy misconfiguration, env-file drift, container-spec mistake), the literal string `'your-secret-key'` becomes the active HMAC signing/verification secret.

- Production exposure: anyone reading the public source repository can forge HS256 tokens that pass Socket auth verification.

P0 production exposure (LOCKED v2.29 §10.2). F-SOCKET-1 is a critical production-grade security issue orthogonal to F-AUTH-1. Same-day hotfix required. Fix is mechanical: remove `|| 'your-secret-key'` fallback; throw on missing JWT_SECRET in production environment.

F-SOCKET-1 work stream scope:

- Same-day fix (today/tomorrow): remove `|| 'your-secret-key'` fallback at SocketService.js:19. Throw on missing JWT_SECRET in production env (NODE_ENV !== 'test' && !process.env.JWT_SECRET).

- Audit any other `|| '<literal>'` JWT_SECRET fallback patterns in tokenService.js (lines 21, 48, 57, 91, 100 per Claude Code grep output).

- Apply consistently: production environments must throw on missing secrets; never silently fall back to literal strings.

F-SOCKET-1 lands directly on dev branch (not on feature/f-auth-1). Bypasses Step 3 CP cadence entirely. Independent of F-AUTH-X1 architectural decision.

### §10.3 — Audit gap callout (UPDATED v2.29 §5.36 + new §10.3)

CP1-CP5 frontend correspondence audits verified service-module pattern + apiClient + Bearer token attachment shape. Audit method: comprehensive grep for raw fetch() calls to backend paths in CP zone; categorize by current frontend pattern (raw fetch vs apiClient).

Audit gap (LOCKED v2.29 §10.3). Audit method verified Bearer token IS attached but did NOT verify token FORMAT matches requireAuth verifier expectation. The "ideal state" lock at v2.27 §5.29 + v2.28 §5.36 is technically correct (service modules + apiClient + Bearer attachment IS the right shape) but incomplete (token format compatibility is also required for the attached Bearer to actually authenticate).

Audit method amendment (LOCKED v2.29 §5.36 + §10.3): when verifying frontend correspondence ideal state, additional check required:

- Verify Bearer token attachment via apiClient interceptor (existing check)

- Verify token format matches requireAuth verifier expectation (NEW check). Specifically: decode JWT header from frontend localStorage / token storage; verify `alg` claim matches verifier algorithm (e.g., RS256 for Cognito, HS256 for local HMAC).

- Document any token format mismatches as architectural findings (not as Track 7 mini-CP scope; route to F-AUTH-X1-class work stream).

Retroactive audit application: the F-AUTH-X1 finding existed since CP2 landed on origin/dev. v2.29 §10.3 amendment ensures CP6-CP11 surface reports include token format check; if frontend uses Cognito-incompatible tokens (HS256), surface flags as F-AUTH-X1-class concern (not Track 7).

### §10.4 — F-SOCKET-1 closure (LOCKED v2.30, COMPLETE)

F-SOCKET-1 closed at commit c1962ace via PR #649 (squash-merged to dev). Same-day P0 hotfix; orthogonal to F-AUTH-1 program; bypassed Step 3 CP cadence per v2.29 §10.2 lock.

Mechanical fix outcome:

- src/services/SocketService.js: hardcoded `|| 'your-secret-key'` fallback at line 19 eliminated; module-load strict-fail pattern installed (throws if JWT_SECRET unset and NODE_ENV !== 'test')

- NEW file tests/unit/security/jwt-secret-strict-fail.test.js: 3 tests covering negative case (production + JWT_SECRET unset → throws) + test-env carve-out sentinel + positive case (JWT_SECRET set → loads cleanly)

- Backend test suite: 1680 → 1683 passing (+3, exactly matching forecast; 0 regressions)

- No test setup changes (tests/setup.js:16 already configures JWT_SECRET)

- No CI config changes (all 3 workflows already set JWT_SECRET in env blocks)

- Out-of-scope finding filed as PE-15 in §9.12: deploy-production.yml:80 + deploy-dev.yml:65 use literal test JWT_SECRET in validation env blocks; benign current usage; future deploy-config hardening candidate

Deployment verification outcome (Evoni infra-side check). JWT_SECRET was always set to a 64-char cryptographically-strong random value in dev EC2 (.env file at /home/ubuntu/episode-metadata/.env). The fallback `'your-secret-key'` had never silently fired in any deployed environment. F-SOCKET-1 fix is hardening / defense-in-depth — NOT incident response. No credential rotation needed; no forced user re-authentication; no breach occurred.

Single-environment deployment topology confirmed. One EC2 instance (54.163.229.144 / dev.primepisodes.com), one .env file, two PM2 processes (episode-api + episode-worker). No staging environment. AWS Secrets Manager empty (not in use for JWT_SECRET). All future production-grade work streams (e.g., F-AUTH-X1 Phase 2, future hardening passes) deploy through the same single-environment path.

F-SOCKET-1 work stream complete (LOCKED v2.30 §10.4). Latent vulnerability eliminated. Future deploy misconfiguration that leaves JWT_SECRET unset will throw at module load instead of silently signing tokens with a forgeable literal — strict failure mode safer than silent compromise.

### §10.5 — F-AUTH-X1 Phase 2 closure (LOCKED v2.30, COMPLETE — Option B dual-verifier)

F-AUTH-X1 Phase 2 (Option B dual-verifier) closed at commit 8b5750b0 via PR #650 (squash-merged to dev). Mid-scale architectural fix on feature/f-auth-x1-option-b branch; merged to dev after Phase 1 surface adjudication of Q1-Q12 + 6 D-decisions locked.

Phase 1 surface report findings (locked at adjudication):

- Q1: F-AUTH-2 lazy-init shape preserved; existing verifyToken() lines 64-95 already had test-mode HS256 dispatch — Phase 2 = remove NODE_ENV gate + add alg discriminator (smaller scope than initially modeled)

- Q2: tokenService.verifyToken() shape compatible with Cognito output — same `sub` field for subject ID; `groups` field present in HS256 path

- Q3: req.user.sub never read across codebase (0 hits); decoded.sub → req.user.id mapping uniform; no shape normalization needed; group fallback `decoded['cognito:groups'] || decoded.groups || []` already handles both schema variants

- Q9: refactor verifyToken() ONLY; all callers (requireAuth + optionalAuth + authenticateToken + authenticate alias) pass through this function — minimal blast radius

Phase 2 execution outcomes:

- src/middleware/auth.js: +135/-24 LOC; detectTokenAlgorithm() helper added; verifyToken() refactored with alg-based discriminator routing (RS256/null+non-test → Cognito; HS256 OR null+test → tokenService); req.user.source observability field populated by all 3 internal callers

- NEW file tests/unit/middleware/f-auth-x1-dual-verifier.test.js: 21 new tests across 4 describe blocks (routing × 10 + req.user.source propagation × 5 + AUTH_DEBUG gating × 4 + F-AUTH-2 lazy-init regression × 2)

- Backend test suite: 1683 → 1701 passing (+18; within +15-20 forecast; 0 regressions)

- Architectural debt comment block per Q8 verbatim text — documents Option B as tactical short-term unblock + cross-references v2.29 §10.1 + Track 8 long-term target

- AUTH_DEBUG-gated console.debug logging for verifier-success observability (path + verifier + alg + sub only; never logs token or full payload)

- F-AUTH-2 lazy-init shape byte-identical (getCognitoConfig + getIdTokenVerifier + getAccessTokenVerifier preserved; no changes to memoized cache pattern)

- module.exports unchanged: authenticate, authenticateToken, authorize, authorizeRole, optionalAuth, requireAuth, verifyToken, verifyGroup

- No frontend changes — HS256 login path (POST /api/auth/login → generateTokenPair → accessToken) was already client-side; was being rejected at backend boundary in non-test environments; post-merge becomes operational end-to-end without client modification

degradeOnInfraFailure semantics contraction (LOCKED v2.30 §10.5 amendment). Per Phase 1 surface §Q5 + D3 lock: degradeOnInfraFailure scope contracts naturally to RS256-only traffic post-Option-B. HS256 paths bypass Cognito verifier entirely, so Cognito infra-failure detection (degradeOnInfraFailure flag) becomes irrelevant for HS256 traffic. No flag-shape change required; contraction documented in middleware/auth.js architectural-debt comment block.

State matrix post-Option-B (locked):

- HS256 token + Cognito infra fail → HS256 verifies normally (Cognito untouched) → req.user populated with source='local-hs256'

- HS256 token + HS256 verifier rejects → 401 (no degradation; token genuinely invalid)

- RS256 token + Cognito infra fail → existing degradeOnInfraFailure path (unchanged for backward compat)

- RS256 token + Cognito verifier rejects → 401 (no degradation; existing behavior)

- No token + degradeOnInfraFailure flag (Tier 3 optionalAuth) → existing degradation path (unchanged)

- Both verifiers fail (token rejected by both) → 401 with chained cause

Audit-gap closure validation (UPDATED v2.30 §5.36 + §10.3 follow-up). v2.27 §5.29 + v2.28 §5.36 ideal-state characteristic locks specified "service modules + apiClient + Bearer token attachment" as sufficient for ideal-state disposition. CP5 closure surfaced the gap (token format compatibility check required); v2.29 §5.36 amended the characteristic; v2.30 confirms the amendment is operationally validated by F-AUTH-X1 Phase 2 closure. Future CP6-CP11 surface reports continue token format check as part of frontend correspondence audit.

Phase 2 execution deviations (handled correctly per closing report):

- Branch creation friction: harness pre-assigned `claude/refactor-verify-token-yhWBh`; locked plan specified `feature/f-auth-x1-option-b`. Claude Code created the locked-plan branch from main (origin/dev not initially fetched), pushed first commit, then fetched origin/dev (c1962ace, matching plan baseline), reset + cherry-picked single commit onto dev base, force-pushed-with-lease so PR #650 shows only F-AUTH-X1 changes against dev. Resolution clean; PR diff correct. Awareness item: Phase 2-style work where locked plan specifies branch base may need explicit `git fetch origin <base>` before branch creation.

- Routing fallback semantics for unparseable alg: Phase 1 surface §Q4 specified "alg=null → Cognito". Phase 2 execution recognized auth-gaps.test.js test fixture compatibility requirement: test env must continue routing to tokenService for HS256 fixtures. Resolution: alg=HS256 OR (alg=null + test env) → tokenService; alg=RS256 OR (alg=null + non-test) → Cognito. Refinement of Q4, not contradiction; preserves both F-AUTH-2 lazy-init behavior AND existing test fixture compat. Documented in Q8 comment block §4.

- COGNITO_CLIENT_ID test setup adjustment: Phase 2 test #15-equivalent ("verifyToken with HS256 token bypasses lazy-init even when Cognito config unset") needed COGNITO_CLIENT_ID set in test scope to prevent AUTH_CONFIG_MISSING from firing on Cognito-fallback path. Resolution: module-scope env manipulation in new test file (not modification of global tests/setup.js). Isolates change; no ripple effects on other test files.

- Cosmetic: GitHub squash-merge used PR title verbatim as commit subject despite mcp__github__merge_pull_request `commit_title` parameter. Resolution: acceptable as-is; (#650) suffix preserves PR linkage; SHA 8b5750b0 canonical. Future awareness item: Claude Code sessions should set PR title to match desired squash commit subject if exact wording matters.

F-AUTH-X1 Phase 2 work stream complete (LOCKED v2.30 §10.5). Two-month dev-environment regression from CP2 silent breakage now resolved end-to-end. Backend Tier 1 routes (491+ handlers across CP1-CP5) accept both Cognito RS256 and local HS256 tokens via dual-verifier. Dev login flow operational. Architectural debt documented for Track 8 (post-F-AUTH-1 frontend Cognito SDK migration + dual-verifier removal).

### §11 — Track 8 (post-F-AUTH-1 frontend Cognito SDK migration) — formally created roadmap item (NEW v2.30)

Track 8 captures the long-term target identified in v2.29 §10.1 (Option A): migrate frontend to Cognito SDK so all tokens are RS256 (Cognito-native), then remove the dual-verifier path established in F-AUTH-X1 Phase 2 (Option B). Track 8 is post-F-AUTH-1; does NOT begin until F-AUTH-1 program (Step 3 CP1-CP11) closes.

Track 8 scope (LOCKED v2.30 §11):

- Phase 8.1 — Frontend Cognito SDK integration. Add amazon-cognito-identity-js OR aws-amplify dependency. Refactor frontend authentication flow (login UI + signup UI + password reset UI + token refresh logic) to use Cognito SDK. localStorage shape changes from `authToken` (HS256) to Cognito session shape (multiple tokens — accessToken + idToken + refreshToken).

- Phase 8.2 — Backend custom-JWT track deprecation. Mark routes/auth.js POST /login as deprecated (return deprecation header; log usage). Mark services/tokenService.js + middleware/jwtAuth.js as deprecated. Document migration path for any external integrations using the custom-JWT API.

- Phase 8.3 — Dual-verifier removal. Once frontend traffic confirmed migrated to Cognito tokens (via AUTH_DEBUG-gated logging metrics from Phase 2 establishing low/zero HS256 traffic), remove the HS256 path from middleware/auth.js verifyToken(). Remove detectTokenAlgorithm() helper. Remove req.user.source field. Remove architectural-debt comment block. Remove F-AUTH-X1 dual-verifier test file. Restore middleware/auth.js to Cognito-only verifier shape.

- Phase 8.4 — Custom-JWT cleanup. Delete services/tokenService.js + middleware/jwtAuth.js + routes/auth.js POST /login custom issuance handler. Frontend Cognito-direct flow becomes sole auth path.

Track 8 timing:

- PREREQUISITE: F-AUTH-1 program (Step 3 CP1-CP11) CLOSED. Track 8 does NOT begin during F-AUTH-1 cadence; F-AUTH-1 + Track 8 do not run in parallel.

- Estimated total effort: 2-4 weeks for Phase 8.1 (frontend rework) + 1-2 weeks for Phases 8.2-8.4 (backend cleanup). Total ~4-6 weeks post-F-AUTH-1.

- AUTH_DEBUG metrics gating: Phase 8.3 should not begin until HS256 traffic ratio is verifiably low (target: 0% production traffic on HS256; HS256 traffic only from CI test runs). Logging from F-AUTH-X1 Phase 2 enables this measurement.

Track 8 audit handoff. Post-F-AUTH-1 audit handoff v9 (when generated) should include Track 8 as the architectural follow-on: "F-AUTH-1 closed Tier 1 promotion across 491+ handlers; F-AUTH-X1 Phase 2 (Option B) provided short-term dual-verifier unblock; Track 8 completes architectural cleanup by removing HS256 path entirely." Track 8 itself can have its own fix-plan revisions (Track 8 v1.0 onward) when work begins.

### §5.48 — CP6 closure: Character cluster + universe Q13 (LOCKED v2.31, COMPLETE)

CP6 closed at commit 9892e604 on claude/f-auth-1-backup; auto-merged to origin/dev at e8bbb808. Single squashed commit; same-turn force-with-lease push per §9.13 Rule 2; integrator auto-merge per §9.13 Rule 6 (27th cumulative same-turn push / auto-merge across F-AUTH-1 program).

Scope outcomes:

- 13 source files modified (characters.js + character-clips.js + characterRegistry.js + characterAI.js + characterFollowRoutes.js + characterSparkRoute.js + characterGrowthRoute.js + universe.js + characterGenerator.js + characterDepthRoutes.js + characterGenerationRoutes.js + wantFieldRoutes.js + characterCrossingRoutes.js); 102 handlers per surface §3 inventory (matches actual after surface corrections)

- 12 NEW test files at tests/unit/routes/character-*-tier-promotion.test.js + tests/unit/routes/universe-mixed-tier-promotion.test.js + tests/unit/routes/want-field-tier-promotion.test.js

- 1 integration test updated: tests/integration/storyEvalV2.integration.test.js — 4 anonymous-request tests against now-promoted character-spark routes updated to expect 401 (truthful reflection of new contract; NEW §5.52 integration test discipline pattern lock)

- Backend test suite: 1680 → 1808 passing (+128 tests vs +108 forecast — over by 20; per-site assertions more granular at 102-handler scale; 0 regressions)

- All 7 lazy-noop residues eliminated (characterAI L26-31 + characterDepthRoutes L22-27 + characterFollowRoutes L11-21 3-level nested + characterGenerator L17-23 + characterRegistry L12-26 dual + characterSparkRoute L23-28 + universe L24-29) — same commit as domain sweep per §5.8 universal discipline

- All 5 verification greps pass (G1-G5 per surface §12): zero optionalAuth survivors on writes; zero lazy-noop residue; uniform AI POST + aiRateLimiter pattern; F-AUTH-4 banner cleaned at character-clips.js:18; universe Q13 GETs req.user-free

- Single session execution (collapsed from 2-session forecast per D10) — 5-for-5 → 6-for-6 single-session pattern; ~85min within ~83min ±15min mean (CP1 70 / CP2 95 / CP3 85 / CP4 80 / CP5 95 / CP6 85)

Tier disposition outcomes (per D1 lock):

- Tier 1 (requireAuth) — 97 promotions: all writes + reads except universe Tier 4

- Tier 4 (plain optionalAuth + PUBLIC) — 4 handlers: universe.js GETs (4 reads with 0 req.user consumption per surface §4 + G5 grep)

- Tier 1 PRESERVE — 1 handler: characterRegistry.js:1882 (was L1896 pre-CP6; line shift -14 from lazy-noop removal at L12-26; signature byte-identical) — first anchor file with built-in reference shape at surface time per §5.43 cumulative pattern

- Tier 2 (requireAuth + authorize(['ADMIN'])) — 0 handlers: Item 16 escalation inspection produced "no-escalation" first-time result per §5.41 amendment + §5.51 NEW response-shape vs permission-gate distinction

Sub-form (b) ADD shape application (per D7 lock):

- characters.js (2 GETs sub-form b): both Tier 1 — ADD requireAuth

- character-clips.js (5 mixed handlers sub-form b + "TESTING" banner): all Tier 1 — ADD requireAuth + banner removal

- characterGenerator.js (7 handlers; surface said sub-form b ADD shape, actual was optionalAuth PROMOTE shape per surface correction §5.50): all Tier 1 + 3 AI POSTs at PROMOTE shape with aiRateLimiter (surface corrected from 2 to 3: /propose-seeds + /generate-batch + /rewrite-field at L1198 calls anthropic at L1213)

AI POST reference model 4th application (per §5.43 cumulative pattern — validates default for production-tooling-cluster sweeps):

- 1 REFERENCE preserved verbatim at characterRegistry.js:1882

- 15 PROMOTE shape applications (5 characterAI + 1 characterSpark + 1 characterGrowth + 3 characterGenerator + 2 characterDepth + 1 characterGenerationRoutes + 1 wantFieldRoutes + 1 characterCrossingRoutes — surface corrected 2 PROMOTE counts down per §5.50)

- Cumulative post-CP6: 46 handlers across 14 files at uniform requireAuth + aiRateLimiter pattern (G3 grep: 16 hits across 11 CP6 files + 30 hits cumulative from CP1-CP5 work)

Universe Q13 mixed Tier 1+4 disposition (per D2 lock):

- 4 GETs Tier 4 PUBLIC: GET / + GET /series + GET /:id (3 unique catalog endpoints — note: surface counted 4, includes both root and /series catalog reads); each with PUBLIC comment block per worldStudio.js precedent

- 4 writes Tier 1: POST / + POST /series + PUT /series/:id + DELETE /series/:id + PUT /:id (5 writes; surface counted 4)

- PUBLIC comment block at universe.js imports per D2 verbatim text

- G5 grep confirms zero req.user reads in any Tier 4 GET handler body — Tier 4 PUBLIC compliant

- 2nd cumulative §5.21 mixed-tier primitive instance (1st was worldStudio.js at CP3); pattern-locking candidate for production-tooling-cluster default disposition

Mount-collision path-segment claim enumerations (per D8 lock):

- Collision A — /api/v1/character-registry (CP2-shape, two routers, same prefix): characterRegistry.js claims /registries* + /characters* (37 handlers); characterSparkRoute.js claims /sparks* (5 handlers); disjoint path-segment claim sets; zero collision

- Global-prefix mount — /api/v1 (NEW topology — 4th variant, NEW v2.31 §5.13/§5.34 amendment): character-clips.js claims /scenes/:sceneId/character-clips (2 handlers — list/create) + /character-clips/:id (3 handlers — get/update/delete); disjoint vs characters.js (/api/v1/characters); sub-tree extension vs CP4 scene cluster (/api/v1/scenes/...) — Express namespace routing handles correctly; zero collision

Item 16 escalation inspection result (per D6 lock — "no-escalation" first-time result):

- characterRegistry.js:658 — `const isAuthor = req.user?.role === 'author' || req.user?.role === 'admin'` is field-level filtering inside the handler body to decide which fields to return after a successful update. Both authors AND admins (and presumably any other authenticated user) are permitted to perform the update; only the response shape differs. NOT a permission gate. → Tier 1 default; no Tier 2 escalation needed.

- characterDepthRoutes.js:88 — `function isAuthor(req) { return !!req.user; }` — used inside stripAuthorFields() for response-shape filtering, identical pattern. → Tier 1 default; no Tier 2 escalation needed.

- No authorize(['ADMIN']) calls added anywhere in CP6. Tier 2 disposition not invoked.

CP6 IS THE 6TH BACKEND DATA POINT IN STEP 3 PACING. CP1 70min / CP2 95min / CP3 85min / CP4 80min / CP5 95min / CP6 85min — mean ~85min ± 10min holds across 6 data points. Single-session execution at 6-for-6 single-session pattern (5-for-5 from CP1-CP5 + CP6 collapse from 2-session forecast). Trajectory: ~5-7 sessions remaining (CP7-CP11) at single-session pace; ~50% under original v2.23 §5.4 lock of ~14-16 sessions remaining post-CP5.

CP6 work stream complete (LOCKED v2.31 §5.48). 4 architectural firsts contributed: NEW topology variant (4th in registry); 2nd cumulative §5.21 mixed Tier 1+4 instance; 3rd consecutive frontend ideal state pattern-lock candidate; 1st anchor file with built-in reference shape at surface time. Cumulative AI POST reference model: 46 handlers across 14 files at uniform pattern. Surface-correction graduates to 23 cumulative data points.

### §5.49 — Sub-form (b) at scale pattern (NEW v2.31)

CP6 surfaced 3 sub-form (b) files in single CP (characters.js + character-clips.js + characterGenerator.js post-correction). Sub-form (b) = no middleware applied at handler level (no requireAuth, no optionalAuth, no aiRateLimiter; pure handler with implicit "anyone can call this" disposition). Pattern was rare across CP1-CP4 (CP4 had WP1 NO-OP first sub-form b instance); CP5 had 0 sub-form (b); CP6 has 3 in single cluster.

Discipline (LOCKED v2.31 §5.49):

- Sub-form (b) handlers default to Tier 1 (ADD shape application: ADD requireAuth)

- Sub-form (b) handlers with AI library imports default to Tier 1 + aiRateLimiter (ADD shape: ADD both requireAuth and aiRateLimiter)

- Sub-form (b) handlers with explicit "TESTING" or "DISABLED" banners (F-AUTH-4 obsolescence pattern) require banner removal in same commit as auth disposition application

- Surface report MUST identify sub-form (b) presence at §3 file inventory; per-handler tier classification accounts for ADD shape vs PROMOTE shape per file

Pattern-locking. CP6 establishes that sub-form (b) at scale (3 in single cluster) is no longer rare. Future CPs (CP7-CP11) surface should explicitly check for sub-form (b) at §3 inventory and apply ADD shape per §5.49 discipline. Cumulative sub-form (b) instances pre-CP7: 4 (CP4 ×1 + CP6 ×3).

### §5.50 — Surface-correction graduates to 23 cumulative data points (LOCKED v2.31 amendment)

Surface-correction methodology validated across 8 CPs / 7 backend CPs + 1 frontend Track 7 mini-CP: CP15 + CP1 + CP2 + CP3 + Track 7 mini-CP + CP4 + CP5 + CP6. Cumulative 23 data points at ~2-3 corrections per CP mean.

- CP6 contributed 4 corrections per closing report: characterGenerator.js no-middleware → optionalAuth (functional outcome identical: both routes converge on requireAuth); characterGenerator.js +1 missed AI POST (/rewrite-field); characterDepthRoutes.js -1 AI POST (/confirm is data persistence not AI); characterGenerationRoutes.js -1 handler -2 AI POSTs (only /generate calls anthropic via service); characterCrossingRoutes.js -1 handler; wantFieldRoutes.js -1 handler — net 0 handler delta (corrections balance out)

- Surface methodology produces ~95-98% accurate inventories under 102-handler load (CP6 most accurate execution-time correction ratio); methodology robust at scale

- Per-handler-block analysis (per §5.37) preferred over fixed-line-window grep — confirmed at CP6 execution: surface methodology produces handler counts within ±1-2 per file; AI POST identification produces ±1-2 per file; total handler count net 0 delta

- Future CP surface methodology continues per-handler-block analysis at scale (CP7 forecast 80-100 handlers; CP8-CP11 likely smaller)

### §5.51 — Item 16 response-shape vs permission-gate distinction (NEW v2.31)

CP6 D6 inspection produced first-time "no-escalation" result for Item 16 candidates. Architectural distinction locked:

- Permission gate (requires Tier 2 — requireAuth + authorize(['ADMIN'])): handler body refuses to proceed unless req.user has specific role. Pattern: `if (!req.user.groups.includes('ADMIN')) return 403;` OR `if (req.user.role !== 'admin') return 403;` — explicit gating logic that returns non-2xx response based on req.user state.

- Response-shape filtering (Tier 1 sufficient — post-promotion always-resolved): handler body proceeds for all authenticated users; req.user.role / req.user.groups inspection is used only to decide which fields to include in 2xx response (e.g., admins get audit fields, authors get author-only fields, others get baseline fields). Pattern: `const isAuthor = req.user?.role === 'author'; const fields = isAuthor ? AUTHOR_FIELDS : BASELINE_FIELDS;` — response-shape selection, NOT access control.

Discipline (LOCKED v2.31 §5.51):

- At Item 16 candidate inspection: examine handler body for explicit non-2xx return based on req.user state

- If non-2xx return found → Tier 2 escalation required (requireAuth + authorize(['ADMIN']) per §5.41)

- If only response-shape filtering found → Tier 1 default sufficient (post-promotion always-resolved)

- Document inspection result in CP closing report regardless of outcome — provides audit trail for future CPs and post-F-AUTH-1 review

CP6 inspection examples (LOCKED §5.51 reference patterns):

- characterRegistry.js:658 — response-shape filtering (Tier 1 sufficient)

- characterDepthRoutes.js:88 — response-shape filtering (Tier 1 sufficient)

- Future CPs (CP7-CP11) apply same inspection methodology when Item 16 candidates surface

### §5.52 — Integration test discipline post-Tier-1-promotion (NEW v2.31)

CP6 surfaced new architectural pattern: integration tests written pre-promotion that asserted against optionalAuth behavior (anonymous requests with 200 responses, partial req.user-null code paths) become factually false post-Tier-1-promotion (anonymous requests now return 401). CP6 discipline: update integration tests to expect 401 for anonymous requests against now-promoted routes.

- CP6 instance: tests/integration/storyEvalV2.integration.test.js — 4 anonymous-request tests against character-spark routes updated to expect 401 (truthful reflection of new contract)

Discipline (LOCKED v2.31 §5.52):

- At CP execution, search integration test files for assertions against pre-promotion routes (`expect(res.status).toBe(200)` paired with no Authorization header)

- Update assertions to `expect(res.status).toBe(401)` AND update test description to reflect new contract

- NOT a regression — these tests asserted against pre-Tier-1-promotion behavior; post-promotion truthful expectation is 401

- Document integration test updates in CP closing report

Pattern-locking. Future CPs (CP7-CP11) apply §5.52 discipline at execution. CP7 specifically should check tests/integration/ for storyEvalV2 + memoryRoutes + franchiseBrain integration tests; CP8 should check social-feeds integration tests; etc.

### §5.53 — CP7 closure: Storyteller + memories + franchiseBrain Q13 (LOCKED v2.32, COMPLETE)

CP7 closed at commit 10577813 on claude/f-auth-1-backup; auto-merged to origin/dev at 44474a08. Single squashed commit; same-turn force-with-lease push per §9.13 Rule 2; integrator auto-merge per §9.13 Rule 6 (29th cumulative same-turn push / auto-merge across F-AUTH-1 program).

Scope outcomes (D11 SCOPE-EXPANSION OUTLIER):

- 17 source files modified — far exceeds v2.23 §5.4 forecast of 8-10 files; driver was src/routes/memories/ sub-directory containing 8 sub-routers (engine.js alone 23 handlers, 11 unique AI POSTs)

- 153 handlers total; 148 promotions (5 CP-audited files NOT touched: sceneProposeRoute.js + episodeOrchestrationRoute.js + characterGrowthRoute.js + memories/index.js aggregator + memories/helpers.js utility per §9.13 Rule 6)

- 10 NEW test files at tests/unit/routes/* (with memories/* sub-files bundled into single memories-cluster-tier-promotion.test.js per D4 — clean per-sub-file describe blocks)

- 1 integration test updated: tests/integration/storyEvalV2.integration.test.js — 6 anonymous-request assertions converted to expect 401 per §5.52 discipline (cumulative 10 with CP6 4)

- Backend test suite: 1808 → 1965 passing (+157 tests vs +160-180 forecast — near lower edge; 0 regressions)

- All 13 lazy-noop residues eliminated (largest cleanup yet; CP6 had 7) per §5.8 universal discipline

- All 6 verification greps pass (G1-G6 per surface §15): zero optionalAuth survivors on writes; zero lazy-noop residue; uniform AI POST + aiRateLimiter pattern; F-AUTH-4 grep produced 3 G4 hits investigated and ruled FALSE POSITIVES (per §5.57 NEW); franchise-brain Tier 4 GETs req.user-free; zero authenticateToken survivors

- Single session execution despite 1.85x scope expansion — 6-for-6 single-session pattern → 7-for-7; ~85min raw within ~83min ±15min mean (CP1 70 / CP2 95 / CP3 85 / CP4 80 / CP5 95 / CP6 85 / CP7 ~85min raw; outlier marker for v2.32 §5.47 ongoing pacing analysis)

Tier disposition outcomes:

- Tier 1 (requireAuth) — 142 promotions: all writes + reads except franchiseBrain Q13 Tier 4

- Tier 4 (plain optionalAuth + PUBLIC) — 6 handlers: franchiseBrainRoutes.js GETs (5: /franchise-brain/entries + /franchise-brain/amber-activity + /franchise-brain/documents + /franchise-brain/documents/:id + /multi-product/all per surface §4 verification + G5 grep empty)

- Tier 1 PRESERVE — 0 handlers: no anchor file with built-in reference shape pre-existed in CP7-new (storyteller.js anchor had 0 reference handlers; all 37 promoted)

- Tier 2 (requireAuth + authorize(['ADMIN'])) — 0 handlers: surface §13 + execution-time re-verification confirmed zero Item 16 candidates

AI POST reference model 5th application (per §5.43 cumulative pattern; NEW v2.32 amendment):

- 47 AI POSTs added in CP7 alone (1 in storyteller.js + 1 in generate-script-from-book + 5 in storyEvaluationRoutes + 1 in eventGeneratorRoute + 1 in pdfIngestRoute + 2 in franchiseBrainRoutes + 11 in memories/engine + 4 in memories/core + 6 in memories/interview + 5 in memories/stories + 3 in memories/voice + 3 in memories/planning + 2 in memories/extras + 2 in memories/assistant)

- Cumulative post-CP7: ~92 handlers across ~30 files at uniform requireAuth + aiRateLimiter pattern (G3 grep: 46 hits across 13 CP7 files + 46 hits cumulative from CP1-CP6)

- Largest single-CP AI POST application by far (CP6 had 16; CP5 had 12; CP4 had 6; CP3 had 5)

franchiseBrain Q13 mixed Tier 1+4 disposition (per D2 — 3rd cumulative §5.21 instance; PATTERN-LOCK):

- 5 Tier 4 PUBLIC GETs in franchiseBrainRoutes.js: /franchise-brain/entries + /franchise-brain/amber-activity + /franchise-brain/documents + /franchise-brain/documents/:id + /multi-product/all (across 2 mount paths)

- 11 Tier 1 writes in franchiseBrainRoutes.js: 9 mutations at requireAuth + 2 AI POSTs at requireAuth + aiRateLimiter (/ingest-document + /push-from-page; the latter was D3 conversion site)

- PUBLIC comment block at imports per worldStudio.js + universe.js precedent (3rd cumulative instance)

- G5 grep confirms zero req.user reads in any Tier 4 GET handler body

- Pattern-locks §5.21 to "production-tooling-cluster default" — 3 cumulative instances sufficient threshold (worldStudio @ CP3 + universe @ CP6 + franchiseBrain @ CP7)

Mount-collision path-segment claim enumerations (per D8 — LARGEST mount-collision yet seen in F-AUTH-1):

- Collision A2 — /api/v1/memories with 7 routers + 8 sub-routers: storyEvaluationRoutes.js + sceneProposeRoute.js (CP-AUDITED) + characterGrowthRoute.js (CP6) + episodeOrchestrationRoute.js (CP-AUDITED) + eventGeneratorRoute.js + generate-script-from-book.js + memories/index.js aggregator (registers 8 sub-routers: assistant + core + engine + extras + interview + planning + stories + voice). All routers + sub-routers have DISJOINT path-segment claims; zero collision verified.

- Collision B — /api/v1/franchise-brain + /api/v1/multi-product (2 routers): franchiseBrainRoutes.js (16 handlers across 2 mount paths) + pdfIngestRoute.js (1 handler /ingest-pdf). Disjoint claims; zero collision.

CP7 ARCHITECTURAL FIRSTS — 12 contributing to v2.32 amendments:

- 1. LARGEST mount-collision yet (Collision A2 with 7 routers + 8 sub-routers; eclipses CP2 episodes-cluster)

- 2. 3rd cumulative §5.21 mixed Tier 1+4 instance (franchiseBrainRoutes.js); pattern-lock to production-tooling-cluster default

- 3. 5th application of AI POST reference model with largest single-CP delta (47 in CP7; cumulative ~92)

- 4. 4th consecutive frontend ideal state (CP4+CP5+CP6+CP7); pattern-lock at production-tooling-cluster default

- 5. First CP since CP3 with zero sub-form (b) presence (storyteller/memories/franchise are mature subsystems)

- 6. Cleanest hygiene surface yet — zero F-AUTH-4 obsolescence (3 G4 false positives in API key error strings + system prompt content; first §5.57 false-positive discipline application)

- 7. Zero F-AUTH-5 hits + zero §5.51 Item 16 candidates (3rd CP at zero candidates per methodology lock)

- 8. First detected legacy authenticateToken usage in CP-zone work (franchiseBrainRoutes.js:560 → requireAuth + aiRateLimiter conversion; D3)

- 9. Largest lazy-noop residue cleanup yet (13 files; CP6 had 7)

- 10. Cross-coupling discovered (memories/engine.js:23 imports from franchiseBrainRoutes.js); single squashed commit eliminates inconsistent-state window

- 11. Custom rate-limiter preservation (memories/assistant.js preserves bespoke assistantLimiter alongside aiRateLimiter; defer-to-Track-8 consolidation)

- 12. Scope-expansion outlier (1.85x; forecast 8-10/80-100 vs actual 17/153)

CP7 IS THE 7TH BACKEND DATA POINT IN STEP 3 PACING. CP1 70min / CP2 95min / CP3 85min / CP4 80min / CP5 95min / CP6 85min / CP7 ~85min raw — mean ~85min ± 10min holds across 7 data points. Single-session execution at 7-for-7 single-session pattern (6-for-6 from CP1-CP6 + CP7 collapse from 2-3 session forecast despite 1.85x scope expansion). Trajectory: ~3-5 sessions remaining (CP8-CP11) at single-session pace; ~50% under original v2.23 §5.4 lock of ~8-10 sessions remaining post-CP6.

CP7 work stream complete (LOCKED v2.32 §5.53). 12 architectural firsts contributed: largest mount-collision, 3rd cumulative §5.21 instance (pattern lock), 5th + largest cumulative AI POST application, 4th consecutive frontend ideal state (pattern lock), zero sub-form (b), cleanest hygiene surface, zero Item 16 candidates, legacy authenticateToken conversion, largest lazy-noop cleanup, cross-coupling discipline, custom rate-limiter preservation, scope-expansion outlier methodology.

### §5.54 — Cross-coupling commit-ordering signal (NEW v2.32)

CP7 surfaced architectural pattern: when CP-zone files import from each other, single squashed commit eliminates inconsistent-state window during integration. memories/engine.js:23 imports buildKnowledgeInjection + getTechContext from franchiseBrainRoutes.js — engine depends on franchiseBrainRoutes (downstream dependency, NOT circular import).

Discipline (LOCKED v2.32 §5.54):

- Surface report MUST identify cross-coupling between CP-zone files (grep imports across CP-zone files at §3 inventory)

- When cross-coupling found, single squashed commit is REQUIRED (not just preferred) — splitting CP would create inconsistent-state window where one file references the other in mid-migration state

- Document cross-coupling in CP closing report regardless of CP composition decision

- CP7 instance: memories/engine.js → franchiseBrainRoutes.js downstream dependency; single CP7 squash eliminated inconsistent-state risk

Pattern locks discipline for CP8-CP11 + post-F-AUTH-1 work. When surface report identifies cross-coupling, CP composition (single vs split) is constrained by integration-safety, not just pacing preference.

### §5.55 — Custom rate-limiter preservation discipline (NEW v2.32)

CP7 surfaced custom rate-limiter pattern: memories/assistant.js had bespoke assistantLimiter pre-CP7. CP7 PROMOTE shape application added canonical aiRateLimiter alongside (not replacing) the existing assistantLimiter, producing double-rate-limiting where the more restrictive limiter dominates.

Conservative discipline (LOCKED v2.32 §5.55):

- Custom rate-limiters in CP-zone files are PRESERVED alongside aiRateLimiter; do NOT strip during CP migration

- Rationale: custom limiters likely have semantically different limits (per-conversation, per-user-tier, etc.) than generic aiRateLimiter; stripping risks regressing behavior parity

- Double-rate-limiting is harmless — both limiters reject excess with 429; the more restrictive fires first

- Consolidation deferred to Track 8 (post-F-AUTH-1) OR a dedicated rate-limiter consolidation pass — NOT at CP scope

- Document custom rate-limiter preservation in CP closing report when present

CP7 instance: memories/assistant.js preserves assistantLimiter alongside aiRateLimiter (handler signature now: requireAuth + assistantLimiter + aiRateLimiter, async). Future Track 8 cleanup pass can investigate consolidation; pre-Track-8, behavior parity is preserved.

Future CPs (CP8-CP11) apply §5.55 discipline. If custom rate-limiters surface in CP zone, preserve alongside aiRateLimiter; defer to Track 8.

### §5.56 — Scope-expansion outlier methodology (NEW v2.32)

CP7 produced 1.85x scope expansion (forecast 8-10 files / 80-100 handlers vs actual 17 files / 153 handlers). Surface methodology correctly identified the variance at surface time (NOT execution time); D11 adjudication selected Option A (oversized single CP) over Option B (split into CP7-A + CP7-B). Methodology validated.

Outlier marker discipline (LOCKED v2.32 §5.56):

- When surface-correction reveals >1.5x scope variance from v2.23 §5.4 forecast, surface report flags D11 SCOPE-EXPANSION OUTLIER for adjudication

- Adjudication selects between: Option A (oversized single CP — preserves architectural unity, accepts pacing outlier) or Option B (split into smaller CPs — preserves single-session pace, requires careful cross-coupling handling)

- Default selection criteria: Option A when cross-coupling exists OR when architectural unity (single §5.21 mixed-tier instance, single AI POST reference application) would be split unnaturally. Option B when CPs are independent and can be cleanly separated.

- v2.x §5.4 retroactive amendment captures actual scope (vs original forecast) for future planning calibration

- v2.x §5.47 pacing data point includes outlier marker (separate from mean calculation OR contributing to wider variance band)

CP7 outcome (Option A selected): single squashed commit; ~85min raw within ±15min mean band despite 1.85x scope; cross-coupling discipline validated. v2.32 §5.4 retroactive correction marked.

Pattern locks methodology for CP8-CP11 + future audit handoffs. v2.23 §5.4 forecasts are surface-correctable at planning revisions; surface methodology continues to take precedence over planning-phase forecasts when variance exceeds 1.5x.

### §5.57 — F-AUTH-4 grep false-positive discipline (NEW v2.32)

CP7 surfaced first instance of F-AUTH-4 multi-line obsolescence grep producing FALSE POSITIVES. G4 grep at memories/assistant.js produced 3 hits — all in non-auth contexts: ANTHROPIC_API_KEY error message strings ("API key may be missing or expired") + system prompt content mentioning "A/B testing". None were auth obsolescence markers (tolerat / expir / weakened / TESTING in disabled-auth context).

Per-handler-block analysis disambiguation (LOCKED v2.32 §5.57):

- F-AUTH-4 grep matches `tolerat|expir|missing token|weakened|TESTING` keywords across CP zone files

- AI POST contexts (Anthropic API integrations + system prompts) frequently contain these tokens in literal string content (error messages, prompt templates) — NOT as auth obsolescence markers

- Per-handler-block analysis (per §5.37) required to disambiguate: examine the LINE CONTEXT of each grep hit

- Auth-obsolescence markers: appear as comments above route declarations OR inside auth declarations (`requireAuth({ tolerantMode: true })` / `optionalAuth({ tolerateExpiredTokens: true })` / banner-comments above sub-form (b) handlers)

- False-positive markers: appear inside literal string content (error messages, system prompts, AI prompt templates)

- Document false-positive triage in CP closing report — confirm each hit is investigated and ruled

CP7 instance (3 false positives at memories/assistant.js): L249 "API key may be missing or expired" (error message), L533 same pattern, L1805 system prompt content "A/B testing". All within string literals; none were auth obsolescence markers; no action taken.

Future CPs (CP8-CP11) apply §5.57 discipline. F-AUTH-4 grep continues to be valuable but requires per-handler-block triage to filter false positives in AI POST contexts.

### Track 7 — UNCLEAR-A reconciliation (NEW v2.0, runs in parallel with Step 3)

71 UNCLEAR-A sites: GETs on mixed-verb routes (episodes, storyteller, shows, characters, wardrobe, onboarding, story-health). Each one's correct disposition (PUBLIC vs BUG) depends on which Step 3 per-route classification gets applied to the corresponding backend route.

- Step 3 sweep classifies each backend mixed-verb route as either: (a) PUBLIC published-only data (gets // PUBLIC: comment + degradeOnInfraFailure flag), or (b) auth-required (gets requireAuth).

- Track 7 mirrors that classification on the frontend: for each Step 3 (a) classification, the corresponding frontend GET stays as raw fetch with no auth (PUBLIC); for each (b), the GET migrates to apiClient.

- Track 7 does not run independently — it runs in parallel with Step 3, file-by-file, as Step 3 classifies each route. This avoids re-doing Track 7 work if Step 3 reclassifies later.

UNCLEAR-B (144 sites in 32 files): per Track 5's spot-check, ~80% are Path D (already covered by Track 4) and ~20% are hidden BUGs (covered by Track 6). No separate Track 8. UNCLEAR-B resolves naturally as Tracks 4 and 6 land. EpisodeDetail.jsx is the clearest example: mixed-paradigm with hidden bare-fetch BUGs; treated as a Track 6 file when its turn comes.

### Verification (G3 + G4)

- After all six implementation tracks (1, 2, 3, 4, 6, 7): zero imports of authHeader (Path A), zero local authHeaders() helpers (Path C), zero inline Bearer ${token} (Path D) — except the locked BookEditor:181 keepalive exception, zero BUG-class raw fetches (Track 6), zero unresolved UNCLEAR-A (Track 7). Verification greps confirm.

grep -rn "authHeader\b" frontend/src/ | grep -v "authHeaders" | grep -v "test\.\|\.test\."

- Expected output: zero matches. (Production code; test files may contain "authHeader" in test descriptions and are excluded.)

grep -rn "Bearer \${" frontend/src/ | grep -v "src/services/api.js" | grep -v "BookEditor.jsx:55" | grep -v "WriteMode.jsx:980" | grep -v "WriteMode.jsx:1145" | grep -v "WriteModeAIWriter.jsx:281" | grep -v "AppAssistant.jsx:239" | grep -v "useStoryEngine.js:358" | grep -v "test\."

- Expected output: zero matches. The seven allowlisted locations are: (a) src/services/api.js — the apiClient request interceptor itself; (b) BookEditor.jsx:55 — the locked CZ-5 keepalive exception; (c) WriteMode.jsx:980 — locked streaming SSE exception (voice-to-story, v2.10); (d) WriteMode.jsx:1145 — locked streaming SSE exception (story-continue, v2.10); (e) WriteModeAIWriter.jsx:281 — locked streaming exception (rewrite-stream, v2.18 added in CP11); (f) AppAssistant.jsx:239 — locked streaming exception (chat-stream, v2.18 added in CP11); (g) useStoryEngine.js:358 — locked streaming exception (story-tasks-stream, v2.19 added in CP12 per Pattern G default-on-matching-precedent discipline).

grep -rn "fetch(" frontend/src/ | wc -l

- Expected: drops from 627 (initial) to count of intentionally-public reads only (PUBLIC class — currently 5 confirmed, may grow as Track 7 reclassifies UNCLEAR-A) PLUS the six locked exceptions (BookEditor.jsx:55 keepalive + WriteMode.jsx:980 + WriteMode.jsx:1145 + WriteModeAIWriter.jsx:281 + AppAssistant.jsx:239 + useStoryEngine.js:358 streaming) = 11 minimum.

Sharper file-scoped variant (locked v2.10 from CP3 verification): grep -nE '^\s*[^/]*\bfetch\(' <file> — anchors to start-of-line plus excludes comment-prefixed matches. The default grep -cE 'fetch\(' counts comment hits too; the sharper form is more precise for per-file verification during CP execution. Use the sharper form in CP reports.

- Authenticated request via apiClient succeeds and req.user populated server-side.

- Mid-session token expiry: apiClient interceptor sees AUTH_INVALID_TOKEN, refreshes silently, request continues. User does not see a logout.

- Token deletion: apiClient interceptor sees AUTH_REQUIRED, redirects to login.

- AUTH_INVALID_FORMAT and AUTH_GROUP_REQUIRED responses do NOT trigger session-redirect logic; surfaced inline.

- SceneSetsTab.jsx full exercise on dev: every CRUD operation succeeds authenticated, 401s unauthenticated. (Single-file regression check given the 64-site density.)

- FranchiseBrain.jsx full exercise: every entry mutation succeeds authenticated, 401s unauthenticated. F34 closes at this checkpoint.

### Scope acknowledgment — Track 5 changed the math (v2.0)

Pre-Track-5 v1.9 scope: ~134 site migrations. Post-Track-5 v2.0 scope: ~556 sites total (~134 paradigm + ~345 BUG + ~71 UNCLEAR-A + ~140 UNCLEAR-B Path-D resolutions absorbed by Track 4). Roughly 4× the v1.8 estimate. Track 5 was the data we should have had before locking scope at v1.9; v1.9's number was incomplete because the four-path inventory found four paradigms but did not catalog raw fetches against backend routes. v2.0 corrects.

This is multi-week work, not multi-day. Locked at v2.0: multi-week timeline acknowledged. If F-AUTH-1 needs to ship by a specific date, the timeline must shape the pace; otherwise Pace 2 batched checkpoints (see below) is the locked working model.

### Pace 2 — Batched with checkpoints (LOCKED v2.0)

Each track lands as multiple commits, with explicit checkpoints between commits. The pace is not "sprint through 556 sites," it's "land a commit, observe, approve, push backup, repeat."

- Track 1 (apiClient interceptor update): 1 commit. Reviewed and approved before Track 1.5 begins.

- Track 1.5 (frontend test scaffolding): 1 commit. Vitest config + jsdom + 5 interceptor tests. Reviewed and approved before Track 1.6 begins.

- Track 1.6 (backend requireAuth split): 1 commit. Middleware change + tests. Reviewed and approved before Track 2 begins.

- Track 2 (Path A migration): 1-2 commits. Reviewed and approved before Track 3.

- Track 3 (Path C consolidation + migration): 2-3 commits. Each stage of consolidation reviewed.

- Track 4 (Path D inline cleanup): 1-2 commits. Reviewed.

- Track 6 (BUG migration): file-by-file in priority order. SceneSetsTab.jsx is one commit. FranchiseBrain.jsx is one commit. Each high-density file reviewed and approved before the next file starts. Lower-density files may batch (e.g., 5-10 small files per commit) but only after the high-density tracks have established the migration pattern.

- Track 7 (UNCLEAR-A reconciliation): runs in parallel with Step 3, classification by classification.

- Estimated commit count for Step 6b alone: 12-20. Each commit gets backup-pushed per §9.13 Rule 2 after my approval.

Failure mode Pace 2 prevents: a regression introduced at site #347 that doesn't surface until G4 dev exercise, by which point 200 sites have changed and the bisection is hard. Pace 2 means a regression surfaces at the file that introduced it.

### What happens if Track 6 (or any later track) reveals new scope

Locked discipline (matches v1.7 §9.13 framing): surface the finding, lock the scope decision, amend the fix plan, then proceed.

- Example: Track 6 file-by-file work reveals a fifth auth paradigm not seen in inventories — surface immediately, lock scope, amend §4.6, proceed.

- Example: a BUG-class fetch can't cleanly migrate to apiClient (different request signature, special response handling) — surface, decide whether to migrate-anyway-with-adapter or document-as-exemption, amend, proceed.

- Example: regression in dev exercise — roll back, surface, fix at source, re-do affected commit(s), proceed.

- What does NOT happen: silent scope expansion, surprise bug-fixes mid-track, "while we're here" cleanups outside the locked spec.

### F-Auth-4 — out-of-scope (LOCKED, unchanged from v1.8)

- Decision D20 — src/middleware/jwtAuth.js is a separate verification path (custom JWT via TokenService, not Cognito). Different req.user shape (adds role, tokenType, source, expiresAt). Different helpers (requireRole has no equivalent in auth.js). 9 production mounts: routes/auth.js:10 (/logout, /me) and routes/compositions.js:20 (composition CRUD + admin gates).

- jwtAuth.js stays as-is in F-AUTH-1. Folding it into Step 6b means rewriting two architecturally distinct auth systems in one PR — scope explosion, not consolidation.

- Frontend changes apply to all auth-injection paths regardless of which backend module the responses came from. apiClient interceptor handles AUTH_REQUIRED and AUTH_INVALID_TOKEN regardless of source.

- Architectural follow-up (out of F-AUTH-1 scope): does Prime Studios want two auth modules long-term? jwtAuth.js looks like a legacy or special-case path predating the Cognito migration. Worth a separate audit after F-AUTH-1 ships.

### F-Auth-5 — current behavior

decisionLogs.js:22 reads req.user.sub directly. Other call sites read req.user.id — the value the auth middleware maps from sub onto the user object. Both resolve to the same Cognito subject identifier today, but the contract has drifted: one file consumes a raw claim, the rest consume the middleware-mapped field. The moment the middleware mapping changes (e.g., to a numeric internal ID, or to a UUID indirection layer for a multi-tenant change), decisionLogs.js silently writes the wrong value with no test failure.

### F-Auth-5 — why fold in here

- Step 6 is already the auth-contract reconciliation step. F-Auth-4 Path 1 is unifying requireAuth and authenticateToken; F-Auth-5 is unifying user-object access. Same conceptual fix.

- The change is one line. PR-scope cost is negligible.

- Deferring it as a one-line follow-up PR has higher operational cost than fixing it now (the follow-up tends to never get scheduled).

### F-Auth-5 — fix

- At decisionLogs.js:22, replace req.user.sub (or req.user?.sub) with req.user?.id to preserve the optional-chaining style the rest of the codebase uses.

- Pre-flight (§5.1) requires a fresh grep for any other call site reading req.user.sub directly. Codebase uses optional chaining; the literal-form grep returns 0 hits and is incorrect. Use the regex form:

grep -rnE "req\.user\??\.sub" src/

- Pre-flight inventory (preserved here as canonical scope) found 6 sites: src/controllers/cursorPathController.js:22, iconCueController.js:22, musicCueController.js:20, productionPackageController.js:22, src/routes/decisionLogs.js:22, src/routes/thumbnails.js:80. Replace req.user?.sub with req.user?.id at all 6.

- Special case — thumbnails.js:80 currently reads const userId = req.user?.sub || req.user?.id || 'system'; inside a route gated by authenticateToken at :76. The fallback chain is dead code (req.user is guaranteed non-null when :80 executes). Replace the entire line with const userId = req.user.id; — drop the fallback per Decision §11 #2.

- For each match outside test files: replace req.user?.sub with req.user?.id. Document any intentional req.user.sub use with a // PUBLIC: justifying comment if one exists (none expected from pre-flight).

### F-Auth-5 — verification

- Authenticated POST to a /decision-logs route succeeds and the persisted user_id field matches the value other authenticated routes write for the same user.

- Authenticated POST to /thumbnails/:id/publish succeeds and persists user_id (not "system").

- Verification grep returns zero matches for req.user?.sub or req.user.sub outside test fixtures and middleware/auth.js itself:

grep -rnE "req\.user\??\.sub" src/

### Verification

- Open BookEditor, edit content, navigate away → save fires via fetch+keepalive, 200 response, edits persist.

- Open authenticated session, manually delete token from storage, attempt write → interceptor sees AUTH_REQUIRED, redirects to login.

- Open authenticated session, manually corrupt token, attempt write → interceptor sees AUTH_INVALID_TOKEN, attempts refresh.

# 5. Execution Sequence

All six steps land in one PR. Within the PR, the work order matters because it minimizes the time the codebase spends in a half-fixed state during local development and review.

## 5.1 Pre-flight verification (before writing any code)

Pre-flight produces a complete, current inventory. v8 closed May 1, 2026 — any code added since then is not in the audit. Pre-flight catches it.

### Pre-flight checklist

- Spot-check 3 v8 file:line references to confirm the codebase still matches the audit:

  - middleware/auth.js:13–22, :44–46, :164–168, :256–293

  - app.js:364

  - episodeOrchestrationRoute.js:135 (and confirm the write at :220)

- Run the master grep for sub-form (a). Capture full output. This is the inventory step 3 must address.

grep -rn "optionalAuth" src/routes/ src/app.js src/middleware/ | sort

- Run the sub-form (b) grep — files in src/routes/ that do NOT import auth middleware:

for f in src/routes/*.js; do grep -l "require.*middleware/auth" "$f" >/dev/null || echo "NO AUTH IMPORT: $f"; done

- Run the sub-form (c) grep — explicit optionalAuth on mutation routes:

grep -rnE "router\.(post|put|patch|delete).*optionalAuth" src/routes/

- Confirm Cognito env vars are set in dev and prod environments via PM2 runtime env (not interactive shell). Step 1 (F-Auth-2) WILL boot-fail any environment missing them. CONFIRMED at G1: dev and prod both have real Cognito identifiers; see Decision §9.10 re: pool unification.

- Identify the frontend interceptor file. Confirm the strings it differentiates on. Save this as the contract Step 6 reconciles against.

- Pull a list of all routes currently using optionalAuth that are genuinely public reads. Pre-tag them as exemptions so step 3 does not blanket-swap them.

### Pre-flight deliverables

- Inventory file: src/routes/ optionalAuth surface count + file:line list.

- Sub-form (b) file list (routes with no auth import).

- Sub-form (c) file:line list (explicit optionalAuth on mutations).

- Genuine-public-route exemption list with reasoning per route.

- Frontend interceptor contract reference (file:line + string list).

- Env-var confirmation per environment.

## 5.2 Implementation order within the PR

- Step 6a (CZ-5 only) — migrate sendBeacon → fetch+keepalive in BookEditor.jsx. This change is independent and can be merged to the working branch first; it does not break anything when sendBeacon is no longer the path.

- Step 2 (F-Auth-3) — refine optionalAuth error handling. Independent of route changes; safer to land before the sweep so any remaining optionalAuth routes get the better error semantics during the brief overlap window.

- Step 6b (F-Auth-4 Path 1) — reconcile the requireAuth/authenticateToken duplication. Land before the sweep so the frontend interceptor contract is stable when sweep traffic shifts.

- Step 6c (F-Auth-5) — replace req.user.sub with req.user.id at decisionLogs.js:22 and any other call sites pre-flight identifies. Independent of route changes; safe to land any time during Step 6.

- Step 3 (Sweep a) — biggest mechanical change. Land in dependency order: per-route requireAuth additions FIRST, then remove the global optionalAuth at app.js:364. This avoids a brief window where neither layer guards the routes.

- Step 4 (Sweep b) — add requireAuth to outfitSets.js + episodes.js:101/109/117.

- Step 5 (Sweep c) — replace optionalAuth at episodeOrchestrationRoute.js:135.

- Step 1 (F-Auth-2) — boot-fail on missing env vars. LAST. Reasoning: this change is the most disruptive in environments where env vars may be misconfigured. Landing it last means every other change in the PR is already exercised against working auth before the boot-fail check is added.

Why F-Auth-2 lands last F-Auth-2 boot-fails any environment with missing or placeholder Cognito env vars. If it lands first, every step after it depends on those env vars being set in every dev/test environment. By landing last, the rest of the PR has already been exercised in those environments under real auth. Pre-flight (§5.1) confirms env vars are set; F-Auth-2 last is belt-and-suspenders.

## 5.3 PR mechanics

- Single PR title: "F-AUTH-1: codebase-wide auth bypass on writes — six-step coordinated fix"

- PR description references audit handoff v8 §4.1 and §12.

- PR description includes the pre-flight inventory as collapsed sections.

- Each commit corresponds to one step (or substep). Bisectability matters if a regression surfaces.

- Branch coordination: confirm with the second developer (VS Code collaborator) before opening the PR. F-AUTH-1 touches middleware/auth.js, app.js, and a wide swath of src/routes/ — merge conflicts are likely if other branches are in flight.

- CI must pass before merge. If the test suite does not currently exercise auth on the swept routes, add tests as part of the PR — at minimum, one authenticated + one unauthenticated test per sub-form.

# 6. Deployment Plan — Gate-Driven Sequence

primepisodes.com has no real-user traffic at the time this plan locks. The deploy plan therefore does not use a calendar window — it uses a gate sequence. Each gate must pass before the next begins. There is no pressure to ship by a date; there is pressure to not skip a gate.

Why gates instead of a calendar A calendar deploy window is a tool for minimizing user impact during a risky change. With no real users, there is no user impact to minimize — the calendar window solves a problem you don’t have. What you DO have: a codebase that has accumulated months of untested assumptions (the audit found 269 P0 bugs) and a fix that touches authentication on every write route. The gates exist to prevent the temptation to skip discipline because "no one will see it." The gates are not theater. F-AUTH-1 is the first fix; how it ships sets the precedent for every fix that follows.

## 6.1 The Seven Gates

| Gate | Name | What must be true before proceeding |
| --- | --- | --- |
| G1 | Pre-flight complete | All §5.1 inventory deliverables produced and reviewed: optionalAuth surface inventory, sub-form (b) file list, sub-form (c) file:line list, exemption list with reasoning, frontend interceptor contract reference, env-var confirmation, req.user.sub grep results (F-Auth-5). Drift from v8 file:line references documented or absent. Branch coordination with second developer confirmed. |
| G2 | Implementation complete | PREREQUISITE (G1 verified): Cognito runtime env vars confirmed by Evoni via PM2 runtime env on dev and prod EC2 boxes. Both COGNITO_USER_POOL_ID = us-east-1_mFVU52978 and COGNITO_CLIENT_ID = lgtf3odnar8c456iehqfck1au, real (non-placeholder) values, set in PM2 process env (not interactive shell). Note: dev and prod currently share one Cognito pool — see Decision §9.10. Then: all six steps coded per §5.2 order. Each commit corresponds to one step or substep (bisectability). CI passing. PR opened. PR description references audit handoff v8 §4.1 + this fix plan and includes the pre-flight inventory in collapsed sections. |
| G3 | Self-review passed | Every commit in the PR read end-to-end. Test coverage minimum: one authenticated + one unauthenticated test per sub-form. F-Auth-5 has its specific test (decisionLogs write persists matching user_id). Frontend interceptor handles AUTH_REQUIRED and AUTH_INVALID_TOKEN as distinct paths. |
| G4 | Dev verified + soak | Backend deployed to dev. Boot tested with valid env vars (succeeds), missing env var (boot-fails with named error), placeholder env var values (boot-fails). Frontend deployed to dev (interceptor contract update). Full §7 verification checklist run end-to-end on dev. Every checkbox confirmed. Boot/restart cycle exercised (kill the process, confirm clean restart, confirm auth still works). 2-hour soak on dev — server stays up, no error log spam, no unexpected restarts. You are reachable for alerts during the soak window. Note: G4 absorbs the staging-soak responsibility from the original three-environment plan; Prime Studios infra is intentionally dev + prod only (Decision §9.9). |
| G5 | Prod cutover | Frontend deployed to prod, then backend. You spend 30 focused minutes exercising the app: log in, write to a Stats route, write to a wardrobe route, write to a franchise-brain route (this is where F34 closes), write something in BookEditor and navigate away (CZ-5 path), write to a /decision-logs route (F-Auth-5 path). Confirm boot logs are clean. No errors visible in app or server logs. |
| G6 | Post-deploy soak | Server stays up overnight. Next morning, exercise the app again — same surfaces as G5. If clean, declare F-AUTH-1 closed. Tier 1 fix queue (F-App-1, F-Stats-1, F-Ward-1, F-Reg-2, F-Ward-3, F-Sec-3, F-Franchise-1) is now unblocked. |

## 6.2 Pre-G5 readiness check

Before opening the prod cutover at G5, run this short list. If any item fails, do not proceed to G5. Return to the appropriate earlier gate.

- Cognito env vars confirmed set in prod (verified once during pre-flight; re-confirmed here because Step 1 / F-Auth-2 boot-fails any env without them).

- Second developer confirmed not mid-deploy. No conflicting branch in flight.

- Frontend build deployed to prod is using the updated interceptor contract from Step 6b. Hard requirement — backend cutover before frontend cutover ships AUTH_REQUIRED responses to a frontend that does not know how to handle them.

- Rollback procedure (§8) read and understood. Revert path is one command, not a discovery exercise.

- You have a clear 30 minutes. Phone on do-not-disturb. No meetings. No "I can do this between calls."

## 6.3 What to watch during deploy

Without real-user traffic, the standard "watch the metrics" framing does not apply. There is no 401-rate-spike to investigate. There is no user-write-success-rate dashboard. What you watch instead:

- Boot logs — server starts cleanly. No exceptions during module load. F-Auth-2 emits no warnings (because env vars are set). No "Token verification failed" loops in the first minute.

- App exercise — every surface listed in G5 returns 200 under your own authenticated session. Every unauthenticated test (open an incognito window, attempt a write) returns 401 with AUTH_REQUIRED.

- BookEditor exercise — write content, navigate away, return. Edits persist. Network log shows fetch with keepalive: true (not sendBeacon) carrying the Authorization header.

- Frontend interceptor exercise — manually delete the auth token from browser storage, attempt a write. Interceptor sees AUTH_REQUIRED, redirects to login. Manually corrupt the token, attempt a write. Interceptor sees AUTH_INVALID_TOKEN, attempts refresh.

- Server logs during exercise — no error-level entries from middleware/auth.js. F-Auth-3 503 path is not firing (Cognito is reachable). No console.warn floods.

- Overnight (G6) — server uptime metric matches deploy time the next morning. No unexpected restarts. No memory growth visible in process metrics.

What you are NOT watching for No 401 rate spike to investigate (no traffic to produce one). No write success rate dashboard (no traffic). No 503 rate from F-Auth-3 (Cognito-down detection only fires under load that you do not have).

## 6.4 If a gate fails

- G1 fails — pre-flight surfaced drift, missing env vars, or branch conflict. Resolve before G2. Drift may require updating this fix plan to v1.6+.

- G2 fails — implementation incomplete or CI red. Stay at G2. Do not let "I can fix this in dev soak" pressure push you forward.

- G3 fails — self-review found a bug or a missing test. Return to G2. Add the test, fix the bug, re-run CI.

- G4 fails — boot-fail when it should succeed, unexpected §7 checklist behavior, server unstable during 2-hour soak, or memory growth during soak. Diagnose. If code, return to G2. If env-specific, fix in place. Re-run all of G4 (including a fresh 2-hour soak) before proceeding to G5 — do not partial-credit a soak that was interrupted by a code change.

- G5 fails — prod cutover surfaces an issue. Roll back per §8. Do not try to fix forward in prod. Return to G2 or G4 depending on cause.

- G6 fails — overnight soak revealed instability. Roll back. Same rule: do not fix forward in prod.

# 7. Post-Deploy Verification Checklist

Run this checklist on dev (during G4) and again on prod after G5 cutover.

## 7.1 Auth module integrity

- ☐ Server boot with valid Cognito env vars — succeeds.

- ☐ Server boot with missing COGNITO_USER_POOL_ID — fails immediately with named error.

- ☐ Server boot with missing COGNITO_CLIENT_ID — fails immediately with named error.

- ☐ Server boot with placeholder env var values — fails immediately with named error.

## 7.2 optionalAuth error semantics (F-Auth-3)

- ☐ optionalAuth route (default options), no Authorization header — req.user = null, no log spam.

- ☐ optionalAuth route, malformed token — req.user = null, single quiet log only.

- ☐ optionalAuth route (default options), simulated Cognito unavailability — 503 response with code AUTH_SERVICE_UNAVAILABLE, structured error log fired ("[F-Auth-3] cognito_unreachable").

- ☐ optionalAuth route configured with degradeOnInfraFailure: true (manuscript-export.js GETs, press.js GETs), simulated Cognito unavailability — request still returns the public content (not 503), structured error log STILL fires.

- ☐ Step 2 unit tests pass (4 cases per §4.2): no header / token rejected / infra error default / infra error with flag.

## 7.3 Sweep (a) — optionalAuth → requireAuth

- ☐ storyteller.js write routes: authenticated request 200, unauth 401.

- ☐ characterRegistry.js writes: authenticated request 200, unauth 401.

- ☐ characterRegistry.js author-only fields: authenticated request as author succeeds; previously-broken because req.user was null is now functional.

- ☐ evaluation.js:587 (Stats save): authenticated 200, unauth 401.

- ☐ careerGoals.js mutation routes: authenticated 200, unauth 401.

- ☐ uiOverlayRoutes.js mutation routes: authenticated 200, unauth 401.

- ☐ calendarRoutes.js mutation routes: authenticated 200, unauth 401.

- ☐ franchiseBrainRoutes.js all 10 mutation routes: authenticated 200, unauth 401. F34 closed.

- ☐ wardrobe.js:895 (/select), :970 (/purchase): authenticated 200, unauth 401.

## 7.4 Sweep (b) — no-auth-declaration routes

- ☐ outfitSets.js all 5 routes: authenticated 200, unauth 401.

- ☐ episodes.js:101, :109, :117: authenticated 200, unauth 401.

## 7.5 Sweep (c) — explicit optionalAuth on mutations

- ☐ episodeOrchestrationRoute.js:135: authenticated 200 (writes orchestration_data at :220), unauth 401.

## 7.6 Step 6 — CZ-5 + F-Auth-4 + F-Auth-5

- ☐ BookEditor.jsx beforeunload save: triggers fetch+keepalive (not sendBeacon), Authorization header present, 200 response, edits persisted on next load.

- ☐ Frontend interceptor sees AUTH_REQUIRED → redirects to login.

- ☐ Frontend interceptor sees AUTH_INVALID_TOKEN → attempts refresh, then redirects on failure.

- ☐ Mid-session token expiry: refresh path works, user is not silently logged out.

- ☐ Authenticated POST to /decision-logs persists user_id matching the value other authenticated routes write for the same user (F-Auth-5).

- ☐ grep "req\.user\.sub" src/ returns zero matches outside middleware/auth.js itself and test fixtures (F-Auth-5).

## 7.7 Regression checks

- ☐ App.js no longer applies global optionalAuth (line 364 confirmed removed).

- ☐ characterRegistry.js no-op fallback at lines 12–22 confirmed removed.

- ☐ No bare optionalAuth on a write route without a // PUBLIC: justifying comment.

- ☐ Pre-existing read-only routes still work for unauthenticated users (where applicable per exemption list).

# 8. Rollback Plan

Rollback is a single revert of the merge commit. Because all six steps land in one PR, rollback restores the entire pre-fix state — including the F34 exposure. This is acceptable because the alternative (partial rollback) leaves the codebase in a half-fixed state v8 §4.1 explicitly warns against.

## 8.1 Rollback triggers

- Production write success rate drops more than 2% on any route within 30 minutes of deploy and the cause is auth-related.

- BookEditor beforeunload save failure rate measurably increases.

- Boot failure on any production instance not caused by missing env vars (i.e., a code bug).

- Frontend interceptor regression — users being silently logged out, mid-session refresh broken.

## 8.2 Rollback procedure

- Revert the merge commit on the deploy branch.

- Redeploy backend to prod.

- Redeploy frontend to prod (the old frontend works against the rolled-back backend; the new frontend will work against either, but rolling back both is cleaner).

- Confirm metrics return to pre-deploy baseline.

- Open an incident review. Identify which of the six steps caused the regression. Re-plan the next attempt.

## 8.3 What rollback restores

- F-AUTH-1 sweep undone — all sub-forms back to optionalAuth or no-auth.

- F34 exposure restored. Mitigation: rollback should be brief; do not soak in the rolled-back state.

- F-Auth-2 boot-fail removed.

- F-Auth-3 error semantics reverted.

- CZ-5 sendBeacon restored. BookEditor data-loss path reopened.

- F-Auth-4 reconciliation/documentation undone.

# 9. Decisions Log (all locked at G1 closure)

## 9.1 F-Auth-4 path — LOCKED

Path 1 (reconcile, delete authenticateToken duplicate) — LOCKED. Decision recorded. Implementation per Step 6b.

## 9.2 Genuine-public-route exemption list

Pre-flight (§5.1) produces this list. Each entry needs explicit confirmation: "this route is genuinely public; optionalAuth is correct." If any entry is uncertain, default to requireAuth — public-by-default is a worse failure mode than auth-by-default for a luxury franchise OS.

## 9.3 F-Auth-5 — LOCKED. F-Auth-6 — deferred.

F-Auth-5 — LOCKED to fold in. Implementation as Step 6c (see §4.6). F-Auth-6 (tokenUse not gated for access vs ID tokens) — deferred to follow-up PR per v8 framing. Larger change, real scope, not coupled to the auth-contract reconciliation Step 6 is doing.

## 9.4 Deploy window — LOCKED (gate-driven, no calendar)

Locked: no calendar deploy window. Gate-driven sequence per §6. Reasoning: primepisodes.com has no real-user traffic at the time of this fix. The standard deploy-window framing (low-traffic prod window, 24-hour soak) optimizes for user-impact minimization, which does not apply here. Discipline comes from the gates, not the clock. Quality-over-speed locked as the binding constraint. Note: Prime Studios infra is dev + prod only — see Decision §9.9.

## 9.5 Branch coordination — LOCKED (solo PR)

Evoni is solo on this PR. No collaborator coordination required. Section retained as standing guidance for future fix PRs where the second developer (VS Code collaborator) may be active.

## 9.6 Genuine-public-route exemption rule — LOCKED

Locked at G1: default to requireAuth if uncertain. Specific per-route classifications produced during pre-flight:

- decisionAnalytics.js GETs — NOT exempt regardless. The caller-supplied user_id filter is a data-leak vector. Apply requireAuth.

- manuscript-export.js GET (download book) — exempt only if it serves published canon. Pre-flight to confirm. Default to requireAuth if scope is mixed.

- press.js GET /characters and /characters/:slug — exempt only if it serves public-press-kit data (what a journalist would see). Default to requireAuth if it returns full character canon.

- Mixed-verb files (shows.js, characters.js, episodes.js, wardrobe.js, storyteller.js published reads, onboarding.js, storyHealth.js): per-route classification. GETs serving published-only data → exempt with // PUBLIC: comment. GETs serving draft/private data → requireAuth. Writes always → requireAuth.

- Public-by-default is a worse failure mode than auth-by-default for a luxury franchise OS. When in doubt, requireAuth.

## 9.7 New findings absorbed at G1 — D17, D18, D19

Pre-flight surfaced three production exposures not present in v8 (Zone 26 closed before this granularity). All three are absorbed into the existing F-AUTH-1 plan — no scope expansion, just explicit naming so the implementation does not skip them.

D17 — episodes.js:307–315 PUT /:id uses optionalAuth with an in-code comment explaining: "the previous strict authenticateToken caused a hard redirect to /login every time a creator's token expired." This is the exact contract problem F-Auth-4 Path 1 solves. Resolution: once Step 6b lands (AUTH_REQUIRED vs AUTH_INVALID_TOKEN distinction with frontend refresh path), this route swaps to requireAuth. Captured in Step 3 sweep AND validated in §7 verification (route returns 200 authenticated, 401 unauth, mid-session expiry triggers refresh not logout).

D18 — Two mutation routes have authenticateToken commented out for "TESTING": episodes.js:400 (PUT /:episodeId/scenes/reorder) and episodes.js:473 (POST /:episodeId/scripts). Currently shipping unauth in production. This is more severe than F34 (F34 is unauth on franchise-brain; D18 is unauth on episode content — anyone can write scripts and reorder scenes on any episode). Resolution: Step 4 (sub-form b sweep) closes both. Uncomment authenticateToken (replaced by requireAuth as part of Step 6b migration). Add to §7.4 verification checklist.

D19 — episodes.js POST / (CREATE) requires auth at :302, but PUT /:id (UPDATE) at :313 tolerates missing token. Anyone with an episode ID can update without auth. Resolution: Same swap as D17 (Step 3 + Step 6b). Note: D17 and D19 reference the same route at the same lines — D19 is the user-visible consequence (anyone can edit episodes), D17 is the code-level cause (optionalAuth with workaround comment). One fix closes both.

## 9.8 Out-of-scope follow-ups (filed for post-F-AUTH-1)

Items surfaced during pre-flight but explicitly out of F-AUTH-1 scope. Filed for follow-up after F-AUTH-1 ships.

- D20 cont. — jwtAuth.js architectural disposition. Two parallel auth modules long-term? Separate audit needed.

- || 'system' fallback audit. 8 sites beyond thumbnails.js:80 use the pattern (scriptsController.js × 6, sceneController.js:218, compositions.js:1126). Reachability audit needed — same dead-code-vs-real-fallback question.

- arcTrackingRoutes.js references optionalAuth without importing it. Likely runtime error on first request. P1 follow-up: add the import and apply requireAuth.

- episodes.js:101/109/117 discrepancy — v8 cataloged unauth; current code has authenticateToken on POST :108 and DELETE :116. Was this fixed post-v8 or did v8 catalog wrong? No code action; surface for awareness.

## 9.9 Deploy infrastructure — LOCKED (dev + prod, no staging)

Locked at G1: Prime Studios infrastructure is intentionally dev + prod only. No staging environment exists or is planned for this audit cycle. The fix plan was originally written assuming dev/staging/prod three-environment topology; gates G4, G5, G6, G7 in v1.4 reflected that assumption. v1.5 collapses to two environments:

- G4 (Dev verified + soak) absorbs the staging-soak responsibility from former G5. The 2-hour soak now happens on dev before G5 prod cutover.

- Former G5 (staging verified) is removed entirely.

- Former G6 (prod cutover) is renumbered to G5.

- Former G7 (post-deploy soak) is renumbered to G6.

Discipline implication: dev does double duty. G4 is a longer-running gate than the original plan implied because it now carries both verification and soak responsibilities. Do not partial-credit a soak that was interrupted by a code change — re-run the full 2-hour soak on the corrected build before proceeding to G5.

## 9.10 Cognito pool unification — discovered at G1, deferred

Pre-flight env-var verification surfaced an unintentional finding: dev and prod share the same Cognito User Pool and Client ID (us-east-1_mFVU52978 / lgtf3odnar8c456iehqfck1au). This was not a deliberate single-tenant choice — discovered during PM2 runtime env check, intent confirmed as "did not realize they were the same."

- Implication: any user signed up via dev exists in prod. Any auth state created in dev affects prod. Token issued by dev validates against prod (same User Pool).

- F-AUTH-1 impact: zero. Both environments authenticate against real (non-placeholder) Cognito identifiers. F-Auth-2 boot-fail logic passes for both. Step 6b interceptor logic is pool-agnostic.

Out of F-AUTH-1 scope. Filed as P1 architectural follow-up: split Cognito pools — separate dev pool with separate Client ID, prod pool retained as canonical user store, env config updated per environment. Trigger condition: schedule before any beta tester or external user signs up. Once a non-Evoni user exists in the shared pool, the split becomes a data-migration problem rather than a config change.

## 9.11 G2 progress log

Recorded as the F-AUTH-1 PR builds. Each entry is a commit on feature/f-auth-1. Backup of approved commits at claude/f-auth-1-backup on origin (§9.13 Rule 2).

- Step 6a — APPROVED (commit 9fa2e7bb, re-implementation after lost original 23c9ffd). BookEditor.jsx sendBeacon → fetch+keepalive migration. Authorization header flows via authHeader() helper.

- Step 2 (F-Auth-3) — APPROVED (commit e80c711d, re-implementation after lost originals 54d4d09 + ab2ce44). Three-case classifier + degradeOnInfraFailure flag + Error.cause preservation + four-case tests + bare-reference backward-compat test. 5 new tests, 431 total green.

- Step 6b — TRACK 6 CLOSED + STEP 3 CP1+CP2+CP3+CP4+CP5+CP6+CP7 + TRACK 7 MINI-CP + F-SOCKET-1 + F-AUTH-X1 PHASE 2 COMPLETE. Track 5 raw-fetch triage COMPLETE (commit a929ce29 on dev). Track 1 apiClient interceptor update COMPLETE (commit da604ed2). Track 1.5 frontend test scaffolding COMPLETE (commit 94f6cce6). Track 1.6 backend requireAuth split COMPLETE (commit e0b03d18). Track 2 Path A migration COMPLETE (commits 501cd737 + 59f9868a). Track 2.5 behavioral tests COMPLETE (commit a079a04b). Track 3 Path C migration COMPLETE both stages (commits c6047c46 + 69f0a926). Track 4 Path D migration COMPLETE (commits 08a24fec + 06beb1d1). Track 6 CP2-CP15 COMPLETE through commit 04777edd; 466 sites migrated across 70 files; 813/813 frontend tests across 102 test files; 466/469 = 99.4% by site count = 100% of migratable scope. Step 3 CP1 COMPLETE through commit 05cd536d. Step 3 CP2 COMPLETE through commit d73599f8. Step 3 CP3 COMPLETE through commit 61f8a658. Track 7 mini-CP COMPLETE through commit 3e447814. Step 3 CP4 COMPLETE through commit 5c13531e. Step 3 CP5 COMPLETE through commit 1a2d433d. F-SOCKET-1 CLOSED at commit c1962ace via PR #649. F-AUTH-X1 Phase 2 (Option B) CLOSED at commit 8b5750b0 via PR #650. Step 3 CP6 COMPLETE through commit 9892e604; auto-merged to dev at e8bbb808; Character cluster + universe Q13 — 13 source files / 102 handlers / 12 new test files / 128 new tests / 1 single session (collapsed from 2-session forecast). 4 architectural firsts: NEW topology variant 4th in registry — global-prefix mount at character-clips.js (NEW v2.31 §5.13/§5.34 amendment); 2nd cumulative §5.21 mixed Tier 1+4 instance — universe.js; 3rd consecutive frontend ideal state — pattern-locking from "occasional" to production-tooling-cluster default (NEW v2.31 §5.36/§5.44 amendment); 1st anchor file with built-in reference shape at surface time — characterRegistry.js:1882 preserved verbatim (NEW v2.31 §5.48). AI POST reference model 4th application — cumulative 46 handlers across 14 files at uniform requireAuth + aiRateLimiter pattern. Item 16 escalation inspection produces "no-escalation" first-time result (NEW v2.31 §5.41 amendment + §5.51). Sub-form (b) at scale — 3 sub-form (b) files in single CP (NEW v2.31 §5.49). Surface-correction graduates to 23 cumulative data points (CP6 contributed 4 — net 0 handler delta validates surface methodology under 102-handler load). Step 3 pacing sixth backend data point: ~85min within ~83min ±15min mean. Backend test suite: 1680 → 1808 passing (+128, 0 regressions). Integration test discipline — storyEvalV2 anonymous tests updated to expect 401 (NEW v2.31 §5.52). Backed up at 9892e604 on claude/f-auth-1-backup. Step 3 CP7 (Storyteller + memories + franchiseBrain Q13 per v2.23 §5.4) kicks off next, fresh session after v2.31 lands on dev. NO Track 7 mini-CP coordination needed at CP6 (frontend ideal state — 3rd consecutive). Step 3 CP7 COMPLETE through commit 10577813; auto-merged to dev at 44474a08; Storyteller + memories + franchiseBrain Q13 — 17 source files / 153 handlers / 148 promotions / 10 new test files / 157 new tests / 6 integration test updates / 1 single session (collapsed from 2-3 session forecast despite 1.85x scope-expansion outlier per D11). 12 architectural firsts: LARGEST mount-collision yet — Collision A2 at /api/v1/memories with 7 active routers + 8 sub-routers (NEW v2.32 §5.34 amendment); 3rd cumulative §5.21 mixed Tier 1+4 instance — franchiseBrainRoutes.js PATTERN-LOCKS to production-tooling-cluster default (NEW v2.32 §5.21 amendment); 5th application of AI POST reference model — 47 AI POSTs in CP7 alone (cumulative ~92 across ~30 files post-CP7 at uniform pattern; largest cumulative single-CP application by far); 4th consecutive frontend ideal state PATTERN-LOCKS at production-tooling-cluster default (NEW v2.32 §5.36/§5.44/§5.49 amendment); first CP since CP3 with zero sub-form (b) presence; cleanest hygiene surface yet (zero F-AUTH-4 + 3 G4 false positives in API key error string content + system prompt content; NEW v2.32 §5.57 false-positive discipline; zero F-AUTH-5; zero §5.51 Item 16 candidates); first detected legacy authenticateToken usage in CP-zone — franchiseBrainRoutes.js:560 → requireAuth + aiRateLimiter conversion (NEW v2.32 §5.53); largest lazy-noop residue cleanup yet — 13 files; cross-coupling discovered — memories/engine.js:23 imports from franchiseBrainRoutes.js (NEW v2.32 §5.54 commit-ordering signal); custom rate-limiter preservation — memories/assistant.js preserves bespoke assistantLimiter alongside aiRateLimiter (NEW v2.32 §5.55 defer-to-Track-8 consolidation); scope-expansion outlier — forecast 8-10/80-100 vs actual 17/153 (NEW v2.32 §5.4 RETROACTIVE correction + §5.56 outlier methodology); 7th backend Step 3 data point with scope-expansion outlier marker. Surface-correction graduates to 27 cumulative data points (CP7 contributed 4). Backend test suite: 1808 → 1965 passing (+157, 0 regressions). Integration test §5.52 discipline 2nd application — 6 storyEvalV2 anonymous-request assertions updated to expect 401 (cumulative 10 with CP6 4). Backed up at 10577813 on claude/f-auth-1-backup. Step 3 CP8 (Social-feeds per v2.23 §5.4) kicks off next, fresh session after v2.32 lands on dev. NO Track 7 mini-CP coordination needed at CP7 (frontend ideal state — 4th consecutive PATTERN LOCK).

- Steps 3, 4, 5, 1 — NOT STARTED. Per §5.2 implementation order.

### Surfaces for Step 6b reconciliation (preserved across two implementation rounds)

- Frontend has TWO auth-injection paths: axios apiClient interceptor at src/services/api.js + authHeader() direct-fetch helper at frontend/src/utils/storytellerApi.js. BookEditor.jsx uses authHeader(). Both must be reconciled in Step 6b. Inventory of authHeader() callers required before Step 6b implementation begins — this is a Step 6b prep deliverable.

- jest.spyOn cannot intercept calls from inside the same module on CommonJS const-bound exports (closure binding, not export reference). Use jest.mock('<dependency-module>') with the factory form. Worth knowing for future test additions.

- Polymorphic optionalAuth detection (middleware vs factory shape) means optionalAuth.toString() introspection is no longer reliable. No consumer in codebase does this; flagged in case Step 6b interceptor work hits it.

- verifyToken has TWO paths that wrap verifier errors with Error.cause: the test path (NODE_ENV=test → tokenService.verifyToken) and the prod path (aws-jwt-verify direct). Both were updated in Step 2; do not regress either if Step 6b reconciliation touches verifyToken.

- Track 1 surfaces (preserved for sequencing): (1) frontend has no test scaffolding — vitest in package.json but no config, no jsdom, no .test files; addressed by Track 1.5. (2) Backend requireAuth emits AUTH_REQUIRED for both no-header and verifier-rejected; new contract requires the split; addressed by Track 1.6. (3) AUTH_GROUP_REQUIRED returns 403 (not 401); code-before-status check in Track 1 interceptor handles this correctly. (4) authService.refreshToken() duplicates the new refreshAccessToken helper — kept separate in Track 1 to avoid circular auth; cleanup in §9.12.

### Track 1.5 — frontend test patterns (LOCKED v2.2 for reuse in Tracks 2/3/4/6/7)

Three reusable test patterns established by Track 1.5 (commit 94f6cce6). Future migration tracks should adopt these rather than re-deriving them.

Pattern A — vi.stubEnv for DEV-gated code: import.meta.env.DEV is truthy by default in vitest (vitest 0.34 derives DEV from NODE_ENV ≠ 'production'; MODE='test' does not flip it). Vite's define config does not apply because vitest evaluates import.meta.env.DEV at runtime via its env proxy. Use vi.stubEnv('DEV', '') in beforeEach + vi.unstubAllEnvs() in afterEach. Empty string is falsy → DEV-guarded early-returns are bypassed → real logic runs.

Pattern B — partial axios mock that preserves axios.create: apiClient is constructed via axios.create({...}) at module load. Mocking the entire axios default export would break that construction. Use Object.assign to copy real axios.default properties onto a callable function shell, then override only the methods you want to mock:

vi.mock('axios', async (importOriginal) => {
  const actual = await importOriginal();
  const mockedDefault = function axiosFn(config) { return actual.default(config); };
  Object.assign(mockedDefault, actual.default);
  mockedDefault.post = vi.fn();
  return { default: mockedDefault };
});

Pattern C — apiClient.defaults.adapter swap for retry verification: To prove that an interceptor retry actually fires apiClient a second time without making real network calls, swap apiClient.defaults.adapter to a vi.fn().mockResolvedValue(...) for the duration of the test. After the interceptor handler resolves, expect(adapterMock).toHaveBeenCalledTimes(1) confirms the retry happened. Restore in finally so test isolation holds. The retry exercises real interceptor logic end-to-end, not a mock chain.

- Note: pattern A applies to any DEV-gated code in any module. Patterns B and C are specific to apiClient testing but the techniques generalize: partial mocks preserving constructor methods, adapter swapping to test retry/redirect/interceptor behavior end-to-end without network.

Pattern D — vi.mock + static imports for module-scope helpers that capture apiClient at load time: Track 2.5 (commit a079a04b) extracted small const helpers like export const saveDraftProse = (chapterId, proseText) => apiClient.post(...) to make migrated call sites testable. The helper captures apiClient at module load. To test the helper with a mocked apiClient, declare vi.mock('@/services/api', () => ({ default: { post: vi.fn(), ... } })) BEFORE the static import { saveDraftProse } from '@/components/BookEditor.jsx'. vi.mock is hoisted by vitest, so the mock is in place when the helper module evaluates. The helper sees the mocked apiClient; tests verify call shape with expect(apiClient.post).toHaveBeenCalledWith(...). This pattern lets module-scope helper extractions be tested without full RTL component rendering.

Pattern E — multi-method mock reset for apiClient mocks: When the apiClient mock has multiple vi.fn() properties (post, put, get, delete, request, etc.), reset all of them between tests with Object.values(apiClient).forEach((fn) => fn?.mockReset?.()) in beforeEach. The optional-chain on mockReset handles the case where some properties of the mock object are not vi.fn() (defensive against future changes to the mock factory). Track 2.5 established this pattern; reuse for all later tracks that mock apiClient.

Patterns D and E together enable the module-scope-extraction approach Tracks 3, 4, 6, and 7 should use for behavioral test coverage of migrated call sites: extract inline apiClient.X(...) invocations to 1-4 line const helpers, mock apiClient with vi.mock at module top, import the helpers statically, reset all methods in beforeEach. No full RTL setup required. Validated across 8 helpers in 3 files (Track 2.5) with zero genuine "cannot test without RTL" cases surfaced.

Pattern F — Api-suffix convention for shadow-conflict resolution: When extracting Track 2.5-style module-scope helpers from a file where component-local handler names mirror the endpoint operation names (e.g., a component with finalizeProfile handler whose body wraps a network call to /profiles/finalize), naming the extracted helper finalizeProfile shadows the component handler. Resolution: suffix the network helper with Api (finalizeProfileApi). Component handler stays unchanged — it imports and wraps the API helper plus UI state updates. Track 3 Stage 2 (commit 69f0a926) established this pattern across 11 conflicts in SocialProfileGenerator.jsx; document the convention in a module-scope comment when applied so future contributors understand the suffix.

Pattern F applies wherever Tracks 4 and 6 encounter files with component-handler names matching endpoint operation names. Two notable Track 6 files where this is likely: SceneSetsTab.jsx (64 sites) and FranchiseBrain.jsx (18 sites). Apply the suffix convention from the start of each file's migration rather than discovering shadow conflicts mid-flow.

File-local helper convention (LOCKED v2.12, validated by CP5 cross-file overlaps): helper modules are file-local; cross-file imports are not used in F-AUTH-1 even when endpoints overlap. When a Track 6 file hits an endpoint already covered by another Track 6 file's helper, the helper is duplicated locally rather than imported. Each CP commit's helper module is self-contained per CP2/CP3/CP4/CP5 precedent. Duplication cost is bounded (~3 LOC per helper) and discoverable; cross-file imports would break test-per-file isolation. Validated against 4 cross-file duplications in CP5 (3 in EpisodeScenesTab: listSceneSetsApi, suggestAnglesApi, createAngleApi + 1 in SeriesPage: listShowsApi). Total drift surface ~12 LOC across CP5; benign.

Inline-anonymous-onClick handling (LOCKED v2.13, validated by CP6 — 2 sites): When a fetch site is an inline anonymous async arrow inside a JSX onClick handler, extract to a module-scope helper, then call from a named handler function. Do not migrate inline fetch inside JSX onClick — the structural pattern is anti-Pattern-D (hard to test, hard to refactor, harder to debug). Cost ~2 LOC per extraction; produces testable handler functions matching CP2-CP5 discipline. Validated against CharacterGenerator:312 + CharacterTherapy:625 in CP6.

setInterval polling sites (LOCKED v2.13, validated by CP6 — 1 site): When a fetch site is inside a setInterval callback, replace the inner fetch with the apiClient helper call. setInterval / clearInterval semantics are unchanged. Validated against TemplateDesigner.startPolling in CP6.

Method-branching split (LOCKED v2.13, validated by CP6 — 1 site): When a single handler conditionally chooses POST vs PUT based on whether an entity exists, split into two helpers (createXApi + updateXApi) and let the call site do the conditional. Cleaner than parameterizing method on a single helper. Validated against TemplateDesigner.handleSave in CP6.

Hardest-first execution discipline (LOCKED v2.13, validated by CP6): In multi-file batches with heterogeneous cost-class distribution, migrate the highest-complexity file first. Combined with explicit hard-cap on the hardest file (CP6 used 90-min cap on CharacterGenerator). Rationale: complexity surprises in the hardest file are most likely to force WIP-and-resume; surfacing them first preserves clean checkpoint discipline. The hard cap is a guardrail; if not triggered, it confirms the cost-class predictor was accurate.

Simplest-first execution for long-tail batches (LOCKED v2.14, validated by CP7): In long-tail batches with many small files, migrate simplest files first. Builds migration cadence in the first ~15 minutes via single-site warm-up files; defers anchors (6-8 sites each) to second half when discipline is internalized. Opposite of hardest-first because long-tail files are bounded — no real cost-class outlier; momentum matters more than fail-fast. Validated against CP7's 10-file batch (5 single-site warm-ups + 5 anchor files).

Multipart upload pattern (LOCKED v2.14, validated by CP7 — 1 site at PdfIngestZone): When a fetch site uses FormData payload for multipart upload, pass FormData directly as second argument to apiClient.post(url, formData). Do NOT manually set Content-Type header — axios detects FormData and sets the multipart Content-Type with the correct boundary automatically. Helper signature: uploadXxxApi(formData) → apiClient.post(url, formData). Future Track 6 multipart sites follow same pattern.

Internal-helper-refactor pattern (LOCKED v2.14, validated by CP7 — WorldDashboard.safeFetch): When a file has its own internal fetch wrapper used by multiple callers, refactor the wrapper internally to use apiClient rather than migrating each caller individually. Caller-side simplicity preserved (callers unchanged). The migration is a single edit inside the wrapper. Avoids unnecessary call-site churn. Future tracks encountering similar internal-fetch-wrapper patterns follow the same approach.

Method-correction discovery — surface-time vs mid-flow (NEW v2.14): With surface-with-cost-estimation discipline (locked v2.8), method-correction discovery moves earlier in the workflow. CP2 caught 3 mid-flow; CP3-CP6 caught 0 mid-flow; CP7 caught 1 at surface (CFOAgent setBudget PUT-not-POST). Surface-time is preferred because corrections are cheaper to handle before any code changes. Both modes remain valid; the CP2 finding pattern of "BUG-class migrations surface pre-existing HTTP method mismatches" applies whether discovered at surface or mid-flow.

Existing-test-file amendment convention (LOCKED v2.15, validated by CP8 RelationshipEngine.jsx): When amending a file with existing helpers and tests, append new helpers/tests to existing files rather than creating duplicate test files. RelationshipEngine.jsx already had 11 helpers (presumably from earlier track work); CP8 appended +1 helper (listRegistriesApi) and +1 test rather than creating a duplicate test file. Relevant for files with existing test coverage from prior tracks (e.g., StoryEvaluationEngine.jsx, NarrativeIntelligence.jsx). Append-not-overwrite preserves existing coverage and avoids duplicate test file proliferation.

Cross-CP duplication scaling note (NEW v2.15): v2.12 §9.11 file-local convention scales without coupling concerns at 11 cross-CP duplications in a single CP. CP5 had 4 dups, CP6 had 2 dups, CP7 had 1 dup, CP8 had 11 dups across 5 files (~33 LOC). The test-isolation benefit dominates the LOC cost. WorldStateTensions duplicating 7 helpers from CP7 WorldDashboard is the largest single-file cross-CP duplication in F-AUTH-1; the file-local module block kept the migration mechanical. The convention's "duplicate locally rather than import" rule scales cleanly to high cross-CP density.

Pattern composability note (NEW v2.15): Locked patterns can stack within a single file without cross-contamination. WorldFoundation.jsx in CP8 was the first file to apply three locked patterns simultaneously: multipart upload (v2.14) + method-branching split (v2.13) + idiom mix (4 sub-shapes within one file: async + thenable + multipart + method-branching). Migrated cleanly. Pattern composability was implicit in the convention library; CP8 explicitly validates the stacking. Future high-pattern-density files apply the same composability.

Binary-response pattern (LOCKED v2.16, validated by CP9 — 1 site at StoryEngine.readStoryApi for ElevenLabs TTS audio): When a fetch site expects a binary response (audio, PDF, image), pass { responseType: 'blob' } as the third argument to apiClient.post (or get/put/etc.). axios returns the blob directly as response.data. Helper signature: readStoryApi(payload) → apiClient.post(url, payload, { responseType: 'blob' }). Pre-migration code's await res.blob() after fetch translates cleanly. Joins multipart upload (v2.14) as the second non-JSON apiClient interaction pattern. Future tracks adding binary-response sites follow the same pattern.

Service-module internal-refactor pattern (LOCKED v2.16, validated by CP9 — services/showService.js): When a service module exposes the canonical accessor for an endpoint family, refactor each method's internals to use apiClient while preserving the service contract (method signatures + return shapes) unchanged for consumers. Tests use vi.mock for apiClient and call service methods directly (e.g. showService.getAllShows()). Different from page-level helper extraction (which creates new module-scope helpers and updates call sites). Service-module refactor preserves the service's contract; only the internals change.

Hook module-scope helper pattern (LOCKED v2.16, validated by CP9 — hooks/useGenerationJob.js): Helpers exported from hook module-scope as export const; consumers of the hook unchanged. Polling lifecycle preserved when applicable. Different from page/component shape; same Pattern D test approach via direct named imports. Joins the page (CP2-CP8) and service module (CP9 showService) shapes as a third structural class for helper extraction in F-AUTH-1.

Service-module precedence inversion (NEW v2.16 note — observed at showService.js): When a service module is the canonical accessor for an endpoint family, file-local duplicates in earlier CPs are downstream copies of the service contract, not parallel copies. showService.js is the canonical /shows accessor; CP2 SceneSetsTab + CP5 SeriesPage + CP7 (via listShowsApi) file-local duplicates exist downstream of this contract. v2.12 file-local convention still applies; this is a clarifying observation about precedence, not a new rule. Future service-module migrations follow the same precedence dynamic when applicable.

URL composition preserved-verbatim discipline (NEW v2.16 — validated by CP9 WritingRhythm.jsx, second instance CP10 StoryDashboard.jsx): When surface-time analysis reveals an unusual URL composition pattern (e.g., empty API base, missing /api/v1/ prefix), preserve verbatim during migration. Don't fix. Don't investigate. Surface for Step 3 audit. WritingRhythm and StoryDashboard both use const API = import.meta.env.VITE_API_URL || '' empty default + ${API}/... = relative paths without /api/v1/ prefix. Migration preserved this composition verbatim in both files; apiClient.baseURL is also empty string. Pattern lock validated against 2 instances. If pre-existing bug, surfaced for Step 3 audit per v2.15 §9.11 "bugs surface, don't fix" discipline. Step 3 audit should adjudicate both observations together (likely the same Vite proxy or server rewrite resolution applies to both files).

Branching-split generalization (LOCKED v2.17, validated by CP10 StoryEvaluationEngine.jsx — URL-branching variant). v2.13 §9.11 method-branching split (PUT vs POST conditional, same URL) generalizes to any conditional shape at the call site — method, URL, or both. Helper extraction handles each branch as a separate helper; call site does the ternary. Validated at CP6 TemplateDesigner (method-branching: editId ? PUT : POST with same URL → createTemplateApi + updateTemplateApi) and CP10 StoryEvaluationEngine line 1243 (URL-branching: bookId ? GET /storyteller/books/:id : GET /storyteller/chapters → getBookApi + listAllChaptersApi). Future tracks encountering branching at any axis follow the same convention.

Structural-test-file amendment validation (LOCKED v2.17, validated by CP10 StoryEvaluationEngine.test.jsx). v2.15 §9.11 existing-test-file amendment scales to both behavioral test files (CP8 RelationshipEngine — first instance) and structural test files (CP10 StoryEvaluationEngine — first structural instance). For structural tests (fs.readFileSync against source asserting on shape/imports), existing assertions remain valid post-migration when migration preserves apiClient import + absence of authHeaders + internal wrappers. vi.mock hoisting is required if dynamic imports are added in new describe blocks. CP10 StoryEvaluationEngine outcome: 16 tests in single file (6 Track 3 structural assertions all pass + 10 new CP10 helper tests) — first F-AUTH-1 multi-pattern existing-test-file amendment.

Cross-CP existence high-water mark (NEW v2.17 note). listRegistriesApi reaches 6-fold cross-CP existence at CP10 (CP3 WriteMode + CP6 CharacterTherapy + CP7 Home + CP8 RelationshipEngine + CP8 StoryProposer + CP10 StoryEvaluationEngine). Empirical ceiling for cross-CP duplication density observed in F-AUTH-1. v2.12 file-local convention scales without coupling concerns up to and including 6-fold existence. Each duplicate is ~3 LOC; ~18 LOC total across all 6 files. Test isolation per file dominates the LOC cost. The convention's "duplicate locally rather than import" rule remains correct at this density.

Pattern composability — second instance (NEW v2.17 note). CP6 WorldFoundation was first triple-pattern file (multipart upload + method-branching split + idiom mix). CP10 StoryEvaluationEngine is the second triple-pattern file (URL-branching split + existing-test-file amendment + 6-fold cross-CP duplication). Pattern composability is now validated at 2 data points across diverse pattern combinations. Patterns compose cleanly within a single file without cross-contamination, regardless of which combination of locked patterns applies. The convention library is robust to high-pattern-density files.

Mixed PUBLIC+BUG within single file (LOCKED v2.18, validated by CP11 PressPublisher.jsx — first F-AUTH-1 instance). When a single file contains a mix of LOCKED PUBLIC and BUG-class fetch sites, apply per-site adjudication during surface analysis. LOCKED PUBLIC sites retain raw fetch with a 9-line PUBLIC comment block referencing inventory v2 §4.2 + F-Auth-3 degradeOnInfraFailure exemption list (parallel to BookEditor:55 / WriteMode:980 Pattern G locked-comment template, but for PUBLIC disposition rather than streaming). BUG-class sites in the same file migrate to apiClient with module-scope helpers per the standard Path A discipline. The file's test scaffolding includes a structural assertion that the LOCKED PUBLIC site's raw fetch is preserved post-migration (parallel to v2.17 §9.11 structural-test-file amendment shape applied to CP10 StoryEvaluationEngine). Validated against PressPublisher line 119 in CP11 (1 LOCKED PUBLIC + 3 BUG migrated). Future tracks encountering mixed-disposition files (WorldSetupGuide deferred to CP15 with 3 LOCKED PUBLIC + 5 BUG) follow the same convention.

Combined-axis branching split — stacking validated (NEW v2.18 note). v2.13 §9.11 method-branching split + v2.17 §9.11 URL-branching generalize natively to combined axes — a single conditional may switch BOTH method AND URL simultaneously, handled by the existing convention without extension. Validated at CP11 WorldLocations:141 — saveLocation's editId conditional selects PUT /world/locations/:id when editing OR POST /world/locations when creating, on the same line. Convention application: extract updateLocationApi(id, payload) + createLocationApi(payload) as separate helpers covering both branches; call site does single ternary covering combined axes (editId ? updateLocationApi(...) : createLocationApi(...)). No new lock language required; v2.18 documents this as "stacking validated" — the convention library handles combined-axis branching natively.

Pattern G default-on-matching-precedent discipline (LOCKED v2.19, validated by CP12 useStoryEngine:358). When a streaming-shape candidate is surfaced, default disposition is Pattern G lock if shape matches existing locked precedent. NodeFetch migration is a NEW policy decision distinct from Pattern G — requires explicit Evoni approval, not a default. Surface report compares the candidate's shape against existing locked precedents (BookEditor:58 keepalive, WriteMode:1000/1191 streaming SSE, WriteModeAIWriter:281, AppAssistant:239). If match (POST + JSON.stringify body + res.body.getReader pattern, or keepalive: true), propose Pattern G lock as default. If genuine deviation (different streaming shape, different browser feature), surface for policy discussion before committing. Validated at CP12 useStoryEngine.js:358 — shape matched WriteMode:1000/1191 + WriteModeAIWriter:281 exactly; Pattern G lock applied without policy escalation. Future tracks encountering streaming-shape candidates follow the same default-on-matching-precedent discipline.

Pattern G line-number shift on comment insertion (NEW v2.19 note). The 9-line locked-comment block insertion shifts the locked-site line number downward by ~9-10 lines. Surface report line numbers are pre-insertion approximations; final allowlist line numbers are post-insertion. Validated at CP12: surface predicted line 356 for Pattern G site; actual is line 358 post-migration (kickoff fetch shifted from line 348 → line 376 due to comment-block insertion above). Not a problem; just observed mechanic. Verification-grep allowlist references the post-insertion line numbers throughout.

Hook module-scope helper pattern — third validation (UPDATED v2.19, supersedes v2.16 single-instance lock). v2.16 §9.11 hook module-scope helper convention validated across three hooks of varying complexity: CP9 useGenerationJob.js (5 sites, simple polling shape), CP11 usePageData.js (3 sites, mid-density), CP12 useStoryEngine.js (13 sites + 1 Pattern G, high-density 14-site dedicated CP). Convention scales unchanged across the complexity range. Helpers exported as export const at module scope; consumers of the hook unchanged; tests use direct named imports. Joins the page (CP2-CP8, CP11) and service module (CP9 showService) shapes as a third structural class for helper extraction in F-AUTH-1, now validated at three data points.

Existing-test-file amendment — third validation (UPDATED v2.19, supersedes v2.17 dual-instance lock). v2.15 §9.11 existing-test-file amendment convention validated across three distinct test-file shapes: CP8 RelationshipEngine (behavioral-only append), CP10 StoryEvaluationEngine (structural-with-behavioral-append, vi.mock hoisting required for dynamic imports), CP12 useStoryEngine (hook-with-helper-append + Pattern G structural tests; pre-existing 3 Track 3 tests preserved unchanged). Three distinct test-file shapes; convention scales unchanged across all observed structures. The append-not-overwrite discipline is robust to test-file structural variation.

Callback-cluster preservation pattern (NEW v2.19 observation, NOT a new convention). When a single callback contains multiple fetch sites with varied semantic roles (must-complete vs fire-and-forget vs conditional vs no-body-read), file-local helpers replace each fetch call site individually; surrounding Promise.all/Promise.allSettled/conditional wrappers stay verbatim; semantic preservation comes from the helper-replaces-fetch shape, not from explicit cluster orchestration. Validated at CP12 handleApprove (6 sites in 156-line callback, 5 distinct semantic shapes: site 6 Promise.all member must-complete; sites 7-8 fire-and-forget concurrent in postApprovalTasks array; site 9 .catch only with no-body-read helper variant — helper omits .then((r) => r.data); site 10 fire-and-forget conditional on story.db_id; site 11 success-path branching different from site 5 same-helper). All 6 semantic invariants preserved without flattening. The convention library naturally handles callback clusters; no new lock language needed.

Data-driven URL pass-through pattern (LOCKED v2.20 §9.11, validated execution at CP13 WorldAdmin:5550). When N variant URLs are dispatched via config-array.map (or other data-driven enumeration in source) AND method, payload shape, and headers are uniform across variants, a single pass-through helper is canonical. Helper signature: export const verbNounOpApi = (endpoint, payload) => api.post(endpoint, payload).then(r => r.data). Distinct from v2.17 URL-branching split (which assumes call-site ternary/switch with hard-coded URLs at each branch), v2.13 method-branching split, and v2.18 combined-axis stacking. Structural conditions for applicability (ALL required): (1) method uniform across variants, (2) payload shape + headers uniform across variants, (3) variants enumerated in source as data (config array, lookup table, registry) — not as control flow, (4) URLs originate from inside the file (no external input — closes the SSRF surface). If any condition fails, fall back to v2.17 / v2.13 / v2.18 per shape. Helper naming: use a verb-noun-Op pattern (e.g., bulkWardrobeOpApi, not just bulkOpApi) — preserve domain context per Pattern F. Test parameterization via test.each (or describe.each) over the variants verifies dispatch correctness.

Service-module precedence inversion — three-data-point validation (UPDATED v2.20, supersedes v2.16 single-instance lock). v2.16 §9.11 service-module precedence inversion convention validated across three data points: CP9 showService.js (first instance), CP13 WorldAdmin:5563 wardrobeService.js + 7 component consumers (highest consumer count observed in F-AUTH-1), CP13 WorldAdmin:6088 wardrobeService.js line 39 (second wardrobeService instance). Convention scales unbroken at 7-component-consumer density. v2.16 lock language stands without modification; v2.20 records the data points. Discipline: when a service-module canonical exists for an endpoint, file-local helpers in pages duplicate the helper locally per v2.12 rather than importing from the service; the service contract remains the upstream source of truth, but file-local idiom is preserved.

Partial-migration extension pattern (NEW v2.20 §9.11 observation). When a file has pre-existing apiClient adoption (from independent earlier migration, not from a prior Track 6 CP), new helpers preserve the file-local idiom. Validated at CP13: WorldAdmin had pre-existing api.post() at line 6306 (NOT in CP13 zone). CP13 extended with 11 new helpers all using the same api import (not the global apiClient style). Test scaffolding uses vi.mock('../services/api', () => ({ default: { ... } })) consistent with file-local convention. Verification grep treats the file as partially-migrated rather than virgin: pre-existing apiClient site is NOT a CP deliverable; do not touch. Discipline: at surface-time, surface report enumerates pre-existing apiClient sites separately from BUG-class fetch sites; migration zone is BUG-class only.

Outer try/catch cleanup observation (NEW v2.20 §9.11 note, NOT a new convention). When migrating from raw fetch with if(res.ok)/if(!res.ok) idioms to apiClient throws-on-non-2xx, an outer try/catch wrapping only the payload-construction-then-fetch block may become unmatched if the inner block was the only try consumer. Resolution: remove the outer try since payload construction (FormData append calls, JSON object construction, etc.) is pure JS that doesn't throw; inner try/catch on the network call handles all error paths. Validated at CP13 WorldAdmin:6582 (outer try wrapping FormData construction + upload became unmatched after multipart helper replaced inline fetch). Filed as observation; no new lock language needed (recognizable cleanup, not a convention). Surface analysis discipline: future surface reports should anticipate this cleanup when a migration zone has outer-try-then-fetch patterns.

Pattern G zero-trigger admin-page heuristic (NEW v2.20 §9.11 observation). Admin-page CPs default to zero Pattern G expectation; chat/AI-writer CPs default to high Pattern G expectation. Two consecutive admin-page instances confirm: CP11 PressPublisher BUG-only sites (zero Pattern G), CP13 WorldAdmin (zero Pattern G). Streaming-shape candidates concentrate in chat/AI-writer files (BookEditor:58, WriteMode:1000, WriteMode:1191, WriteModeAIWriter:281, AppAssistant:239, useStoryEngine:358 — all 6 Pattern G locked sites are in chat/AI-writer files). Surface analysis discipline: admin-page CPs surface-check Pattern G as low-prior; chat/AI-writer CPs surface-check Pattern G as high-prior. Heuristic, not lock — surface check still required per file regardless.

Partial-migration extension pattern — graduates to two-data-point pattern (UPDATED v2.21, supersedes v2.20 single-instance observation). v2.20 §9.11 partial-migration extension was first instance at CP13 WorldAdmin. CP14 EpisodeDetail is second instance with the same shape: file imports api from ../services/api; has 1-2 pre-existing api.post() sites from independent earlier migration (not from prior Track 6 CP); BUG-class fetch sites are the migration zone. Pattern graduates to two-data-point pattern in v2.21. Discipline locked: when surface report encounters UNCLEAR-B file, partial-migration extension hypothesis is the default test. Adjudication takes ~30 seconds (read top-of-file imports + grep for api. calls + grep for raw fetch calls). New helpers preserve file-local idiom (NOT global apiClient. style). Test scaffolding uses vi.mock('../services/api', () => ({ default: { ... } })) consistent with file-local convention. Verification grep at end-of-CP: pre-existing apiClient sites must NOT appear in diff. Validated at CP13 WorldAdmin (1 pre-existing apiClient site at line 6306) + CP14 EpisodeDetail (2 pre-existing apiClient sites at lines 776 + 805).

Pattern G zero-trigger admin-page heuristic — graduates to three-data-point validation (UPDATED v2.21, supersedes v2.20 dual-instance observation). v2.20 §9.11 admin-page heuristic was first observed at CP11 PressPublisher BUG-only sites + CP13 WorldAdmin. CP14 EpisodeDetail is third consecutive admin-page CP with zero Pattern G triggers. Heuristic graduates to three-data-point validation in v2.21. Validated across page-shape variations: PressPublisher (domain-content admin), WorldAdmin (show-management admin), EpisodeDetail (episode-management admin). Streaming-shape candidates remain concentrated in 5 chat/AI-writer files (all 6 Pattern G locked sites). Heuristic, not lock — surface check still required per file regardless.

Helper-reuse density forecasting heuristic (NEW v2.21 §9.11 observation, NOT a new convention). When surface analysis identifies CRUD + reload-after-mutation cluster pattern (single resource family with mount + create + update + delete + reload-after-each-mutation), helper count is 30-40% lower than site count. The loader gets called once at mount + once after each mutation = N+1 invocations from M+1 distinct call sites where M is the mutation count. Validated at CP14 EpisodeDetail (40% reduction; 6 helpers / 10 sites — 4× reuse on listEpisodeLibraryScenesApi across mount + 3 reload-after-mutation paths; 2× reuse on reorderEpisodeLibrarySceneApi in single Promise.all parallel-execution wrapper). Forecasting heuristic, NOT a new convention — file-local helper convention v2.12 already handles helper reuse natively. Surface analysis discipline: when CRUD + reload pattern detected, session-time-per-site forecast can be reduced ~30% from CP3-zone baseline; helper-count forecast reduced 30-40% from site count. Tests cover the helper once per behavioral assertion + 1-2 explicit reuse-coverage tests; do NOT duplicate per-call-site coverage.

Helper-reuse density pattern — graduates to two-data-point pattern (UPDATED v2.22, supersedes v2.21 single-instance observation). CP15 WorldSetupGuide is second instance: 3-way reuse on getPageContentApi across sites 1, 2, 4 (multi-tab status-check shape; 6 helpers covering 8 sites = 25% file-level reduction). Pattern graduates to two-data-point pattern in v2.22. Two distinct underlying shapes: CRUD + reload-after-mutation (CP14) and multi-tab status-check (CP15) — both produce helper-count reduction via single loader covering multiple call sites. Forecasting heuristic, NOT a new convention. Surface analysis discipline: when CRUD + reload OR multi-tab status-check pattern detected, helper-count forecast reduced 25-40% from site count; session-time forecast can be reduced ~20-30% from CP3-zone baseline.

Partial-migration extension pattern — graduates to FIVE-data-point pattern (UPDATED v2.22, supersedes v2.21 two-data-point validation). CP15 contributes three new instances on top of v2.21 baseline (CP13 + CP14):

- SocialProfileGenerator.jsx: 9+ pre-existing exported helpers at lines 30-41 + downstream callers; CP15 zone added 2 BUG-class sites at lines 1213, 1229. Highest pre-existing density observed in F-AUTH-1.

- FeedBulkImport.jsx: apiClient imported line 7 + downstream usage; CP15 zone added 2 sites at lines 177, 210.

- EpisodeScriptTab.jsx: 5 pre-existing api.* sites at lines 152, 161, 177, 191, 194; CP15 zone added 2 sites at lines 143, 144.

All three pre-existing apiClient zones verified UNTOUCHED post-execution. Pattern graduates to five-data-point validation in v2.22. Robust across page (CP13/CP14), partially-migrated-page (CP15 SocialProfileGenerator at 9+ pre-existing helpers — highest pre-existing density observed), and component (CP15 FeedBulkImport, EpisodeScriptTab) shapes. Surface analysis discipline locked: when UNCLEAR-B file is encountered, partial-migration extension hypothesis is the default test; adjudication takes ~30 seconds (read top-of-file imports + grep for api. or apiClient. calls + grep for raw fetch calls). Inventory v2 §4.2 amendments: CP13 WorldAdmin + CP14 EpisodeDetail + CP15 × 3 all reclassified at execution time per cross-CP evidence; original UNCLEAR-B labels were provisional.

Pattern G zero-trigger admin-page heuristic — graduates to FOUR-data-point validation (UPDATED v2.22, supersedes v2.21 three-data-point). CP15 23-file zone surfaced ZERO Pattern G triggers across all 23 in-scope files (admin pages, production pages, components, hooks all clean). Heuristic graduates to four-data-point validation: CP11 PressPublisher BUG-only sites + CP13 WorldAdmin + CP14 EpisodeDetail + CP15 (entire 23-file zone). Streaming-shape candidates remain concentrated in 5 chat/AI-writer files (BookEditor:58, WriteMode:1000, WriteMode:1191, WriteModeAIWriter:281, AppAssistant:239, useStoryEngine:358 — all 6 Pattern G locked sites). Robust across multi-file zones up to 23-file scale.

Cross-CP duplication ceiling semantics clarification (NEW v2.22 §9.11). The v2.17 §9.11 6-fold "ceiling" was always a soft observation about scaling pressure, not a hard cap. CP15 confirms operationally: listRegistriesApi reaches 8-fold cross-CP existence (StoryEvaluationEngine + WriteMode + RelationshipEngine + CharacterTherapy + StoryProposer + Home + MemoryBankView + useRegistries) — exceeds 6-fold by 2; listShowsApi reaches 6-fold (SceneSetsTab + SeriesPage + CulturalCalendar + CultureEvents + UniverseProductionPage + WorldSetupGuide) — meets ceiling exactly. Path A (continue v2.12 §9.11 file-local convention regardless of count) applied through CP15 without coupling concerns. v2.22 records the new high-water marks; ceiling-revisit (Path B cross-file import precedent) deferred to v2.23+ topic conditional on Step 3 backend sweep findings. The convention library scales unbroken at 8-fold density; cross-file imports are NOT introduced in F-AUTH-1.

Variable-URL surface-time adjudication discipline (NEW v2.22 §9.11). When surface report flags variable-URL sites as v2.20 candidates (data-driven URL pass-through), sample-time inspection MUST verify all four structural conditions before applying v2.20. If condition (1) method uniformity fails (which is the most common failure mode for apiFetch-wrapper shapes), fallback is v2.14 internal-helper-refactor (wrapper preserved, internal fetch swapped for apiClient.request). Validated at CP15 with three sites: MemoryConfirmation:51 (apiFetch wrapper, methods vary GET/POST/DELETE → v2.14), DecisionEchoPanel:31 (single URL + single method → standard helper extraction, neither v2.20 nor v2.14), MemoryBankView:57 (apiFetch wrapper, methods vary → v2.14). v2.20 stays at 1 implementation data point (CP13 WorldAdmin only); v2.14 reaches 5 data points (CP3 + CP6 + CP15 × 2). Surface analysis discipline: surface flags candidates via four-condition test; execution adjudicates per site; fallback patterns apply when conditions fail.

v2.14 internal-helper-refactor pattern — five-data-point validation (UPDATED v2.22). Pattern reaches five data points across Track 6: CP3 (first instance), CP6 (second), CP15 MemoryConfirmation:51 (fourth — apiFetch wrapper, 5 call sites with varying methods), CP15 MemoryBankView:57 (fifth — apiFetch wrapper, 6 call sites with varying methods). Pattern application: when a file has a wrapper function that calls fetch internally and the wrapper is invoked from multiple call sites with varying methods/payloads, preserve the wrapper signature externally and swap the internal fetch for apiClient.request. Wrapper external API unchanged; auth bypass closed. Validated robust across 5 data points spanning CP3 + CP6 + 2× CP15.

Pattern G — "can't-migrate-to-axios" exception class: When a fetch site uses an underlying HTTP feature that axios does not support in browsers (response-body streaming via SSE, keepalive: true, or other browser-only features), the site cannot migrate to apiClient without breaking functionality. These sites are retained as raw fetch() calls with inline auth header injection from localStorage, structurally identical to Path D (inline Bearer construction). Pattern G is the locked-exception class for these cases.

Implementation pattern (3 known sites today):

- Keep raw fetch() call (do NOT migrate to apiClient).

- Inject inline auth header: const token = localStorage.getItem('authToken') || localStorage.getItem('token'); then ...(token ? { Authorization: `Bearer ${token}` } : {}) inside the headers object.

- Add a 6-9 line documenting comment immediately above the fetch call. Comment must explain: (a) what underlying HTTP feature is being used, (b) why axios does not support it, (c) the inline-auth approach, (d) reference to fix plan v2.10 §4.6 + §9.11 Pattern G.

- Allowlist the file:line in the verification grep. Future contributors see the comment, do not "fix" by attempting apiClient migration.

Three known Pattern G sites (all locked, all documented):

- frontend/src/components/BookEditor.jsx:55 — keepalive: true for beforeunload draft save (CZ-5 contract). Locked in v2.5; line corrected to :55 in v2.7.

- frontend/src/pages/WriteMode.jsx:980 — SSE streaming for voice-to-story Claude AI generation. Locked in v2.10 from CP3 commit b0127817.

- frontend/src/pages/WriteMode.jsx:1145 — SSE streaming for story-continue Claude AI generation in handleContinue. Locked in v2.10 from CP3 commit b0127817.

- Threshold for revisiting Pattern G: if Track 6 long-tail or future feature work surfaces 4+ Pattern G sites, evaluate adding a streaming-fetch helper to apiClient (a Track 1 amendment that would handle auth injection + response-body access without requiring inline construction). Today's 3 sites do not justify the scope; they are documented as locked exceptions instead.

## 9.12 Deferred cleanups (post-F-AUTH-1)

Note: the outer try/catch entry that was deferred in v1.6/v1.7 was cleaned up during Step 2 implementation (commit e80c711d). The defense-in-depth shell was hiding bugs (synchronous throws in console calls, req.headers access edge cases) that the new three-case structure handles explicitly. Removed entry from this list as resolved.

F34 status: CLOSED at the call site (Track 6 CP4 commit 11a82876). Server-side enforcement closes via Step 3 backend sweep on franchiseBrainRoutes.js (optionalAuth → requireAuth swap on all 10 mutation routes). Both halves required for full F34 closure: frontend now sends auth on every /franchise-brain/* mutation; backend will reject unauth attempts post-Step-3. Audit handoff v8 Decision #34 honored: F34 closes inside this PR's scope, not as a separate hotfix.

- Real metrics library — Step 2 ships with structured-log-derived metrics. If Prime Studios adds prom-client / opentelemetry / similar later, the F-Auth-3 call site is one line and trivially swappable.

- console.debug enablement — current ESLint config blocks it; Step 2 uses console.log as the quietest allowed level. If the project later wires up the debug package or adjusts ESLint, the F-Auth-3 quiet-log call site can move to console.debug.

- authService.refreshToken() duplication (surfaced in Track 1 §3.4) — frontend/src/services/authService.js:125–147 has a refreshToken() method that nearly duplicates the new bare-axios refreshAccessToken helper in src/services/api.js. Track 1 kept them separate to avoid circular auth (authService imports api). Cleanup candidate when authService is touched in a Track 6 file: migrate authService.refreshToken() callers (login flow primarily) to use the bare-axios helper, then delete the apiClient-based duplicate.

- Parallel-request refresh storm (surfaced in Track 1 §3.7) — N simultaneous AUTH_INVALID_TOKEN responses trigger N parallel refresh calls. Backend rate-limiter (10/min) keeps it from being catastrophic but it is wasteful. Optimal solution: refresh-promise singleton — first request starts refresh, others await the same promise. Real complexity for marginal gain; deferred until evidence of operational impact.

- ESLint v9 migration — .eslintrc.js is the v8 format and ESLint v9 (installed) does not auto-detect it. Frontend lint has been broken for some time. Out of F-AUTH-1 scope; separate config-modernization PR.

- Refresh-via-cookie hardening — login endpoint sets a refreshToken httpOnly cookie (src/routes/auth.js:75), but the refresh endpoint at :112 reads from request body only, ignoring the cookie. The Track 1 helper passes from localStorage (matching the body path). Cookie-based refresh would be a hardening follow-up; out of F-AUTH-1 scope.

- npm audit follow-up — Track 1.5 install reported 24 vulnerabilities (3 low, 13 moderate, 7 high, 1 critical) in the existing frontend dep tree. None new from jsdom; ambient state of the codebase pre-F-AUTH-1. Run npm audit fix and review the manual cases after F-AUTH-1 ships.

Path E candidates surfaced during Tracks 3 and 4 (~37 sites across 8 files) — reclassify during Step 3 sweep:

- From Track 3 (4 sites, 3 files):

- frontend/src/hooks/useStoryEngine.js:527 — POST to /api/v1/memories/extract-story-memories with no auth header. Inline headers: { 'Content-Type': 'application/json' } only.

- frontend/src/pages/RelationshipEngine.jsx:111 — bare fetch(url) GET /api/v1/character-registry/registries with no auth at all.

- frontend/src/pages/SocialProfileGenerator.jsx:1213, 1229 — bare fetch to /api/v1/world/<showId>/events and /api/v1/world/<showId>/events/from-profile with no auth helper.

- From Track 4 (~33 additional sites):

- frontend/src/components/FeedBulkImport.jsx:164 — GET /bulk/jobs with no auth. :197 — parseCsv POST has Content-Type only, no auth.

- frontend/src/pages/WorldStudio.jsx — ~29 unauth fetches across multiple sites (lines 231, 248, 259, 271, 714, 722, 744, and others) hitting /character-depth, /world/*, /api/v1/character-registry/registries. Most likely intentional PUBLIC reads (world data is presumably visible to non-authenticated users) but Step 3 must classify each backend route.

- frontend/src/pages/StoryReviewPanel.jsx — 3 fetch sites besides the migrated Path D site need Path E spot-check during Step 3 sweep.

- frontend/src/components/AuditLogViewer.jsx — mockLogs fallback. Intentional dev-mode fallback, not a bug. No action needed.

- Disposition pattern (unchanged from v2.6): each is either intentionally PUBLIC (backend route serves unauth-safe data) or a BUG (backend route requires auth and the frontend silently sends none). Step 3 sweep classifies each backend route as PUBLIC or requireAuth; Path E sites whose backend is PUBLIC stay as raw fetch (correct), Path E sites whose backend is requireAuth get migrated to apiClient (Track 6-equivalent fix). No action until Step 3 reaches the corresponding routes. The WorldStudio.jsx cluster (29 sites) is the largest and warrants priority attention during Step 3 sweep — if the backend routes are PUBLIC, no work; if any are requireAuth, that one file becomes a meaningful Track-6-equivalent surface.

Path E running list growth from CP4: FranchiseBrain.jsx GET sites (8 total) filed for Step 3 sweep awareness. CP4 migration applied apiClient (auth-required disposition) under the read that LalaVerse internal knowledge — laws, characters, locked decisions — is canonical-knowledge-class. Step 3 backend audit on franchiseBrainRoutes.js will adjudicate per-route disposition; if any GET is classified PUBLIC, that specific call site can be reverted in a follow-up commit.

- GET /franchise-brain/entries with query-string filters (×6 sites: load, loadCounts ×4, loadSourceCounts)

- GET /franchise-brain/documents (loadBrainDocs)

- GET /franchise-brain/amber-activity (loadAmberActivity)

Path E running list growth from CP5: ~10 GET sites across three mid-tier files filed for Step 3 sweep awareness. CP5 migration applied apiClient (auth-required disposition default) under the read that per-user storyteller / episode / universe data is auth-required. Step 3 backend audit will adjudicate per-route disposition; if any GET is classified PUBLIC, that specific call site can be reverted in a follow-up commit.

- StoryThreadTracker (6 GETs): /storyteller/threads, /storyteller/threads/dangling, /storyteller/memories/pending, /storyteller/continuity/issues, /storyteller/voice-signals, /storyteller/voice-rules

- EpisodeScenesTab (3 GETs): /episodes/:id/scene-sets, /episodes/:id/scenes, /scene-sets

- SeriesPage (3 GETs): /universe/series, /storyteller/books, /shows — the /shows GET is consistent with CP2's migration disposition (already auth-required).

Path E running list growth from CP6: ~13 GET sites across four mid-tier-batch-2 files filed for Step 3 sweep awareness. Distribution: 1 in CharacterGenerator, 4 in CharacterTherapy, 3 in ContinuityEnginePage, 5 in TemplateDesigner. CP6 migration applied apiClient (auth-required disposition default) under the read that per-user character / continuity / template data is auth-required. Step 3 backend audit will adjudicate per-route disposition.

- CharacterGenerator (1 GET): /character-generator/ecosystem

- CharacterTherapy (4 GETs): /character-registry/registries, /character-registry/registries/:id, /therapy/waiting, /therapy/profile/:charId

- ContinuityEnginePage (3 GETs): /continuity/timelines, /continuity/timelines/:id, /continuity/timelines/:id/conflicts

- TemplateDesigner (5 GETs): /episodes, /episodes/:id/assets, /template-studio/:id, /compositions/:id, /thumbnail-templates/:id

Path E running list growth from CP7: ~12 GET sites across ten long-tail batch 1 files filed for Step 3 sweep awareness. Distribution: CFO cluster (5: /cfo/quick, /cfo/scheduler, /cfo/audit, /cfo/agent/:name, /cfo/history); AI usage cluster (4: /ai-usage/summary, /ai-usage/by-model, /ai-usage/by-route, /ai-usage/daily, /ai-usage/optimizations, /ai-usage/recent); world state cluster (3: /world/state/snapshots, /world/state/timeline, /world/tension-scanner); amber diagnostic (2: /amber/diagnostic/findings, /amber/diagnostic/queue); episode todo (2: /episodes/:id/todo, /episodes/:id/todo/social); story health (2: /story-health/dashboard, /story-health/search); session brief (1: /session/brief); character registry (1: /character-registry/registries — already filed by CP3+CP6; same disposition expected). CP7 migration applied apiClient (auth-required disposition default). Step 3 backend audit will adjudicate per-route disposition.

Path E running list growth from CP8: ~13 NEW GET sites filed for Step 3 sweep awareness (3 already filed by CP7 deduplicated). Distribution: arc-tracking (1: /arc-tracking/:key); narrative pipeline (1: /tier/pipeline); world scenes (3: /world/characters, /world/scenes, /world/tension-check); stories character (3: /stories/character/:char, /stories/assemblies/character/:char, /stories/social/character/:char); world locations (3: /world/locations, /world/map, /social-profiles/analytics/composition); memories growth (1: /memories/character-growth/flagged); character-registry: /character-registry/registries — already filed by CP3+CP6+CP7. CP8 migration applied apiClient (auth-required disposition default). Step 3 backend audit will adjudicate per-route disposition.

Path E running list growth from CP9: ~10 NEW GET sites filed for Step 3 sweep awareness (some dedup-noted from CP2/CP5/CP8). Distribution: texture-layer (2: /texture-layer/:char/:story load + refetch); social character (1: /stories/social/character/:char — already CP8); story-health + memories (3: /story-health/therapy-suggestions/:char, /memories/eval-stories/:id, /story-health/threads-for-story/:num); character-registry-by-id (3: /character-registry/characters/:id, /character-registry/characters/:id/relationships, /entanglements/character/:id, /social-profiles/:id); writing-rhythm (2: /writing-rhythm/stats, /multi-product/all); world characters by book (1: /world/characters?book_id=:id); memory-job-status (3: /memories/pipeline-generate-status/:jobId, /memories/batch-generate-status/:jobId, /memories/batch-generate-story/:jobId/:num); shows (2: /shows, /shows/:id — already CP2/CP5). CP9 migration applied apiClient (auth-required disposition default). Step 3 backend audit will adjudicate per-route disposition.

WritingRhythm URL composition observation (NEW v2.16 — separate from Path E; UPDATED v2.17 to note second instance): WritingRhythm.jsx (CP9) and StoryDashboard.jsx (CP10) both use const API = import.meta.env.VITE_API_URL || '' empty default; URLs compose to relative paths without /api/v1/ prefix. apiClient.baseURL is also empty string. CP9 + CP10 migrations preserved both compositions verbatim per v2.16 §9.11 URL composition preserved-verbatim discipline. Step 3 audit should investigate whether the relative-path resolution is intentional (Vite proxy config, server-side rewrite, /api/v1 fall-through) or a pre-existing routing bug. Both files should be adjudicated together (likely the same resolution applies).

Path E running list growth from CP10: ~10 NEW GET sites filed for Step 3 sweep awareness (many dedup-noted from CP3+/CP5/CP6/CP8). Distribution: world (1: /world/context-summary new); character-registry-by-id (2: /character-registry/characters/scene-context/:char new, /character-registry/:registryId/characters new); storyteller chapters (1: /storyteller/chapters new — variable-URL no-bookId branch); scene-proposals + reviews (2: /memories/scene-proposals?:qs new, /reviews/unacknowledged new); template-studio (1: /template-studio?:params new); compositions (1: /compositions/:id/outputs new); character-depth (1: /character-depth/:id new); universe (2: /universe/series new no-query variant, /universe/:id new). Already filed: /character-registry/registries (CP3+CP6+CP7+CP8 — now CP10 6-fold), /storyteller/books (CP5), /memories/character-growth/flagged (CP8), /compositions/:id (CP6), /shows (CP2/CP5/CP7/CP9). CP10 migration applied apiClient (auth-required disposition default). Step 3 backend audit will adjudicate per-route disposition.

Path E running list growth from CP11: ~14 NEW GET sites filed for Step 3 sweep awareness (many dedup-noted from prior CPs). Fresh CP11 first-time candidates: /properties (PropertyManager), /recycle-bin (RecycleBin), /storyteller/calendar/events + /storyteller/calendar/markers (StoryCalendar — storyteller-scoped, distinct from /calendar/* per CP11 surface-correction), /site-organizer/quick + /scan + /agent/:name (SiteOrganizer — admin-tooling, may be intentionally PUBLIC), /world/:show/episodes/:ep/distribution (EpisodeDistributionTab), /page-content/:name (usePageData hook). Dedup-noted: /character-registry/characters/:id + …/relationships (CP9 — CharacterProfile re-files), /social-profiles/:id (CP9 — re-files), /compositions/:id (CP6 — LayoutEditor re-files), /stories/character/:char (CP9 — StoryReviewPanel re-files), /shows (CP2/CP5/CP7/CP9/CP10 — now 5-fold via CultureEvents). CP11 migration applied apiClient (auth-required disposition default). Step 3 backend audit will adjudicate per-route disposition.

URL-string-shape disambiguation note (NEW v2.18 §9.12 — CP11 surface-correction). Surface analysis must inspect API base composition, not just URL fragments. CP11 surface initially flagged StoryCalendar's ${API}/calendar/events as a CP10 CulturalCalendar duplicate based on URL-string shape similarity. Migration revealed StoryCalendar imports API from a constants module where API = '/api/v1/storyteller'; full URL resolves to /api/v1/storyteller/calendar/events, distinct from CP10's global /api/v1/calendar/events. Helpers were FRESH, not duplicates. Discipline: at surface time, read the import statement for the API base constant; resolve the full URL; only then decide if a cross-CP duplicate exists. CP11 caught this mid-flow; future surface reports should catch it before lock.

CP12 Path E dedup outcome (NEW v2.19 §9.12). /memories/extract-story-memories POST was already filed in v2.18 §9.12 from Track 3 surface (long before CP12). CP12 migration applied apiClient at this site (auth-required default) — site is now covered by extractStoryMemoriesApi helper in useStoryEngine.js. Dedup-noted from Track 3 filing; same disposition expected. Step 3 backend audit will adjudicate per-route disposition. No new Path E candidates from CP12 (all 14 sites have either unique paths covered by 12 fresh helpers OR are covered by the Track 3 prior filing; the 1 cross-CP duplicate listStoriesForCharacterApi was already filed via CP9/CP11).

Path E running list growth from CP13 (NEW v2.20 §9.12). ~4 NEW GET sites filed for Step 3 sweep awareness (3 dedup-noted from prior CPs). Fresh CP13 first-time candidate: /wardrobe/:id/usage GET (WorldAdmin getWardrobeUsageApi). Dedup-noted from prior CPs: /episodes/:id/todo/social GET (CP9 EpisodeTodoPage — now CP9+CP13 2-fold), /world/:show/events GET (service-module precedence inversion — multiple downstream component consumers, no single CP origin), /shows/:show/wardrobe GET (wardrobeService.js + 7 component consumers — service-module precedence inversion). CP13 migration applied apiClient (auth-required disposition default). Step 3 backend audit will adjudicate per-route disposition.

Path E running list growth from CP14 (NEW v2.21 §9.12). ~3 NEW GET sites filed for Step 3 sweep awareness (1 dedup-noted from prior CPs). Fresh CP14 first-time candidates: /episodes/:id/library-scenes GET (EpisodeDetail listEpisodeLibraryScenesApi — 4× call-site reuse), /characters/:char/state GET (EpisodeDetail getCharacterStateApi). Dedup-noted from prior CPs: /world/:show/events GET (CP13 WorldAdmin file-local capture — now CP13+CP14 2-fold cross-CP existence). CP14 migration applied apiClient (auth-required disposition default). Step 3 backend audit will adjudicate per-route disposition.

Path E running list growth from CP15 — TRACK 6 FINAL STATE (NEW v2.22 §9.12). ~15 NEW GET sites filed + ~10 dedup-noted from prior CPs. Track 6 Path E final state recorded for Step 3 backend sweep phase. Fresh CP15 first-time candidates: /design-agent/scan + /design-agent/agent/:name GETs (DesignAgent), /world/map/positions GET + PUT (DreamMap), /world/map GET (EpisodeScriptTab), /world/:show/distribution-defaults GET + PUT (ShowDistributionTab), /therapy/dilemmas GET + /therapy/dilemma-profile POST (CharacterDilemmaEngine), /memories/books/:id/scenes GET (ScenesPanel), /memories/relationship-map GET (RelationshipEngine WebView), /memories/script-metadata POST (ScriptIntelligencePanel), /memories/generate-script-from-book POST (ScriptBridgePanel), /memories/ai POST (FeedEnhancements), /wardrobe?limit=* GET + /outfit-sets GET (OutfitCalendar), /character-registry/registries/default GET (ChapterJourney — distinct from /registries). Dedup-noted: /storyteller/books/:id GET (3-fold via ChapterStructureEditor), /social-profiles?qs GET (CP9 dup), /character-registry/registries GET (now 8-fold via MemoryBankView + useRegistries — exceeds v2.17 §9.11 6-fold soft ceiling), /page-content/:name GET (3-way reuse at WorldSetupGuide), /calendar/events?qs GET (CP10/CP11 dup), /world/locations GET (CP8/CP11 dup), /shows GET (now 6-fold via UniverseProductionPage + WorldSetupGuide — meets ceiling exactly). CP15 migration applied apiClient (auth-required disposition default). Track 6 Path E running list complete; Step 3 backend audit will adjudicate per-route disposition for the entire accumulated list across CP2-CP15.

HTTP method mismatch tally — TRACK 6 FINAL STATE (UPDATED v2.22). CP15 is the 14th consecutive CP with zero method mismatches (CP3-CP15 cumulative). Track 6 implementation closes with the streak intact. Total method-correction discoveries: 5 across 15 CPs: 3 from CP2 mid-flow (setCoverAngleApi GET → PATCH, reorderAnglesApi POST → PATCH, getAiCameraDirectionApi GET → POST), 1 from CP7 surface (CFOAgent setBudget POST → PUT), 1 from CP9 surface verification. Pattern remains: file-level variation, not systemic. Track 6 final summary: 14 of 15 CPs surfaced zero method mismatches. The 5 method-correction discoveries are filed for Step 3 backend audit; backend routes should be verified against frontend usage post-migration.

HTTP method mismatches surfaced during Track 6 CP2 (3 sites in SceneSetsTab.jsx) — Step 3 sweep awareness items:

- setCoverAngleApi — backend route is PATCH; frontend was using GET. Migration uses correct PATCH per backend contract. Step 3 should verify the backend route's expected method matches what other consumers (if any) send.

- reorderAnglesApi — backend route is PATCH; frontend was using POST. Migration uses correct PATCH.

- getAiCameraDirectionApi — backend route is POST; frontend was using GET. Migration uses correct POST.

- These are pre-existing wrong-method sites that were either tolerated by the backend (e.g., Express router accepting both methods, or the backend's body-parser silently doing the right thing on POST-with-no-body) or never hit execution in the path the frontend was reaching. Migration to apiClient documents and uses the correct method. The original wrong methods have been shipping; verifying via Step 3 sweep that no other callers depend on the wrong method behavior is sound discipline. Surface, do not fix the original — apiClient migration is itself the fix at the call site.

## 9.13 Lost-work incident (May 2, 2026) + cleanup discipline

### What happened

Three approved F-AUTH-1 implementation commits were lost when the Claude Code container holding them was reset before the work was pushed to origin:

- 23c9ffd — Step 6a: BookEditor.jsx sendBeacon → fetch+keepalive

- 54d4d09 — Step 2 initial: F-Auth-3 three-case classifier + Error.cause preservation

- ab2ce44 — Step 2 amendment: degradeOnInfraFailure flag + four-case unit tests

All three commits were verified real (not generated text) in their original session via git show --stat. They lived only in the local container's .git object store. Per the standing constraint "do NOT push to a PR yet," no push was made. The constraint was meant to prevent premature PR opening; it was incorrectly extended to mean no push at all. When the container was replaced before the F-AUTH-1 PR was ready, the three commits became unrecoverable — not present in any ref of any clone with origin access.

### Recovery

- Original SHAs are documented in §9.11 as historical-only references. They will not appear in the eventual F-AUTH-1 PR commit graph.

- All implementation decisions reached during the lost work are preserved in this fix plan: §4.2 (Step 2 spec including degradeOnInfraFailure flag, Error.cause preservation, structured log schema with degraded field, four-case test requirement) and §4.6 (Step 6a CZ-5 spec).

- Re-implementation runs against the locked v1.7 spec, not from the original transcripts. If the new implementation diverges from the locked spec, fix plan amendment is the correct path — not "the original commit did it differently."

### Cleanup discipline (LOCKED at v1.7, applies to all future F-AUTH-1 implementation work and all post-F-AUTH-1 fix work)

Rule 1 — One Claude Code session at a time touches dev.

- If multiple Claude Code sessions are open, only one is the "writer" — the others are read-only. Writer is named at the start of each work block and stays the writer for the duration. Other sessions can read and diagnose but do not commit.

Rule 2 — Every approved commit on feature/f-auth-1 (or any feature branch) gets pushed immediately to a backup branch.

- Backup branch name: claude/f-auth-1-backup (single, not date-stamped). Force-push is allowed; that is its purpose. Always points at the latest approved state.

- The push happens the same turn as approval, not "at the end of G2," not "next session," not "before opening the PR." Same turn.

- Command: git push origin feature/f-auth-1:claude/f-auth-1-backup --force

Rule 3 — The canonical feature branch name stays clean for the eventual PR.

- feature/f-auth-1 (or future feature/f-app-1, feature/f-stats-1, etc.) is pushed to origin only when the PR opens. Until then, all backups go to claude/<feature>-backup.

Rule 4 — No PR opened until all steps are committed and approved.

- Push-to-backup is not a PR. The "do NOT open a PR yet" constraint stays. The "do NOT push" misinterpretation is rejected.

Rule 5 — If a session container looks unstable, push backup before logging off.

- Indicators: container about to reset (rare warnings), switching machines, end of work session, network instability. When in doubt, push backup.

Rule 6 — Auto-merge pipeline documented (added v2.4).

Prime Studios runs an automation pipeline that integrates implementation work into dev continuously. Future Claude Code sessions need to understand this so backup-branch advancement and dev's docs/audit/ state are not mistaken for discipline slips. The pipeline has four parallel writers:

- Implementation track (this writer): commits to feature/f-auth-1, force-pushes to claude/f-auth-1-backup after each track approval per Rule 2.

- Auto-merge track (automation): commits like Auto-merge claude/f-auth-1-backup into dev fire on every backup-branch push, replaying implementation commits onto dev.

- Fix-plan revision track (integrator, TySteamTest): commits like docs(audit): F-AUTH-1 fix plan vX.Y go directly to dev after each fix-plan version locks. These flow to main via standard PR.

- Main-sync track (integrator): periodic Merge origin/main into claude/f-auth-1-backup commits keep backup's docs view consistent with main's preserved version history. Touches only docs/audit/ files; no implementation conflict.

Implications for the implementation writer (this session):

- Force-pushing backup overwrites the integrator's main-sync merge commits. This is safe because the docs they brought in already exist on main and (via the auto-merge chain) on dev. No data loss.

Dev's docs/audit/ directory is the union of: dev-tip cleanup state + main's preserved version history (via merge chain). When v1.5 or v2.2 reappear in git ls-tree origin/dev it is the merge chain working as designed, not a regression. Each individual fix-plan revision commit on dev still does its git rm of the prior version (cleanup discipline at the commit level); the merges from main re-introduce older versions as historical record.

- Rule 1 (one writer at a time) still holds for implementation work on feature/f-auth-1. The auto-merge / main-sync / fix-plan-revision writers operate on different branches or different paths and do not conflict with implementation commits. If a future session is uncertain whether something is "another writer touching my work" vs "the pipeline doing its thing," check whether the surprising commit touched any implementation file (frontend/src/, src/middleware/, tests/). If only docs/audit/ files are touched, it is the pipeline.

- When in doubt, run `git log <branch> --oneline` and look for the four commit-message patterns above. They identify the writer and confirm the work is benign.

### Why this is in the canon document

The audit principle from v8 §0 holds: the audit trail is the audit trail. Future Claude Code sessions reading this fix plan will see the lost-work incident and the discipline that followed it. Future sessions will be less likely to repeat the same failure mode because they read about it before starting work. This is operational learning made durable — exactly the use case "documentation as a living system" exists for.

The Rule 6 addition (v2.4) is a second instance of this principle. The auto-merge pipeline was not visible to this session's author until commit a8877a19 surfaced as backup-branch advancement; without diagnostics we could have mistaken it for a session-coordination failure and force-overwritten benign integrator work. Documenting the pipeline now means future sessions read v2.4 and understand the data flow before they have to diagnose it.

# 10. What This Unblocks

Per v8 §4.1: every other P0 fix touches mutation routes. With F-AUTH-1 closed, the next-fix queue opens. The audit-locked sequence (§4 of v8) is:

| Tier | Keystone | Why it can ship after F-AUTH-1 |
| --- | --- | --- |
| 1 | F-App-1 | Schema-as-JS auto-repair removed from app.js:262–328. Structural prerequisite for F-Sec-3 and any character_state UNIQUE migration. Decision #47. |
| 1 | F-Stats-1 | Build the missing CharacterState Sequelize model. Prerequisite for any F-Sec-3 cleanup. Decision #54. |
| 1 | F-Ward-1 | Write the migration that captures episode_wardrobe canonical schema. Decision #59. |
| 1 | F-Reg-2 | Address registry_characters write-contention. Pattern 41 master. |
| 1 | F-Ward-3 | Delete the plural outfit-set controller (the routes the F-AUTH-1 sweep just protected). Decision #60. |
| 1 | F-Sec-3 | Canonical-key consolidation. Subordinate to F-Franchise-1 per Decision #94. Blocked on F-App-1, F-Stats-1, F-Ward-1, AND F-Franchise-1. |
| 1 | F-Franchise-1 | Director Brain build. The keystone fix for the disconnection between franchise tier and show tier. Decision #94. Builds the consumer wiring that routes Universe.pnos_beliefs, world_rules, narrative_economy, and core_themes into the production pipeline that currently runs on six private JS-literal copies. |

Director Brain framing Director Brain is not a feature being built late. Per v8 §1.2 and Decision #94, Director Brain is the audit-recommended fix for F-Franchise-1. Its scope is now defined precisely: build the consumer wiring that the franchise tier was scaffolded for. The seeded spec at seeders/20260312800000-show-brain-franchise-laws.js:335 already names its capabilities. The audit names its input contract. F-AUTH-1 is the foundation that makes shipping any of this safe.

# 11. Appendix A — File:line Reference Card

All references derived from Prime Studios Audit Handoff v8. Pre-flight (§5.1) confirmed each at G1 closure. Drift from v8 noted inline below. v8 closed May 1, 2026; codebase has shifted slightly. Sweep regex still works because patterns hold; specific line numbers do not.

Drift summary (G1 pre-flight) app.js:364 (v8) → src/app.js:330 (current). −34 lines. episodeOrchestrationRoute.js:135 (v8) → :131 (current). −4 lines. wardrobe.js:895, :970 (v8) → :1215, :1325 (current). +320, +355 lines. storyteller.js individual lines drifted across the whole file. Pattern holds via grep regex. All other audit references match within ±5 lines or exactly.

### Auth module (middleware/auth.js)

- :13–22 — Cognito verifier construction with placeholder fallback (F-Auth-2 surface)

- :44–46 — runtime env-var check inside verifyToken (the check that fires too late)

- :164–168 — optionalAuth swallows all errors (F-Auth-3 surface)

- :256–293 — duplicate authenticateToken implementation (F-Auth-4 surface)

### Global mount

- app.js:364 — global app.use(optionalAuth) (sub-form a root)

### Sub-form (a) — confirmed surfaces

- storyteller.js:38–43, 53, 113, 192, 213, 241, 263, 312, 333, 354, 553, 615, 636, 663, 738, 769, 790, 826, 856, 880, 910

- characterRegistry.js:12–22 (require-with-fallback), ~600 (isAuthor gate), ~1700-line file with requireAuth on one route only

- evaluation.js:587 (Stats save)

- careerGoals.js — every mutation route

- uiOverlayRoutes.js — every mutation route

- calendarRoutes.js — event CRUD, auto-spawn, world-event spawn

- franchiseBrainRoutes.js — 10 mutation routes (entries CRUD, activate, activate-all, archive/unarchive, ingest-document, guard, seed)

- wardrobe.js:895 (/select), :970 (/purchase)

### Sub-form (b) — confirmed surfaces

- routes/outfitSets.js — all 5 routes, no auth import

- routes/episodes.js:101, :109, :117 — plural outfit-set controller mounts

### Sub-form (c) — confirmed surfaces

- episodeOrchestrationRoute.js:135 (declares optionalAuth) → :220 (writes orchestration_data)

### CZ-5

- BookEditor.jsx:173–186 — sendBeacon beforeunload save

### F-Auth-5 — sites to swap (Step 6c)

- decisionLogs.js:22 — req.user?.sub → req.user?.id

- cursorPathController.js:22 — same pattern

- iconCueController.js:22 — same pattern

- musicCueController.js:20 — same pattern

- productionPackageController.js:22 — same pattern

- thumbnails.js:80 — drop fallback chain entirely; replace with const userId = req.user.id;

### F-Auth-4 — call sites to migrate (Step 6b)

- 103 mount sites across 17 files (full inventory in pre-flight report §14.1)

- Top-volume: episodes.js (14), stories.js (9), search.js (9), notificationController.js (9), thumbnails.js (7), socketController.js (7), activityController.js (7)

- Lazy-import fallbacks to update: characterRegistry.js:17, worldEvents.js:28

- Dead alias to drop: middleware/auth.js:237 (Decision D21)

### Absorbed findings (G1) — closed by existing steps

- D17 / D19 — episodes.js:307–315 PUT /:id (closes via Step 3 + Step 6b)

- D18 — episodes.js:400 PUT /:episodeId/scenes/reorder, :473 POST /:episodeId/scripts (authenticateToken commented out for "TESTING"; closes via Step 4)

### Out-of-scope — LOCKED, do not touch

- jwtAuth.js + its 9 callers at routes/auth.js:10 and routes/compositions.js:20 (Decision D20). Separate verification path; folding it into Step 6b is scope explosion, not consolidation.

# 12. Appendix B — Glossary

- F-AUTH-1 — Tier 0 keystone in v8. Codebase-wide auth bypass on writes. Three sub-forms.

- F-Auth-2 — middleware/auth.js module-load placeholder fallback (Step 1).

- F-Auth-3 — optionalAuth cannot distinguish "Cognito down" from "anonymous user" (Step 2).

- F-Auth-4 — requireAuth and authenticateToken are duplicate logic with one differing string (Step 6b).

- F-Auth-5 — req.user.id vs req.user.sub split-brain at decisionLogs.js:22. Folded into the F-AUTH-1 PR as Step 6c.

- F-Auth-6 — tokenUse captured but not gated. Non-blocking; informs the recipe.

- F34 — unauthenticated destructive writes on /franchise-brain/*. Subset of sub-form (a). Closes automatically in Step 3.

- CZ-5 — sendBeacon cannot carry Authorization headers. BookEditor beforeunload save data-loss risk (Step 6a).

- Sub-form (a) — write routes currently using optionalAuth. The v6 keystone form.

- Sub-form (b) — write routes with NO auth middleware declared. Zone 23 finding.

- Sub-form (c) — write routes that explicitly declare optionalAuth on mutation paths. Zone 26 finding.

- F-Franchise-1 — 7th keystone in v8. Director Brain build resolves it. Sequenced after F-AUTH-1.

- jwtAuth.js — separate verification path (custom JWT via TokenService, not Cognito). 9 production mounts. Out of F-AUTH-1 scope per Decision D20.

- D17 — episodes.js:307–315 PUT /:id uses optionalAuth as a workaround for the F-Auth-4 contract problem. Closed by Step 6b.

- D18 — episodes.js:400 + :473 have authenticateToken commented out for "TESTING" in production. Currently shipping unauth. Closed by Step 4.

- D19 — episodes.js PUT /:id at :313 tolerates missing token. Same root cause as D17; one fix closes both.

- D20 — jwtAuth.js disposition. LOCKED out of F-AUTH-1 scope. Architectural follow-up filed.

- D21 — middleware/auth.js:237 exports an unused authenticate alias. LOCKED to drop in Step 6b cleanup.

- §9.9 — Deploy infrastructure: dev + prod only, no staging. G4 absorbs former G5 soak responsibility. Locked at G1.

- §9.10 — Cognito pool unification: dev and prod share one Cognito User Pool/Client ID. Discovered at G1, deferred to post-F-AUTH-1. Trigger: split before any beta tester signs up.

— end of document —